## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/03/25/08/WP/KTR | RR/RDA/03/25/08 | Asphalting from near Valkandala transformer to Panthiya Watta (Malamiriskanda road) | Kalutara | Agalawatta | Accon Engineering (PVT) LTD | 100% | 14577590.15 | 22843424.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-15
RR/RDA/03/25/09/WP/KTR | RR/RDA/03/25/09 | Concreting of Weedahena road | Kalutara | Agalawatta | Develco Engineering (PVT) LTD | 100% | 15010244 | 19919301.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/03/25/36 |  | 10 Mw T Jayarathne mahathge niwas asala concrete kara nawatha ati sthanaya sita nawa margaya desata | Kalutara | Agalawatta |  | 100% | 34917696.41 | 34917696.41 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/03/25/13 |  | Morapitiya Aluth Mawatha to 1st mile post via Rankoth lane | Kalutara | Agalawatta |  | 100% | 38713954.65 | 38713954.65 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2026-02-28