## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/20/25/05/NCP/ANP | RR/RDA/20/25/05 | Meda oyamaduwa handiye sita ehetuwawa dakwa margaya | Anuradhapura | Anuradhapura | D.M.C. CONSTRUCTION (PVT) LTD | 100% | 37593399.55 | 56374105.66 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-02-23
RR/RDA/20/25/12/NCP/ANP | RR/RDA/20/25/12 | Thalakolawewa carpert margaye awasanaye sita kudagama haraha dakunu ela iuwra margaya | Anuradhapura | Anuradhapura | CS Construction | 100% | 37091276.8 | 49135056.85 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27
RR/RDA/20/25/14/NCP/ANP | RR/RDA/20/25/14 | Kukulewa pansala asalin arambavee samadhigama haraha seeppukulama rambewa maragaya dakwa divena pare pasala asala sita margaya | Anuradhapura | Anuradhapura | Kumari Konthrathkaruwo | 100% | 29296077 | 44635822.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-04-10
RR/RDA/20/25/02 |  | Anuradhapura - Kurunegala pradana pare paththara kade handiyen aramba vee kodigala dakwa diwena margaya | Anuradhapura | Anuradhapura |  | 100% | 50844733.35 | 50844733.35 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-07-06 |  | 2025-10-30
RR/RDA/20/25/21 |  | Pawithrapura Road | Anuradhapura | Anuradhapura |  | 100% | 32078244.1 | 32078244.1 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-30 |  | 2026-02-15
RR/RDA/20/25/17 |  | Galwaduwawa Junction to Yaya 02 road of Thambuththegama Eppawala Road | Anuradhapura | Anuradhapura |  | 100% | 64398698.77 | 64398698.77 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2026-02-26
RR/RDA/20/25/19 |  | Thalawa Tsunami junction to Indigaspathana road of Padeniya Anuradhapura Road | Anuradhapura | Anuradhapura |  | 100% | 64760087.22 | 64760087.22 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-22 |  | 2026-03-31