## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/20/25/01/NCP/ANP | RR/RDA/20/25/01 | Road from Thambuttegama - Nochchiyagama road to the road near the DIG's office of Thambuthegama Rajanganaya | Anuradhapura | Anuradhapura | Creates Consultant and Construction | 30% | 96940000 | 147079527.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-09-03
RR/RDA/20/25/03/NCP/ANP | RR/RDA/20/25/03 | Thalawa - Eppawala margaye kele Amunukola handiyen aramba vee kele amunukola viddiyalayen divena margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 40% | 26155768.37 | 41286372.1 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-30
RR/RDA/20/25/04/NCP/ANP | RR/RDA/20/25/04 | A - 9 maragayen aramba vee wale kade dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 45% | 27008370.51 | 43911304.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-06-15
RR/RDA/20/25/05/NCP/ANP | RR/RDA/20/25/05 | Meda oyamaduwa handiye sita ehetuwawa dakwa margaya | Anuradhapura | Anuradhapura | D.M.C. CONSTRUCTION (PVT) LTD | 100% | 37593399.55 | 56374105.66 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-02-23
RR/RDA/20/25/11/NCP/ANP | RR/RDA/20/25/11 | Palayakulama sita halmillakulama dakwa margaya | Anuradhapura | Anuradhapura | Dissanayaka Builders | 75% | 20887268.2 | 33233870.01 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-05-30
RR/RDA/20/25/12/NCP/ANP | RR/RDA/20/25/12 | Thalakolawewa carpert margaye awasanaye sita kudagama haraha dakunu ela iuwra margaya | Anuradhapura | Anuradhapura | CS Construction | 100% | 37091276.8 | 49135056.85 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27
RR/RDA/20/25/14/NCP/ANP | RR/RDA/20/25/14 | Kukulewa pansala asalin arambavee samadhigama haraha seeppukulama rambewa maragaya dakwa divena pare pasala asala sita margaya | Anuradhapura | Anuradhapura | Kumari Konthrathkaruwo | 100% | 29296077 | 44635822.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-01-27 | 2026-04-10
RR/RDA/20/25/18/NCP/ANP | RR/RDA/20/25/18 | Pahala Talawa road of Thalawa Andarawewa road | Anuradhapura | Anuradhapura | HPS Construction | 80% | 32443580.5 | 46999616.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-07 | 2026-06-30
RR/RDA/20/25/20/NCP/ANP | RR/RDA/20/25/20 | Development of the road from near the Siri Sambodhi Viharaya, 4th Mile post, on the Airport Roundabout Road to the house of Mr. Peme | Anuradhapura | Anuradhapura | HPS Construction | 70% | 38820000 | 58718404.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-16 | 2026-12-15
RR/RDA/20/25/26/NCP/ANP | RR/RDA/20/25/26 | Development of IV lane from Nuwara Road to Mihinthalaya Road | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 6% | 29650453.29 | 38283840.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-02
RR/RDA/20/25/28/NCP/ANP | RR/RDA/20/25/28 | Development of Rathnayake Mawatha | Anuradhapura | Anuradhapura | Priyantha Civil Engineering | 5% | 23041750.8 | 30142796.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-02-11
RR/RDA/20/25/02 |  | Anuradhapura - Kurunegala pradana pare paththara kade handiyen aramba vee kodigala dakwa diwena margaya | Anuradhapura | Anuradhapura |  | 100% | 50844733.35 | 50844733.35 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-07-06 |  | 2025-10-30
RR/RDA/20/25/21 |  | Pawithrapura Road | Anuradhapura | Anuradhapura |  | 100% | 32078244.1 | 32078244.1 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-30 |  | 2026-02-15
RR/RDA/20/25/17 |  | Galwaduwawa Junction to Yaya 02 road of Thambuththegama Eppawala Road | Anuradhapura | Anuradhapura |  | 100% | 64398698.77 | 64398698.77 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2026-02-26
RR/RDA/20/25/19 |  | Thalawa Tsunami junction to Indigaspathana road of Padeniya Anuradhapura Road | Anuradhapura | Anuradhapura |  | 100% | 64760087.22 | 64760087.22 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-22 |  | 2026-03-31