## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/22/25/12/UP/BDL | RR/RDA/22/25/12 | Galwelagama Margaye Pansala Asala Kotasa | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 16955320.78 | 19698086.11 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/22/25/14/UP/BDL | RR/RDA/22/25/14 | Pulleyar Kadura sita Keselwaththa Dakwa Piwisena Athrur Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 6085915 | 7780120.14 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/15/UP/BDL | RR/RDA/22/25/15 | Gallulla sita Galwelagama Margaya | Badulla | Badulla | Ema Constructions (Pvt) Ltd | 100% | 15696340 | 19949882.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-07 | 2026-01-06
RR/RDA/22/25/18/UP/BDL | RR/RDA/22/25/18 | Pelgahathenna Vidyalaya asalin Landewela dakwa athi Margaya | Badulla | Badulla | Prasad Builders | 100% | 5317232 | 6839881.74 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/19/UP/BDL | RR/RDA/22/25/19 | Tholabowaththa sita Meedumpitiya Dakwa yana Athuru Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 30478561.74 | 47901120.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/16 |  | Dameria Handiye sita wathu Karyalaya Dakwa Margaya | Badulla | Badulla |  | 100% | 12215323.92 | 12215323.92 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/22/25/13 |  | Peessa Pradana Margaye Abalan wu Ellanda Marga Kotasa | Badulla | Badulla |  | 100% | 13192586.35 | 13192586.35 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2026-02-06