## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/01/25/03/WP/COL | RR/RDA/01/25/03 | Appropriate development of road from Maligagodella lake crossing near Isuri Motors to junction with Chandrika Kumaratunga Mawatha | Colombo | Colombo | Jayasinghe Contractors (Pvt) Ltd. | 100% | 23009836.05 | 31303935.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-16 | 2026-01-29
RR/RDA/01/25/14/WP/COL | RR/RDA/01/25/14 | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | Colombo | Colombo | W.A. Perera & Company (Pvt) Ltd. | 68% | 33591596.5 | 51359519.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-10 | 2026-05-12
RR/RDA/01/25/12/WP/COL | RR/RDA/01/25/12 | 550 A Lakshapathi North Sri Lanka Army Electrical and Mechanical Engineering Base Workshop (Katupedda) to be carpeted and developed from Galle Road. | Colombo | Colombo | Accon Engineering (PVT) LTD | 100% | 8465142.73 | 11014256.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-02-12 | 2025-12-29
RR/RDA/01/25/30/WP/COL | RR/RDA/01/25/30 | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Colombo | Colombo | Asset Engineering (Pvt)LTD | 0% | 21619184.95 | 22641802.22 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-30 | 2026-08-29
RR/RDA/01/25/11 |  | Vijitha Salawa asala sita Kothalawala Vidyalaya Asalin Gothami Viharaya dakva Margaya | Colombo | Colombo |  | 100% | 17512654.33 | 17512654.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/01/25/02 |  | Paving and developing the road from North Borella Ganga Lower Vivekaramaya Temple to Siwali Lane No. 241/35D. | Colombo | Colombo |  | 100% | 3636186.59 | 3636186.59 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-17
RR/RDA/01/25/16 |  | Bangalawa Road from 01st Gate to 04th Gate | Colombo | Colombo |  | 100% | 18170451.82 | 18170451.82 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01
RR/RDA/01/25/21 |  | Development of Yakala Cemetery Road up to Welihinda Bridge by carpeting | Colombo | Colombo |  | 5% | 9242749.23 | 9242749.23 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-03-07 |  | 2026-03-30
RR/RDA/01/25/24 |  | Development of the road from the beginning of the Horahena road from Wanaguru Mawatha in the Hokandara East Division to the Hokandara Pasmanhandiya with a carpet | Colombo | Colombo |  | 100% | 3140831.06 | 3140831.06 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-03-07 |  | 2026-04-12
RR/RDA/01/26/10KM/04 |  | Carpeting and development of Vijithapura Liyanage Mawatha and 3rd Lane | Colombo | Colombo |  | 100% | 1560361.91 | 1560361.91 | Awarded | DL Stage 04 | Yes | Yes | Yes