## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/01/AKK/AMP | RR/RDA/16/25/01 | Samanalathenna- Road from House No.63 To the Monastery Muwagammana -From First Lane to Cemetry | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 21336681.87 | 36719169.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-24 | 2025-12-24
RR/RDA/STA II/16/25/02/AKK/AMP | RR/RDA/STA II/16/25/02 | Concreting entrance road with culvert at Dehiaththakandiya Kelegama | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 30737790.6 | 47778623.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-25
RR/RDA/16/25/02 |  | Muwagammana First Lane to Cemetry | Ampara | Dehiaattakandiya |  | 100% | 37324257.12 | 37324257.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-16 | 2025-11-30