## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/08/08/SP/MTR | RR/RDA/25/08/08 | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Matara | Deniyaya | Induwara Construction | 100% | 11168036 | 14394112.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-16
RR/RDA/08/25/19/SP/MTR | RR/RDA/08/25/19 | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Matara | Deniyaya | Gamage Builders | 100% | 10371473.2 | 14049577.09 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-12-16
RR/RDA/25/08/01 |  | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara | Matara | Deniyaya |  | 100% | 78061393.44 | 78061393.44 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-15 | 2026-01-31