## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/26/10KM/14 | RR/RDA/07/26/10KM/14 | Kodagoda Thudugala Road | Galle | Galle | Jayathissa Construction | 0% | 43914369.51 | 49447887.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/18 | RR/RDA/07/26/10KM/18 | Expansion of Alikehena Road from Thalawa Junior College to Atakohota border | Galle | Galle | S.A.Construction | 0% | 32247273.3 | 34701241.47 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-24 | 2026-12-24
RR/RDA/07/26/10KM/20 | RR/RDA/07/26/10KM/20 | Development of Paramount City Road. | Galle | Galle | EHL Constructions | 0% | 17088929 | 21005952.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21
RR/RDA/07/26/10KM/21 | RR/RDA/07/26/10KM/21 | Concretisation of Dikhena Welamedda road up to Addunkelle with 2 culverts and side walls on both sides. | Galle | Galle | Isula Construction | 0% | 37684669 | 44235916.42 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21