## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
| RR/RDA/02/25/15 | Udupila South Dolewatta | Gampaha | Gampaha | Creates Consultant and Construction | 0% | 7423117.7 | 8968820.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-04-15 | 2026-07-14
RR/RDA/02/25/18/WP/GAM | RR/RDA/02/25/18 | Peliyagoda Naranminiya Road | Gampaha | Gampaha | Ceylux Civil engineering (Pvt) Ltd | 0% | 19082810 | 24821169.03 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-26 | 2026-10-20
| RR/RDA/02/25/22 | 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Gampaha | Gampaha | Yagoda Construction | 0% | 11473274.8 | 12991931.82 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-29 | 2026-10-29
RR/RDA/02/25/02 |  | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Gampaha | Gampaha |  | 100% | 10523274.77 | 10523274.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/02/25/07 |  | Road near Ozon Educational Institiute | Gampaha | Gampaha |  | 100% | 12058540.61 | 12058540.61 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-27 |  | 2025-11-05