## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/31/CP/KY | RR/RDA/04/25/31 | Shantha Janapada Village middle road | Kandy | Gampola | Ajith Construction | 100% | 42357645 | 47278636.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-05 | 2026-03-20
RR/RDA/04/25/33/CP/KY | RR/RDA/04/25/33 | New forest kotase Jana Udana gammana margaya | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 6992144.5 | 12512939.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/18 |  | Dewaraja Mw (Balance Work) | Kandy | Gampola |  | 100% | 29009072.8 | 29009072.8 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/40 |  | Lanka bankuwa asala sita Unambuwa dakwa diwena margaya thara damima | Kandy | Gampola |  | 100% | 21307459.69 | 21307459.69 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-10-01