## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/21/25/03/NCP/POL | RR/RDA/21/25/03 | Mahasenpura pradeepika kadaya asala sita Katukeliyawa dakwa margaya Carpart kireema | Polonnaruwa | Habarana | Nadun Construction (Pvt) Ltd | 80% | 33480137.33 | 53473343.43 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-11 | 2026-04-10