## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/06/25/34/CP/NE | RR/RDA/06/25/34 | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 54639783.83 | 84599211.7 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/38/CP/NE | RR/RDA/06/25/38 | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 38465634.79 | 54713411.13 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/40/CP/NE | RR/RDA/06/25/40 | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | Nuwara Eliya | Hanguranketha | UGD Constructions | 10% | 31672222.12 | 35044851.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/06/25/44 |  | Carpeting of Muloya Main Road Section 2 | Nuwara Eliya | Hanguranketha |  | 60% | 42312390.95 | 42312390.95 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-22 | 2025-12-31 | 2026-03-15
RR/RDA/06/25/47 |  | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala | Nuwara Eliya | Hanguranketha |  | 38% | 28020844.83 | 28020844.83 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-31 | 2026-03-15