## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
| RR/RDA/06/25/45 | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Nuwara Eliya | Hanguranketha | Ajith Construction | 10% | 61551869.38 | 68311664.39 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
| RR/RDA/06/25/46 | Carpeting of Mahathenna to Hapugasdeniya Main Road | Nuwara Eliya | Hanguranketha | Ajith Construction | 73% | 68070000 | 79957655.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
RR/RDA/06/25/33 |  | Mool oya Main Road Section 1 | Nuwara Eliya | Hanguranketha |  | 100% | 59668203.37 | 59668203.37 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-30