## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/08/SP/GAL | RR/RDA/07/25/08 | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | Galle | Hiniduma | EHL Constructions | 100% | 27637049 | 39100160.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-09
RR/RDA/07/25/09/SP/GAL | RR/RDA/07/25/09 | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Galle | Hiniduma | DGSD Construction | 98% | 28039359.88 | 42959652.18 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-03-31
RR/RDA/07/25/15/SP/GAL | RR/RDA/07/25/15 | Dikhena Margaya | Galle | Hiniduma | Thilak Kumara Builders | 100% | 34817376.22 | 51022213.05 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/20/SP/GAL | RR/RDA/07/25/20 | Road from Kammale Kadaya Junction to Udumalagala Juunction | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 100% | 25272045.84 | 40743279.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-30
RR/RDA/07/26/10KM/05 | RR/RDA/07/26/10KM/05 | Widening and Development of the road from Angaliya Junction to Akuratiya Hill with culverts | Galle | Hiniduma | EHL Constructions | 0% | 36101846 | 32752577.91 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/08 | RR/RDA/07/26/10KM/08 | Development of 700 meters from Baddegama Vanduramba Road near Kola Kids Preschool and 300 meters from Temple Junction towards Dolahena | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 16745721.52 | 19813729.63 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/12 | RR/RDA/07/26/10KM/12 | 9 Pillar Junction to Mr. Asanka's Shop on Udubattawa Watta Road | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 17311725.2 | 19631662.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/22 | RR/RDA/07/26/10KM/22 | Kapalwila Olympus Waththa I.K. Road from Mr. Sunil's house to Rakshana Village Bodhi near Ketagoda Kada. | Galle | Hiniduma | Woshitha Engineering(Pvt)Ltd | 0% | 18381732.6 | 22218525.7 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/25/16 |  | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima | Galle | Hiniduma |  | 100% | 30597079.78 | 30597079.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/07/25/18 |  | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima | Galle | Hiniduma |  | 100% | 27525465.5 | 27525465.5 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/21 |  | Asphalting Newungala Na tree to Bedimeda road | Galle | Hiniduma |  | 100% | 35369824.16 | 35369824.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-18 | 2026-03-20 | 2026-02-15