## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/26/10KM/05 | RR/RDA/07/26/10KM/05 | Widening and Development of the road from Angaliya Junction to Akuratiya Hill with culverts | Galle | Hiniduma | EHL Constructions | 0% | 36101846 | 32752577.91 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/08 | RR/RDA/07/26/10KM/08 | Development of 700 meters from Baddegama Vanduramba Road near Kola Kids Preschool and 300 meters from Temple Junction towards Dolahena | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 16745721.52 | 19813729.63 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/12 | RR/RDA/07/26/10KM/12 | 9 Pillar Junction to Mr. Asanka's Shop on Udubattawa Watta Road | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 17311725.2 | 19631662.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/22 | RR/RDA/07/26/10KM/22 | Kapalwila Olympus Waththa I.K. Road from Mr. Sunil's house to Rakshana Village Bodhi near Ketagoda Kada. | Galle | Hiniduma | Woshitha Engineering(Pvt)Ltd | 0% | 18381732.6 | 22218525.7 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18