## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/10/25/03/NP/JFN | RR/RDA/10/25/03 | Navalar Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 7919722.64 | 16240094.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-04-01 | 2026-06-08
RR/RDA/10/25/04/NP/JFN | RR/RDA/10/25/04 | Aluminium Factory Road | Jaffna | Jaffna | Majurathas Building Contractors | 100% | 36973948 | 56580112.16 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-04-04 | 2026-06-08
RR/RDA/10/25/05/NP/JFN | RR/RDA/10/25/05 | Renovation of Kokkuruniya Veethy | Jaffna | Jaffna | Majurathas Building Contractors | 100% | 22247557.75 | 34746312.4 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-06
RR/RDA/10/25/08/NP/JFN | RR/RDA/10/25/08 | Renovation of Ilanthaikulam Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 12089810.15 | 17821627.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/10/NP/JFN | RR/RDA/10/25/10 | Nayanmar Road | Jaffna | Jaffna | AVP Construction (Pvt) Ltd | 100% | 17917437.01 | 27107876.22 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/11/NP/JFN | RR/RDA/10/25/11 | Amman Road | Jaffna | Jaffna | Thaaru Construction | 100% | 14588981 | 19749993.06 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-05 | 2026-03-05
RR/RDA/10/25/13/NP/JFN | RR/RDA/10/25/13 | lnbacholai Road (Iththiyadi Muthali Kovilady - Inbacholai Road) | Jaffna | Jaffna | AVP Construction (Pvt) Ltd | 100% | 22527821.25 | 33467961.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-05-12 | 2026-05-12
RR/RDA/10/25/15/NP/JFN | RR/RDA/10/25/15 | Kadavaippulam Road | Jaffna | Jaffna | KBS Engineering Solution | 100% | 7712452 | 12352166.19 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13 | 2026-02-13
RR/RDA/10/25/16/NP/JFN | RR/RDA/10/25/16 | Kalai Makal Road | Jaffna | Jaffna | Jana Civil Work Contractors and Material Suppliers | 100% | 17670712.18 | 25146295.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-06
RR/RDA/10/25/17 |  | College Road | Jaffna | Jaffna |  | 100% | 35288918.91 | 35288918.91 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/10/25/12 |  | Anaikoddai - Kakaithivu Road | Jaffna | Jaffna |  | 100% | 34361480.4 | 34361480.4 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-11 | 2025-11-10