## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
| RR/RDA/04/25/16 | Palawa ihala meda Wijitha mawatha Waliyangadeniya margaya yakarana athuru Margaya | Kandy | Kadugannawa | Galahitiyawa Builders | 100% | 12240493.1 | 16221430 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/17/CP/KY | RR/RDA/04/25/17 | Nuganga Margaya | Kandy | Kadugannawa | Weebedda Construction | 100% | 9650635.5 | 15455845 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/34/CP/KY | RR/RDA/04/25/34 | Liyandeniya wewa margya | Kandy | Kadugannawa | Nimsara Construction & Holdings (PVT) Ltd | 100% | 9134433 | 11711039.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-28 | 2026-04-10
RR/RDA/04/25/35/CP/KY | RR/RDA/04/25/35 | Gamunupura Gonawatta pradana margaye Gamunupura pera pasala asala sita idiriyata pradana margaya | Kandy | Kadugannawa | Senerath Engineering (pvt) Ltd | 100% | 30043716.01 | 34175878.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-02-05
RR/RDA/04/25/30 |  | Uduwella Ganadevi strachue near the Sahira Estate to Alugolla Road | Kandy | Kadugannawa |  | 100% | 19320349.84 | 19320349.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/04/25/46 |  | Gelioya to Pahingamuwa Road | Kandy | Kadugannawa |  | 100% | 61266480.98 | 61266480.98 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-01 | 2025-11-30 | 2025-11-05
RR/RDA/04/25/38 |  | Moladanda handiye sita Mangalagama maima dakwa diwena margaya thara dama sanwardanya | Kandy | Kadugannawa |  | 100% | 13871976.5 | 13871976.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-18 | 2025-11-10 | 2025-11-15