## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/10KM/11/AKK/AKK | RR/RDA/16/25/10KM/11 | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Ampara | Kalmunai | Zaka Engineering Consultancy | 10% | 20596083.2 | 32835450.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-08 | 2026-06-06