## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/20/CP/KY | RR/RDA/04/25/20 | Carpeting road Ratemulla to Wendesiwaththa End | Kandy | Kandy | Wiscon (Pvt) Ltd | 45% | 36995817.1 | 40119276.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-08 | 2026-02-05 | 2026-03-20
RR/RDA/04/25/27/CP/KY | RR/RDA/04/25/27 | Dadahogama pitiye gedara pathibami sahitha Margaya | Kandy | Kandy | Nimsara Construction & Holdings (PVT) Ltd | 100% | 12532355 | 14990258.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/28/CP/KY | RR/RDA/04/25/28 | Dehideniya sita Hedeniya dakwa Margaya | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 35% | 38495776 | 41827394.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-23 | 2026-04-10
RR/RDA/04/25/52/CP/KY | RR/RDA/04/25/52 | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 60% | 50478905 | 72631674.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-21 | 2026-08-22
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
| RR/RDA/04/25/54 | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Kandy | Kandy | Ajith Construction | 20% | 65808186.5 | 73819405.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-08 | 2026-10-05
| RR/RDA/04/25/55 | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Kandy | Kandy | Southern Group Civil Construction (Pvt) Ltd. | 40% | 83080000 | 98049399.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-06 | 2026-08-07
RR/RDA/04/25/45 |  | Seewalee Kande sits Mahthanna Samadi Senasuna dakwa divena margaya | Kandy | Kandy |  | 100% | 40376466.56 | 40376466.56 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/04/25/12 |  | Wattaranthenna Sri Sumangala Mawatha | Kandy | Kandy |  | 100% | 8793978.6 | 8793978.6 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-11 | 2025-10-11