## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/05/25/22/CP/MTL | RR/RDA/05/25/22 | Sigirimulla sita Mailetthewa Aluthyaya dakwa margaya | Matale | Nalanda | Asiri Contractor and Designers | 100% | 33057264.9 | 48133410.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-03-10
RR/RDA/05/25/24/CP/MTL | RR/RDA/05/25/24 | Pahala Hombawa palama dakwa Daduwagolla kanaththa langa sita | Matale | Nalanda | Ajith Construction | 100% | 35817952.5 | 49816825.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-01-23
RR/RDA/05/25/05 |  | Near the Old Foodsity to Galwetiyawa Road | Matale | Nalanda |  | 100% | 35717528.78 | 35717528.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21