## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/06/25/37/CP/NE | RR/RDA/06/25/37 | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Nuwara Eliya | Norwood | Ajith Construction | 100% | 28282100 | 31658635.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-01-23 | 2025-12-31
RR/RDA/06/25/42/CP/NE | RR/RDA/06/25/42 | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Nuwara Eliya | Norwood | UKS Lanka Engineering Pvt Ltd. | 50% | 220116957.84 | 276005265.17 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-08-22 | 2026-08-22
RR/RDA/06/25/35 |  | Gaminipura Road | Nuwara Eliya | Norwood |  | 100% | 59292443.8 | 60272506.06 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-01
RR/RDA/06/25/43 |  | Development of Ponnagar Road | Nuwara Eliya | Norwood |  | 100% | 37481052.81 | 37481052.81 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-30 | 2026-01-31