## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/06/25/37/CP/NE | RR/RDA/06/25/37 | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Nuwara Eliya | Norwood | Ajith Construction | 100% | 28282100 | 31658635.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-01-23 | 2025-12-31
RR/RDA/06/25/35 |  | Gaminipura Road | Nuwara Eliya | Norwood |  | 100% | 59292443.8 | 60272506.06 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-01
RR/RDA/06/25/43 |  | Development of Ponnagar Road | Nuwara Eliya | Norwood |  | 100% | 37481052.81 | 37481052.81 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-30 | 2026-01-31