## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/06/25/36 |  | CWM Factory Road | Nuwara Eliya | Nuwara Eliya |  | 100% | 65323196.31 | 65323196.31 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-10
RR/RDA/06/25/39 |  | Madakumbura Dunukedeniya haraha Udagama dakwa Margaya | Nuwara Eliya | Nuwara Eliya |  | 100% | 40703316.18 | 40703316.18 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-12 | 2025-11-16 | 2026-03-31
RR/RDA/06/25/48 |  | Development of road in front of Divisional Secretariat East of Sangiripalayam Kothmale | Nuwara Eliya | Nuwara Eliya |  | 100% | 9106875.1 | 9106875.1 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2026-02-15
RR/RDA/06/25/52 |  | Development of Chandra Lal Karunarathne Mawatha | Nuwara Eliya | Nuwara Eliya |  | 100% | 9758284.5 | 9758284.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2025-11-05