## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/10/SBP/RTP | RR/RDA/25/24/10 | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Ratnapura | Pelmadulla | Sam Dam | 95% | 31673916.45 | 50516461.34 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-04-27
RR/RDA/24/25/25/SBP/RTP | RR/RDA/24/25/25 | From the point where the Bulathgama-Pallevela road starts from Rasagala Road | Ratnapura | Pelmadulla | Sathira Construction | 0% | 7273850 | 9080628.78 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/24/25/28/SBP/RTP | RR/RDA/24/25/28 | From near Kalal Ella Rubber Store to Narangalla via Navinikanda Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 18880633.26 | 24660700.4 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-11 | 2026-11-09
RR/RDA/24/25/31/SBP/RTP | RR/RDA/24/25/31 | Development of Koratuwegoda Road from Main Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 19882000.02 | 29632612.99 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-04 | 2026-12-03
RR/RDA/24/25/32/SBP/RTP | RR/RDA/24/25/32 | Weligepola to Nitta Kumbura Road | Ratnapura | Pelmadulla | Sasiri Construction | 0% | 14421268 | 18898027.21 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/25/24/15 |  | D03 Road Near the Yaka Poll | Ratnapura | Pelmadulla |  | 100% | 52683572.48 | 52683572.48 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/25/24/09 |  | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) | Ratnapura | Pelmadulla |  | 100% | 33251409.79 | 33251409.79 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-09-09 | 2025-11-15 | 2025-11-05