## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/21/25/04/NCP/POL | RR/RDA/21/25/04 | 10th Canal Lake Road | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 100% | 18877127 | 33113556.37 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-28 | 2026-01-20 | 2026-02-28
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/26 | Development of the road from Kaduruwela Muslim Kolaniya road to Pachcha Palliya | Polonnaruwa | Polonnaruwa | Central Engineering Services Pvt Ltd. (CESL) | 80% | 53880000 | 75598504.72 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-25 | 2026-08-24 | 2026-10-31
RR/RDA/21/25/17/NCP/POL | RR/RDA/21/25/27 | Development of 1 canal Road from Kadurwela Muslim Kolaniya Road to Parakum Mawatha | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 45% | 54640000 | 62351983.93 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-07-02 | 2026-10-01
| RR/GA/21/25/40 | Development of the road from near the Pimburatthewa Mahaweli Resort to the Aralaganwila Maha Oya main road | Polonnaruwa | Polonnaruwa | Sawsiri Construction | 7% | 59570000 | 64012244.55 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-09-30 | 2026-12-30
| RR/GA/21/25/41 | Development of the road from near the railway on the entrance road to the house of Mrs. 286 Latha in Boatta village | Polonnaruwa | Polonnaruwa | Nathan's Construction | 3% | 73470000 | 84585495.48 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-09-15 | 2026-12-15
| RR/GA/21/25/42 | Development of the road from the main road to near the Kadawala Wewa School | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 5% | 93990000 | 108995356.01 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-09-15 | 2026-12-15
| RR/GA/21/25/44 | Development of the road from near the house at Pulastigama 156 to Sungawila 1 Canal Junction | Polonnaruwa | Polonnaruwa | Nadun Construction (Pvt) Ltd | 5% | 67120000 | 78477567.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-09-15 | 2026-12-15
RR/RDA/21/25/02 |  | 273 Idama Sita Katuwavila Main Road | Polonnaruwa | Polonnaruwa |  | 100% | 61265788.54 | 61265788.54 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-13
RR/RDA/21/25/01 |  | Ganangolla pradhana para sihala moola asala sita sirisena mahathage niwasa dakwa margaya | Polonnaruwa | Polonnaruwa |  | 100% | 34916075.79 | 34916075.79 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2026-01-22 | 2026-01-31
RR/RDA/21/25/AC/15 |  | Aralaganwila Allewewa road Balance Section | Polonnaruwa | Polonnaruwa |  | 100% | 51779609.7 | 51779609.7 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 |  | 2026-01-31
RR/RDA/21/25/25 |  | School Main Road (Old Jumma Mosque Road) | Polonnaruwa | Polonnaruwa |  | 100% | 43759842.36 | 43759842.36 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31