## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/01/NWP/PUT | RR/RDA/19/25/01 | Development of carpeting the Gammedda road up to Anathapara. | Puttalam | Puttalam | Chandana Construction | 65% | 27734432.55 | 24961884.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2026-07-19
RR/RDA/19/25/05/NWP/PUT | RR/RDA/19/25/05 | Development of the road from near Mr. Chaminda's house to Boga Pathaha | Puttalam | Puttalam | Sampath Contractors | 65% | 36592843.95 | 60367316.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04 | 2026-07-04
RR/RDA/19/25/08/NWP/PUT | RR/RDA/19/25/08 | Carpeting of Velasia Main Road from Madurankuliya. | Puttalam | Puttalam | Sri Ram Constructions | 70% | 39584083.5 | 61899364.5 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-04-04 | 2026-05-04
RR/RDA/19/25/26/NWP/PUT | RR/RDA/19/25/26 | Abayarama Mawatha Bomimakka Kovil Road to Sembandaluwa Temple Road | Puttalam | Puttalam | Sampath Construction | 100% | 26275458.07 | 42010632 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-05 | 2026-02-03
RR/RDA/19/25/28/NWP/PUT | RR/RDA/19/25/28 | Samagi Mawatha | Puttalam | Puttalam | Ranuja Construction | 100% | 25908850 | 36001594.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
RR/RDA/19/25/29/NWP/PUT | RR/RDA/19/25/29 | Development of the road from Galkuliya Welameda to Mrs. Deepani's house | Puttalam | Puttalam | Sampath Construction | 100% | 8675871.6 | 13481102.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
RR/RDA/19/25/30/NWP/PUT | RR/RDA/19/25/30 | Development of carpeting from Mihirajthotupola to Serakkuliya 1 on the Serakkuliya main road | Puttalam | Puttalam | Omega Construction (Pvt) Ltd | 70% | 38494009.5 | 45465357.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/31/NWP/PUT | RR/RDA/19/25/31 | Development of carpeting from the point where carpeting has stopped on the Tammana main road | Puttalam | Puttalam | Sampath Construction | 50% | 26013841.83 | 39960885.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-13 | 2026-05-13
RR/RDA/19/25/32/NWP/PUT | RR/RDA/19/25/32 | Development of the Bammeyaya Road | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 50% | 10904293.4 | 17431257.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-05-12 | 2026-06-12
RR/RDA/19/25/33/NWP/PUT | RR/RDA/19/25/33 | Development of the road from near the Sugatarama Temple, Periyakulam to Thalgaswewa | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 45% | 24440875.25 | 38370082.14 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/34/NWP/PUT | RR/RDA/19/25/34 | Carpeting & Development of Bodhirajapura 4th Lane | Puttalam | Puttalam | Sampath Construction | 70% | 12568847.5 | 19966435.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-12 | 2026-05-13
| RR/RDA/19/25/40 | Development of the road from Madurankuliya to Velasiya College | Puttalam | Puttalam | Sampath Construction | 30% | 55254878 | 90437412.35 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-20 | 2026-05-21
RR/RDA/19/25/03 |  | Nawagattegama Rohala Pare sita Thapal Karyalaya Dakwa margaya (Nawagattegama) | Puttalam | Puttalam |  | 100% | 23512239.79 | 23512239.79 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/02 |  | Concrete development of the road from Hopper Kada junction to Elu Farm. | Puttalam | Puttalam |  | 100% | 33229489.54 | 33229489.54 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2026-01-31
RR/RDA/19/25/35 |  | Carpeting & Development of Kolithatissa Mawatha | Puttalam | Puttalam |  | 100% | 10359335.01 | 10359335.01 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31