## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/19/25/01/NWP/PUT | RR/RDA/19/25/01 | Development of carpeting the Gammedda road up to Anathapara. | Puttalam | Puttalam | Chandana Construction | 65% | 27734432.55 | 24961884.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2026-07-19
RR/RDA/19/25/05/NWP/PUT | RR/RDA/19/25/05 | Development of the road from near Mr. Chaminda's house to Boga Pathaha | Puttalam | Puttalam | Sampath Contractors | 65% | 36592843.95 | 60367316.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04 | 2026-07-04
RR/RDA/19/25/08/NWP/PUT | RR/RDA/19/25/08 | Carpeting of Velasia Main Road from Madurankuliya. | Puttalam | Puttalam | Sri Ram Constructions | 70% | 39584083.5 | 61899364.5 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-04-04 | 2026-05-04
RR/RDA/19/25/30/NWP/PUT | RR/RDA/19/25/30 | Development of carpeting from Mihirajthotupola to Serakkuliya 1 on the Serakkuliya main road | Puttalam | Puttalam | Omega Construction (Pvt) Ltd | 70% | 38494009.5 | 45465357.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/31/NWP/PUT | RR/RDA/19/25/31 | Development of carpeting from the point where carpeting has stopped on the Tammana main road | Puttalam | Puttalam | Sampath Construction | 50% | 26013841.83 | 39960885.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-13 | 2026-05-13
RR/RDA/19/25/32/NWP/PUT | RR/RDA/19/25/32 | Development of the Bammeyaya Road | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 50% | 10904293.4 | 17431257.91 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-05-12 | 2026-06-12
RR/RDA/19/25/33/NWP/PUT | RR/RDA/19/25/33 | Development of the road from near the Sugatarama Temple, Periyakulam to Thalgaswewa | Puttalam | Puttalam | Jayawardana Constructions (Pvt) Ltd. | 45% | 24440875.25 | 38370082.14 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-12 | 2026-04-12 | 2026-06-12
RR/RDA/19/25/34/NWP/PUT | RR/RDA/19/25/34 | Carpeting & Development of Bodhirajapura 4th Lane | Puttalam | Puttalam | Sampath Construction | 70% | 12568847.5 | 19966435.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-12 | 2026-05-12 | 2026-05-13