## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/25/34/SBP/KGL | RR/RDA/25/25/34 | Road Connecting Ihala Palampitiya and Pahala Palampitiya | Kegalle | Ruwanwella | DKS Nishantha Construction | 0% | 26331747.62 | 36648120.48 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-24 | 2026-10-22
RR/RDA/25/25/35/SBP/KGL | RR/RDA/25/25/35 | Kudadeniya Adurapola Watta Road | Kegalle | Ruwanwella | TMT Construction | 60% | 29362927.93 | 41661137.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-02