## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/25/20/SBP/KGL | RR/RDA/25/25/20 | Neluwakkana gama meda Road | Kegalle | Ruwanwella | Loshitha Construction | 95% | 23823804.13 | 33221060.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-20 | 2026-02-18
RR/RDA/25/25/28/SBP/KGL | RR/RDA/25/25/28 | Naagas thenna Road | Kegalle | Ruwanwella | Jayasinghe Contractors (Pvt) Ltd. | 90% | 102000742.36 | 103886540.99 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-11 | 2026-08-12
RR/RDA/25/25/31/SBP/KGL | RR/RDA/25/25/31 | Developing the section connecting the road from the old office in Yatawala to the road in Beraliyahinna | Kegalle | Ruwanwella | DHP Construction | 100% | 13369909.3 | 14520809.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/32/SBP/KGL | RR/RDA/25/25/32 | Concreting the unconcreted areas of the Hingurana road | Kegalle | Ruwanwella | DHP Construction | 100% | 15740043.19 | 17242742.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-04
RR/RDA/25/25/33/SBP/KGL | RR/RDA/25/25/33 | Rehabilitation of Kahatapanawa Kajugahamula road | Kegalle | Ruwanwella | Jayabima Engineering | 100% | 12423785 | 16993706.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-20 | 2026-02-18
RR/RDA/25/25/40/SBP/KGL | RR/RDA/25/25/40 | Kabagamuwa 17 Acres Road Development | Kegalle | Ruwanwella | TMT Construction | 95% | 14823379.41 | 18604688.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-28 | 2026-05-28
RR/RDA/25/25/16 |  | Ma dola Jansalu Mawatha Rathnapuara Colombo Road to Welangalla Maha ela Bridge | Kegalle | Ruwanwella |  | 100% | 40604043.84 | 37225336.73 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25
RR/RDA/25/25/21 |  | Kalupahanawaththa Road | Kegalle | Ruwanwella |  | 100% | 28324647.09 | 28324647.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-11-30 | 2025-11-15
RR/RDA/25/25/30 |  | Developing the dilapidated section of the lower part of the Pallebage road to the Watte junction | Kegalle | Ruwanwella |  | 100% | 6992158.2 | 6992158.2 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-18 | 2025-10-10