## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/09/25/08/SP/HMB | RR/RDA/09/25/08 | Carpeting Pissubedda Medagamgoda road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 98% | 28923336.75 | 46881232.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-20 | 2026-06-19
RR/RDA/08/25/05 |  | Koggalla bus stand to Sooriyawewa Road | Hambantota | Tangalle |  | 95% | 127573213.52 | 127573213.52 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-02-28