## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/13/CP/KY | RR/RDA/04/25/13 | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Kandy | Kundasale | Dharshana Construction | 37% | 35195820 | 42644514.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-08-21 | 2026-08-21
RR/RDA/04/25/15/CP/KY | RR/RDA/04/25/15 | Madolkale sita Huluganga dakwa yana athuru margaye Bandaranayakapura gam kotasata adala Margaya | Kandy | Kundasale | UGD Constructions | 100% | 12711509.59 | 20856501.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
| RR/RDA/04/25/16 | Palawa ihala meda Wijitha mawatha Waliyangadeniya margaya yakarana athuru Margaya | Kandy | Kadugannawa | Galahitiyawa Builders | 100% | 12240493.1 | 16221430 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/17/CP/KY | RR/RDA/04/25/17 | Nuganga Margaya | Kandy | Kadugannawa | Weebedda Construction | 100% | 9650635.5 | 15455845 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/19/CP/KY | RR/RDA/04/25/19 | Mulgama viduhala Asala sita lewalan dakwa | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 35% | 25917512.5 | 46131296.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/20/CP/KY | RR/RDA/04/25/20 | Carpeting road Ratemulla to Wendesiwaththa End | Kandy | Kandy | Wiscon (Pvt) Ltd | 45% | 36995817.1 | 40119276.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-08 | 2026-02-05 | 2026-03-20
RR/RDA/04/25/21/CP/KY | RR/RDA/04/25/21 | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | Kandy | Gampola | UGD Constructions | 80% | 22711029 | 40719533.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-03-10
RR/RDA/04/25/22/CP/KY | RR/RDA/04/25/22 | Rambukwella viharasthanaya asala sita Dodamgolla Rambukwella nagenhira haraha Udispaththuwa dakwa diwena Margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 15056107 | 26802449.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/23/CP/KY | RR/RDA/04/25/23 | Minuwangamuwa gammada margaye Aberathne mahathage niwasa asala sita Abesinha Banda mahathage Niwasa dakwa | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 27734432.55 | 49079937.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/24/CP/KY | RR/RDA/04/25/24 | Galamuduna gamata pivisena Margaya | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 157638978.9 | 201921834.86 | Awarded | Tender Above 50Mn |  |  |  | 2026-02-01
RR/RDA/04/25/25/CP/KY | RR/RDA/04/25/25 | Delgasthenna Road | Kandy | Kundasale | NAGMA ENGINEERING (PVT) LTD | 0% | 56035922.24 | 78736509.47 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06 | 2026-05-31
RR/RDA/04/25/27/CP/KY | RR/RDA/04/25/27 | Dadahogama pitiye gedara pathibami sahitha Margaya | Kandy | Kandy | Nimsara Construction & Holdings (PVT) Ltd | 100% | 12532355 | 14990258.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/28/CP/KY | RR/RDA/04/25/28 | Dehideniya sita Hedeniya dakwa Margaya | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 35% | 38495776 | 41827394.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-23 | 2026-04-10
RR/RDA/04/25/31/CP/KY | RR/RDA/04/25/31 | Shantha Janapada Village middle road | Kandy | Gampola | Ajith Construction | 100% | 42357645 | 47278636.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-05 | 2026-03-20
RR/RDA/04/25/31(1)/CP/KY | RR/RDA/04/25/31(1) | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Kandy | Gampola | Central Engineering Services Pvt Ltd. (CESL) | 30% | 50476865.28 | 65989182.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-03 | 2026-07-07 | 2026-10-31
RR/RDA/04/25/32/CP/KY | RR/RDA/04/25/32 | Pilawala Navodya pasala asala sita Nelumpathhinna pansala dakwa margaya | Kandy | Kundasale | Senerath Engineering (pvt) Ltd | 100% | 18059531.27 | 19939938.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/04/25/33/CP/KY | RR/RDA/04/25/33 | New forest kotase Jana Udana gammana margaya | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 6992144.5 | 12512939.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/34/CP/KY | RR/RDA/04/25/34 | Liyandeniya wewa margya | Kandy | Kadugannawa | Nimsara Construction & Holdings (PVT) Ltd | 100% | 9134433 | 11711039.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-28 | 2026-04-10
RR/RDA/04/25/35/CP/KY | RR/RDA/04/25/35 | Gamunupura Gonawatta pradana margaye Gamunupura pera pasala asala sita idiriyata pradana margaya | Kandy | Kadugannawa | Senerath Engineering (pvt) Ltd | 100% | 30043716.01 | 34175878.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-02-05
RR/RDA/04/25/41/CP/KY | RR/RDA/04/25/41 | Karyala handiya pahala margya concrete kirima | Kandy | Gampola | UGD Constructions | 85% | 22047564 | 39022781.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2026-01-14 | 2026-01-31
RR/RDA/04/25/43/CP/KY | RR/RDA/04/25/43 | Dodamgolla kowila asla sita hindu susana boomiya dakwa margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 14680539.5 | 26797465.46 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
| RR/RDA/04/25/50 | Ambakote Road | Kandy | Kundasale | Dharshana Construction | 5% | 32019889 | 31070808.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-09-10
RR/RDA/04/25/52/CP/KY | RR/RDA/04/25/52 | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Kandy | Kandy | Senerath Engineering (pvt) Ltd | 60% | 50478905 | 72631674.77 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-21 | 2026-08-22
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
| RR/RDA/04/25/54 | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Kandy | Kandy | Ajith Construction | 20% | 65808186.5 | 73819405.52 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-06-08 | 2026-10-05
| RR/RDA/04/25/55 | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Kandy | Kandy | Southern Group Civil Construction (Pvt) Ltd. | 40% | 83080000 | 98049399.56 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-06 | 2026-08-07
| RR/RDA/04/25/56 | Renovation of road Haidri estate to Barcapal | Kandy | Gampola | Ajith Construction | 25% | 51476130 | 56051060.7 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-11-20
RR/RDA/05/25/01/CP/MTL | RR/RDA/05/25/01 | Moragahamada pasala asalin arambhawa Rajagammana gama madin Madawala adawala para dakwa pradana athuru Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 41535473.64 | 60115019.16 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-22 | 2026-05-26 | 2026-05-20
RR/RDA/05/25/02/CP/MTL | RR/RDA/05/25/02 | Lakshahena maragaya Mathalapitiya margaye sita Lakshahena Kosgolla dakwa Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 36743107.5 | 50437576.84 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-18 | 2025-12-31 | 2026-01-07
RR/RDA/05/25/04/CP/MTL | RR/RDA/05/25/04 | Aiththaliyadda sita Porcilain eka dakwa Margaya | Matale | Matale | Ajith Construction | 100% | 27015791 | 33583183.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/07/CP/MTL | RR/RDA/05/25/07 | Uladawa Mansandiye sita Homapola Janapadaye Saukkaya Maddayasthanaya dakawa Diwena Udurmpelessa thek Diwena Margaya Kapat Kirima | Matale | Nalanda | Ajith Construction | 0% | 92740000 | 84423480.85 | Awarded | Tender Above 50Mn |  |  |  | 2026-10-13
RR/RDA/05/25/09/CP/MTL | RR/RDA/05/25/09 | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Matale | Matale | Pragathi Civil Contractor | 80% | 38748820 | 41365188.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/10/CP/MTL | RR/RDA/05/25/10 | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | Matale | Nalanda | NAGMA ENGINEERING (PVT) LTD | 70% | 56167707.75 | 79104652.3 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-24 | 2026-04-27 | 2026-05-31
RR/RDA/05/25/11/CP/MTL | RR/RDA/05/25/11 | Hunukete sita Elagala dakwa Pradana Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 50% | 82470143.89 | 108683600.82 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-06 | 2026-03-26 | 2026-05-20
RR/RDA/05/25/12/CP/MTL | RR/RDA/05/25/12 | A9 pare Kist biscuit factoryata meha sithuwam kanda board eka (savikara athi) Nalanda wattata yana para | Matale | Matale | Senevirathna Enterprise | 100% | 10340000 | 14006802.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-07 | 2026-01-05 | 2026-01-02
RR/RDA/05/25/13/CP/MTL | RR/RDA/05/25/13 | A9 pare Elik Aluvihare niwasa lagin arambha wee Hunugalwala dakwa margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 19486197.5 | 27383521.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-01-31
RR/RDA/05/25/16/CP/MTL | RR/RDA/05/25/16 | Dangan pedesa Mithragama margya Kurunegala margaye sita Mithragama | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 23856545.35 | 33031745.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2025-12-31
RR/RDA/05/25/17/CP/MTL | RR/RDA/05/25/17 | Ambagastenna to gurubebila temple via Polwaththa nikawella | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 56391365.63 | 73216443.75 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-03-25 | 2026-03-20
RR/RDA/05/25/18/CP/MTL | RR/RDA/05/25/18 | Bandarapola Ulpathapitiya haraha Kiula margaya | Matale | Matale | Ajith Construction | 100% | 26720870 | 34151478.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/19/CP/MTL | RR/RDA/05/25/19 | Katudeniya bahukarya godanagilla asala Hettiyawatta dakwa margaya | Matale | Matale | Ajith Construction | 100% | 13129506.5 | 17556901.6 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-02-15
RR/RDA/05/25/20/CP/MTL | RR/RDA/05/25/20 | Harispattuwa margaya arambaka mansandiye sita Thusitha maranadara godanagilla dakwa | Matale | Matale | Ajith Construction | 100% | 15584937.5 | 21943997.74 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2026-01-31
RR/RDA/05/25/22/CP/MTL | RR/RDA/05/25/22 | Sigirimulla sita Mailetthewa Aluthyaya dakwa margaya | Matale | Nalanda | Asiri Contractor and Designers | 100% | 33057264.9 | 48133410.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-03-10
RR/RDA/05/25/24/CP/MTL | RR/RDA/05/25/24 | Pahala Hombawa palama dakwa Daduwagolla kanaththa langa sita | Matale | Nalanda | Ajith Construction | 100% | 35817952.5 | 49816825.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-01-23
RR/RDA/05/25/26/CP/MTL | RR/RDA/05/25/26 | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Matale | Nalanda | Jayaru Engineering (Pvt) Ltd | 60% | 18760083.54 | 30575367.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2025-12-31 | 2026-03-25
RR/RDA/05/25/27/CP/MTL | RR/RDA/05/25/27 | Welemulla sita Kandewaththa | Matale | Matale | Ajith Construction | 100% | 23207525 | 32539052.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-20
RR/RDA/05/25/29/CP/MTL | RR/RDA/05/25/29 | Pitawala handiye sita pitawala desata | Matale | Matale | Lahiru Construction & Consultants (PVT) Ltd | 100% | 37136372.9 | 38781690.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/05/25/30/CP/MTL | RR/RDA/05/25/30 | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Matale | Nalanda | Lahiru Construction & Consultants (PVT) Ltd | 60% | 59540000 | 77270301.29 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-10 | 2026-08-10 | 2026-08-10
RR/RDA/06/25/32/CP/NE | RR/RDA/06/25/32 | Nanuoya Glaso pahala kotasa Margaya | Nuwara Eliya | Nuwara Eliya | wiscon (pvt) ltd | 5% | 38841280.5 | 43085721.61 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-05-20
RR/RDA/06/25/34/CP/NE | RR/RDA/06/25/34 | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 54639783.83 | 84599211.7 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/37/CP/NE | RR/RDA/06/25/37 | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Nuwara Eliya | Norwood | Ajith Construction | 100% | 28282100 | 31658635.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-01-23 | 2025-12-31
RR/RDA/06/25/38/CP/NE | RR/RDA/06/25/38 | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | Nuwara Eliya | Hanguranketha | NAGMA ENGINEERING (PVT) LTD | 0% | 38465634.79 | 54713411.13 | Awarded | Tender Above 50Mn |  |  |  | 2026-01-01 | 2026-05-06
RR/RDA/06/25/40/CP/NE | RR/RDA/06/25/40 | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | Nuwara Eliya | Hanguranketha | UGD Constructions | 10% | 31672222.12 | 35044851.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/06/25/41/CP/NE | RR/RDA/06/25/41 | Nayapana Gammada tharapara sanwardhanaya | Nuwara Eliya | Nuwara Eliya | Central Engineering Services Pvt Ltd. (CESL) | 35% | 51754603.52 | 64794731.2 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-28 | 2026-07-29
RR/RDA/06/25/42/CP/NE | RR/RDA/06/25/42 | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Nuwara Eliya | Norwood | UKS Lanka Engineering Pvt Ltd. | 50% | 220116957.84 | 276005265.17 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-11-24 | 2026-08-22 | 2026-08-22
| RR/RDA/06/25/45 | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Nuwara Eliya | Hanguranketha | Ajith Construction | 10% | 61551869.38 | 68311664.39 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
| RR/RDA/06/25/46 | Carpeting of Mahathenna to Hapugasdeniya Main Road | Nuwara Eliya | Hanguranketha | Ajith Construction | 73% | 68070000 | 79957655.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
RR/RDA/04/25/42 |  | Mahanuwara Digana pradana margaye gamudawa jala tankiya asala sita Malgahamula handiya dakwa Margaya | Kandy | Kundasale |  | 100% | 21611921.71 | 21611921.71 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/45 |  | Seewalee Kande sits Mahthanna Samadi Senasuna dakwa divena margaya | Kandy | Kandy |  | 100% | 40376466.56 | 40376466.56 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/04/25/18 |  | Dewaraja Mw (Balance Work) | Kandy | Gampola |  | 100% | 29009072.8 | 29009072.8 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/30 |  | Uduwella Ganadevi strachue near the Sahira Estate to Alugolla Road | Kandy | Kadugannawa |  | 100% | 19320349.84 | 19320349.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/05/25/03 |  | Serugolla Middle Road Kanwawala Junction to NawarathnaGoda Main Road | Matale | Matale |  | 100% | 29509544.69 | 30080524.87 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-19 | 2025-09-30
RR/RDA/05/25/05 |  | Near the Old Foodsity to Galwetiyawa Road | Matale | Nalanda |  | 100% | 35717528.78 | 35717528.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/06/25/33 |  | Mool oya Main Road Section 1 | Nuwara Eliya | Hanguranketha |  | 100% | 59668203.37 | 59668203.37 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-30
RR/RDA/06/25/35 |  | Gaminipura Road | Nuwara Eliya | Norwood |  | 100% | 59292443.8 | 60272506.06 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-01
RR/RDA/06/25/36 |  | CWM Factory Road | Nuwara Eliya | Nuwara Eliya |  | 100% | 65323196.31 | 65323196.31 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-10
RR/RDA/04/25/12 |  | Wattaranthenna Sri Sumangala Mawatha | Kandy | Kandy |  | 100% | 8793978.6 | 8793978.6 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-11 | 2025-10-11
RR/RDA/04/25/37 |  | Elkaduwa pare sita Japan para sanwardanaya kirima | Kandy | Kundasale |  | 100% | 48931555.87 | 48931555.87 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-30 | 2025-10-30 | 2026-02-15
RR/RDA/04/25/40 |  | Lanka bankuwa asala sita Unambuwa dakwa diwena margaya thara damima | Kandy | Gampola |  | 100% | 21307459.69 | 21307459.69 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-10-01
RR/RDA/04/25/46 |  | Gelioya to Pahingamuwa Road | Kandy | Kadugannawa |  | 100% | 61266480.98 | 61266480.98 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-01 | 2025-11-30 | 2025-11-05
RR/RDA/05/25/15 |  | Salagama margaya Nikagolla margaye sita Boraluwa dakwa | Matale | Matale |  | 100% | 31665473.42 | 31665473.42 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30
RR/RDA/06/25/39 |  | Madakumbura Dunukedeniya haraha Udagama dakwa Margaya | Nuwara Eliya | Nuwara Eliya |  | 100% | 40703316.18 | 40703316.18 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-12 | 2025-11-16 | 2026-03-31
RR/RDA/04/25/38 |  | Moladanda handiye sita Mangalagama maima dakwa diwena margaya thara dama sanwardanya | Kandy | Kadugannawa |  | 100% | 13871976.5 | 13871976.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-18 | 2025-11-10 | 2025-11-15
RR/RDA/04/25/47 |  | Manikhinna Hurikaduwa Iththamaliyagoda New Temple Access Road | Kandy | Kundasale |  | 100% | 10442337.36 | 10442337.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2026-01-25
RR/RDA/06/25/43 |  | Development of Ponnagar Road | Nuwara Eliya | Norwood |  | 100% | 37481052.81 | 37481052.81 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-30 | 2026-01-31
RR/RDA/06/25/44 |  | Carpeting of Muloya Main Road Section 2 | Nuwara Eliya | Hanguranketha |  | 60% | 42312390.95 | 42312390.95 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-22 | 2025-12-31 | 2026-03-15
RR/RDA/06/25/47 |  | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala | Nuwara Eliya | Hanguranketha |  | 38% | 28020844.83 | 28020844.83 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-31 | 2026-03-15
RR/RDA/06/25/48 |  | Development of road in front of Divisional Secretariat East of Sangiripalayam Kothmale | Nuwara Eliya | Nuwara Eliya |  | 100% | 9106875.1 | 9106875.1 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2026-02-15
RR/RDA/06/25/52 |  | Development of Chandra Lal Karunarathne Mawatha | Nuwara Eliya | Nuwara Eliya |  | 100% | 9758284.5 | 9758284.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2025-11-05
RR/RDA/05/25/23 |  | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya | Matale | Nalanda |  | 60% | 28401905.12 | 28401905.12 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-12-13 | 2026-06-13
RR/RDA/05/25/28 |  | Adawala Udagama Road | Matale | Nalanda |  | 75% | 56161142.68 | 56161142.68 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-09-22 | 2026-02-22 | 2026-04-20