## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/04/25/15/CP/KY | RR/RDA/04/25/15 | Madolkale sita Huluganga dakwa yana athuru margaye Bandaranayakapura gam kotasata adala Margaya | Kandy | Kundasale | UGD Constructions | 100% | 12711509.59 | 20856501.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
| RR/RDA/04/25/16 | Palawa ihala meda Wijitha mawatha Waliyangadeniya margaya yakarana athuru Margaya | Kandy | Kadugannawa | Galahitiyawa Builders | 100% | 12240493.1 | 16221430 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/17/CP/KY | RR/RDA/04/25/17 | Nuganga Margaya | Kandy | Kadugannawa | Weebedda Construction | 100% | 9650635.5 | 15455845 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/22/CP/KY | RR/RDA/04/25/22 | Rambukwella viharasthanaya asala sita Dodamgolla Rambukwella nagenhira haraha Udispaththuwa dakwa diwena Margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 15056107 | 26802449.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/23/CP/KY | RR/RDA/04/25/23 | Minuwangamuwa gammada margaye Aberathne mahathage niwasa asala sita Abesinha Banda mahathage Niwasa dakwa | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 27734432.55 | 49079937.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2026-01-14 | 2026-03-31
RR/RDA/04/25/27/CP/KY | RR/RDA/04/25/27 | Dadahogama pitiye gedara pathibami sahitha Margaya | Kandy | Kandy | Nimsara Construction & Holdings (PVT) Ltd | 100% | 12532355 | 14990258.08 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-25 | 2026-01-09 | 2026-03-31
RR/RDA/04/25/31/CP/KY | RR/RDA/04/25/31 | Shantha Janapada Village middle road | Kandy | Gampola | Ajith Construction | 100% | 42357645 | 47278636.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-05 | 2026-03-20
RR/RDA/04/25/32/CP/KY | RR/RDA/04/25/32 | Pilawala Navodya pasala asala sita Nelumpathhinna pansala dakwa margaya | Kandy | Kundasale | Senerath Engineering (pvt) Ltd | 100% | 18059531.27 | 19939938.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-31
RR/RDA/04/25/33/CP/KY | RR/RDA/04/25/33 | New forest kotase Jana Udana gammana margaya | Kandy | Gampola | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 6992144.5 | 12512939.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
RR/RDA/04/25/34/CP/KY | RR/RDA/04/25/34 | Liyandeniya wewa margya | Kandy | Kadugannawa | Nimsara Construction & Holdings (PVT) Ltd | 100% | 9134433 | 11711039.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-28 | 2026-04-10
RR/RDA/04/25/35/CP/KY | RR/RDA/04/25/35 | Gamunupura Gonawatta pradana margaye Gamunupura pera pasala asala sita idiriyata pradana margaya | Kandy | Kadugannawa | Senerath Engineering (pvt) Ltd | 100% | 30043716.01 | 34175878.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-02-05
RR/RDA/04/25/43/CP/KY | RR/RDA/04/25/43 | Dodamgolla kowila asla sita hindu susana boomiya dakwa margaya | Kandy | Kundasale | The Wise Lanka Construction Company (Pvt) Ltd | 100% | 14680539.5 | 26797465.46 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-17 | 2025-12-31 | 2026-02-28
| RR/RDA/04/25/50 | Ambakote Road | Kandy | Kundasale | Dharshana Construction | 5% | 32019889 | 31070808.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-09-10
RR/RDA/04/25/53/CP/KY | RR/RDA/04/25/53 | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Kandy | Kandy | Tiasa Construction (Pvt) Ltd | 40% | 29850460.2 | 39182935.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-08 | 2026-09-08
RR/RDA/05/25/01/CP/MTL | RR/RDA/05/25/01 | Moragahamada pasala asalin arambhawa Rajagammana gama madin Madawala adawala para dakwa pradana athuru Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 41535473.64 | 60115019.16 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-22 | 2026-05-26 | 2026-05-20
RR/RDA/05/25/02/CP/MTL | RR/RDA/05/25/02 | Lakshahena maragaya Mathalapitiya margaye sita Lakshahena Kosgolla dakwa Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 36743107.5 | 50437576.84 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-18 | 2025-12-31 | 2026-01-07
RR/RDA/05/25/04/CP/MTL | RR/RDA/05/25/04 | Aiththaliyadda sita Porcilain eka dakwa Margaya | Matale | Matale | Ajith Construction | 100% | 27015791 | 33583183.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/11/CP/MTL | RR/RDA/05/25/11 | Hunukete sita Elagala dakwa Pradana Margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 50% | 82470143.89 | 108683600.82 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-06 | 2026-03-26 | 2026-05-20
RR/RDA/05/25/12/CP/MTL | RR/RDA/05/25/12 | A9 pare Kist biscuit factoryata meha sithuwam kanda board eka (savikara athi) Nalanda wattata yana para | Matale | Matale | Senevirathna Enterprise | 100% | 10340000 | 14006802.35 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-07 | 2026-01-05 | 2026-01-02
RR/RDA/05/25/13/CP/MTL | RR/RDA/05/25/13 | A9 pare Elik Aluvihare niwasa lagin arambha wee Hunugalwala dakwa margaya | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 19486197.5 | 27383521.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2026-01-31
RR/RDA/05/25/16/CP/MTL | RR/RDA/05/25/16 | Dangan pedesa Mithragama margya Kurunegala margaye sita Mithragama | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 23856545.35 | 33031745.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-08 | 2025-12-31
RR/RDA/05/25/17/CP/MTL | RR/RDA/05/25/17 | Ambagastenna to gurubebila temple via Polwaththa nikawella | Matale | Matale | Senerath Engineering (pvt) Ltd | 100% | 56391365.63 | 73216443.75 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-03-25 | 2026-03-20
RR/RDA/05/25/18/CP/MTL | RR/RDA/05/25/18 | Bandarapola Ulpathapitiya haraha Kiula margaya | Matale | Matale | Ajith Construction | 100% | 26720870 | 34151478.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2025-12-31
RR/RDA/05/25/19/CP/MTL | RR/RDA/05/25/19 | Katudeniya bahukarya godanagilla asala Hettiyawatta dakwa margaya | Matale | Matale | Ajith Construction | 100% | 13129506.5 | 17556901.6 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-02-15
RR/RDA/05/25/20/CP/MTL | RR/RDA/05/25/20 | Harispattuwa margaya arambaka mansandiye sita Thusitha maranadara godanagilla dakwa | Matale | Matale | Ajith Construction | 100% | 15584937.5 | 21943997.74 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-07 | 2026-01-31
RR/RDA/05/25/22/CP/MTL | RR/RDA/05/25/22 | Sigirimulla sita Mailetthewa Aluthyaya dakwa margaya | Matale | Nalanda | Asiri Contractor and Designers | 100% | 33057264.9 | 48133410.98 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-03-10
RR/RDA/05/25/24/CP/MTL | RR/RDA/05/25/24 | Pahala Hombawa palama dakwa Daduwagolla kanaththa langa sita | Matale | Nalanda | Ajith Construction | 100% | 35817952.5 | 49816825.04 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-01-23
RR/RDA/05/25/26/CP/MTL | RR/RDA/05/25/26 | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Matale | Nalanda | Jayaru Engineering (Pvt) Ltd | 60% | 18760083.54 | 30575367.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-01 | 2025-12-31 | 2026-03-25
RR/RDA/05/25/27/CP/MTL | RR/RDA/05/25/27 | Welemulla sita Kandewaththa | Matale | Matale | Ajith Construction | 100% | 23207525 | 32539052.69 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-20
RR/RDA/05/25/29/CP/MTL | RR/RDA/05/25/29 | Pitawala handiye sita pitawala desata | Matale | Matale | Lahiru Construction & Consultants (PVT) Ltd | 100% | 37136372.9 | 38781690.92 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-23 | 2026-02-15
RR/RDA/06/25/37/CP/NE | RR/RDA/06/25/37 | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Nuwara Eliya | Norwood | Ajith Construction | 100% | 28282100 | 31658635.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-01-23 | 2025-12-31
| RR/RDA/06/25/45 | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Nuwara Eliya | Hanguranketha | Ajith Construction | 10% | 61551869.38 | 68311664.39 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
| RR/RDA/06/25/46 | Carpeting of Mahathenna to Hapugasdeniya Main Road | Nuwara Eliya | Hanguranketha | Ajith Construction | 73% | 68070000 | 79957655.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-05 | 2026-06-05
RR/RDA/04/25/42 |  | Mahanuwara Digana pradana margaye gamudawa jala tankiya asala sita Malgahamula handiya dakwa Margaya | Kandy | Kundasale |  | 100% | 21611921.71 | 21611921.71 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/45 |  | Seewalee Kande sits Mahthanna Samadi Senasuna dakwa divena margaya | Kandy | Kandy |  | 100% | 40376466.56 | 40376466.56 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/04/25/18 |  | Dewaraja Mw (Balance Work) | Kandy | Gampola |  | 100% | 29009072.8 | 29009072.8 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-21
RR/RDA/04/25/30 |  | Uduwella Ganadevi strachue near the Sahira Estate to Alugolla Road | Kandy | Kadugannawa |  | 100% | 19320349.84 | 19320349.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/05/25/03 |  | Serugolla Middle Road Kanwawala Junction to NawarathnaGoda Main Road | Matale | Matale |  | 100% | 29509544.69 | 30080524.87 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-19 | 2025-09-30
RR/RDA/05/25/05 |  | Near the Old Foodsity to Galwetiyawa Road | Matale | Nalanda |  | 100% | 35717528.78 | 35717528.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21
RR/RDA/06/25/33 |  | Mool oya Main Road Section 1 | Nuwara Eliya | Hanguranketha |  | 100% | 59668203.37 | 59668203.37 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-30
RR/RDA/06/25/35 |  | Gaminipura Road | Nuwara Eliya | Norwood |  | 100% | 59292443.8 | 60272506.06 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-01
RR/RDA/06/25/36 |  | CWM Factory Road | Nuwara Eliya | Nuwara Eliya |  | 100% | 65323196.31 | 65323196.31 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-10
RR/RDA/04/25/12 |  | Wattaranthenna Sri Sumangala Mawatha | Kandy | Kandy |  | 100% | 8793978.6 | 8793978.6 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-11 | 2025-10-11
RR/RDA/04/25/37 |  | Elkaduwa pare sita Japan para sanwardanaya kirima | Kandy | Kundasale |  | 100% | 48931555.87 | 48931555.87 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-30 | 2025-10-30 | 2026-02-15
RR/RDA/04/25/40 |  | Lanka bankuwa asala sita Unambuwa dakwa diwena margaya thara damima | Kandy | Gampola |  | 100% | 21307459.69 | 21307459.69 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-10-01
RR/RDA/04/25/46 |  | Gelioya to Pahingamuwa Road | Kandy | Kadugannawa |  | 100% | 61266480.98 | 61266480.98 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-01 | 2025-11-30 | 2025-11-05
RR/RDA/05/25/15 |  | Salagama margaya Nikagolla margaye sita Boraluwa dakwa | Matale | Matale |  | 100% | 31665473.42 | 31665473.42 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30
RR/RDA/06/25/39 |  | Madakumbura Dunukedeniya haraha Udagama dakwa Margaya | Nuwara Eliya | Nuwara Eliya |  | 100% | 40703316.18 | 40703316.18 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-12 | 2025-11-16 | 2026-03-31
RR/RDA/04/25/38 |  | Moladanda handiye sita Mangalagama maima dakwa diwena margaya thara dama sanwardanya | Kandy | Kadugannawa |  | 100% | 13871976.5 | 13871976.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-18 | 2025-11-10 | 2025-11-15
RR/RDA/04/25/47 |  | Manikhinna Hurikaduwa Iththamaliyagoda New Temple Access Road | Kandy | Kundasale |  | 100% | 10442337.36 | 10442337.36 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2026-01-25
RR/RDA/06/25/43 |  | Development of Ponnagar Road | Nuwara Eliya | Norwood |  | 100% | 37481052.81 | 37481052.81 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-30 | 2026-01-31
RR/RDA/06/25/48 |  | Development of road in front of Divisional Secretariat East of Sangiripalayam Kothmale | Nuwara Eliya | Nuwara Eliya |  | 100% | 9106875.1 | 9106875.1 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2026-02-15
RR/RDA/06/25/52 |  | Development of Chandra Lal Karunarathne Mawatha | Nuwara Eliya | Nuwara Eliya |  | 100% | 9758284.5 | 9758284.5 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-17 | 2025-11-15 | 2025-11-05