## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/16/25/04/AKK/AMP | RR/RDA/16/25/04 | Pokunugama near Mr. Dinesh Tharaga House to Road (From Pokunugama Pre School to up to Mr. Dinesh Tharaga House) | Ampara | Ampara | Harischandra Idikirim | 100% | 6435000 | 10039653.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-10 | 2025-12-19
RR/RDA/16/25/01/AKK/AMP | RR/RDA/16/25/01 | Samanalathenna- Road from House No.63 To the Monastery Muwagammana -From First Lane to Cemetry | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 21336681.87 | 36719169.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2025-12-24 | 2025-12-24
RR/RDA/16/25/03/AKK/AMP | RR/RDA/16/25/03 | Polbedda Junction to Galwalayaya Road | Ampara | Dehiaattakandiya | MOTEC Engineering & Construction | 52% | 17506335 | 24800970.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-10 | 2026-03-10 | 2026-03-16
RR/RDA/SP/16/25/01/AKK/AMP | RR/RDA/SP/16/25/01 | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | Ampara | Ampara | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 34% | 222189859.13 | 306475548.92 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-31 | 2026-06-30
RR/RDA/STA II/16/25/02/AKK/AMP | RR/RDA/STA II/16/25/02 | Concreting entrance road with culvert at Dehiaththakandiya Kelegama | Ampara | Dehiaattakandiya | Vithu Construction | 100% | 30737790.6 | 47778623.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-25
RR/RDA/STA II/16/25/03/AKK/AMP | RR/RDA/STA II/16/25/03 | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Ampara | Dehiaattakandiya | Vithu Construction | 65% | 39470000 | 60426139.14 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/STA II/16/25/04/AKK/AKK | RR/RDA/STA II/16/25/04 | Lahugala Hulannuge Roundabout road | Ampara | Akkaraipattu | Zaka Engineering Consultancy | 100% | 26597958.2 | 36508598.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-16 | 2026-03-16 | 2026-03-16
RR/RDA/16/25/10KM/01/AKK/AMP | RR/RDA/16/25/10KM/01 | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Ampara | Dehiaattakandiya | Sawsiri Construction | 17% | 24113338.37 | 34027781.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-25 | 2026-05-26
RR/RDA/16/25/10KM/02/AKK/AMP | RR/RDA/16/25/10KM/02 | Road from Nelum Cafe Junction to Neeththa | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 20% | 19318560.1 | 29760217.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-06-05
RR/RDA/16/25/10KM/03/AKK/AMP | RR/RDA/16/25/10KM/03 | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Ampara | Dehiaattakandiya | Sawsiri Construction | 55% | 21202726.44 | 32963348.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-05-25
RR/RDA/16/25/10KM/04/AKK/AMP | RR/RDA/16/25/10KM/04 | Vevinna Boogas Junction Inner Road | Ampara | Ampara | Gama Construction & Consultant pvt Ltd | 15% | 9692957.45 | 14460000 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-07 | 2026-05-08
RR/RDA/16/25/10KM/05/AKK/AMP | RR/RDA/16/25/10KM/05 | Road from Dorapaha Junction to Navagiriya Lake | Ampara | Ampara | Ema Constructions (Pvt) Ltd | 10% | 18058942 | 28554939.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-09 | 2026-06-07
RR/RDA/16/25/10KM/06/AKK/AKK | RR/RDA/16/25/10KM/06 | Hulannuge School Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 100% | 11406166.73 | 17414587.68 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-24 | 2026-04-27
RR/RDA/16/25/10KM/07/AKK/AMP | RR/RDA/16/25/10KM/07 | Bedirakka Malgastalawa Road | Ampara | Dehiaattakandiya | Pearl Construction | 0% | 16362791.5 | 28483156.49 | Awarded | Tender Below 50Mn |  |  |  | 2026-03-14 | 2026-05-15
RR/RDA/16/25/10KM/08/AKK/AKK | RR/RDA/16/25/10KM/08 | RDS Road Addalachena 6, 8 | Ampara | Akkaraipattu | MLH & sons Construction | 0% | 18326682.5 | 29731841.59 | Awarded | Tender Below 50Mn |  |  |  | 2026-02-26 | 2026-05-27
RR/RDA/16/25/10KM/09/AKK/AKK | RR/RDA/16/25/10KM/09 | Road behind Necode Institute (Navatkadu Akkarapattu) | Ampara | Akkaraipattu | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 100% | 15228903.25 | 24614649.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-02-26 | 2026-04-29
RR/RDA/16/25/10KM/11/AKK/AKK | RR/RDA/16/25/10KM/11 | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Ampara | Kalmunai | Zaka Engineering Consultancy | 10% | 20596083.2 | 32835450.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-08 | 2026-06-06
RR/RDA/16/25/10KM/13/AKK/AKK | RR/RDA/16/25/10KM/13 | Jaica - Tsunami Village Road | Ampara | Akkaraipattu | Gama Construction & Consultant pvt Ltd | 70% | 26167747.32 | 39951889.78 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-15 | 2026-06-13
RR/RDA/15/25/01/EP/BTC | RR/RDA/15/25/01 | Concreting to Vipulananthar road | Batticaloa | Batticaloa | SSK Construction | 100% | 29074090.89 | 44424075.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-08
RR/RDA/15/25/02/EP/BTC | RR/RDA/15/25/02 | Concreting to Samurthi 1st Cross road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 20% | 22158474.12 | 42354466.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2025-02-06 | 2026-02-15
RR/RDA/15/25/15/EP/BTC | RR/RDA/15/25/15 | Concrete to the Majma Nagar Mullivattuvan at paper town 210B | Batticaloa | Batticaloa | KMC Construction | 80% | 25270404.71 | 44093282.42 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/05/EP/BTC | RR/RDA/15/25/05 | Concreting to Mailanthanai Sri Muththumariyamman Main Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 50% | 23225083.2 | 44365292.45 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/07/EP/BTC | RR/RDA/15/25/07 | Concreting to Thakwa masjith Cross Road | Batticaloa | Batticaloa | Nazeeha Hardware and Construction | 100% | 22206567.3 | 36804461.32 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/09/EP/BTC | RR/RDA/15/25/09 | Concreting to NHDA Housing Scheme Internal Road 1st 2nd Cross | Batticaloa | Batticaloa | DKJ Construction | 40% | 7972333.63 | 16362900.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-15
RR/RDA/15/25/11/EP/BTC | RR/RDA/15/25/11 | Concreting to Kali Kovil Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 5% | 14105564 | 27925821.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/12/EP/BTC | RR/RDA/15/25/12 | Concreting to Muthalaikuda to Munnaikkadu Boundary Road | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 40% | 26564874.51 | 47720744.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/13/EP/BTC | RR/RDA/15/25/13 | Concreting to Sangarpuram- Vilavadi | Batticaloa | Batticaloa | Kumaran Construction and Civil Works | 10% | 24189660 | 46948339.52 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-02-15
RR/RDA/15/25/14/EP/BTC | RR/RDA/15/25/14 | Concreting to Agriculture Road | Batticaloa | Batticaloa | Jeezan Trading and Transport | 60% | 10593750 | 21690291.65 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-07 | 2026-02-06 | 2026-02-08
RR/RDA/15/25/10KM/01/BTC | RR/RDA/15/25/10KM/01 | Sooriya farm Road sathurukondan | Batticaloa | Batticaloa | Ganan Construction | 50% | 20565497.24 | 29978952.9 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/02/BTC | RR/RDA/15/25/10KM/02 | Iruthayapuram west 8th cross | Batticaloa | Batticaloa | Sanju Civil Construction | 30% | 27156544.25 | 37780902.59 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/15/25/10KM/06/BTC | RR/RDA/15/25/10KM/06 | Al Ameen Vidyaya Road | Batticaloa | Batticaloa | Nathan's Construction | 20% | 32841084.21 | 48327996.29 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/15/25/10KM/07/BTC | RR/RDA/15/25/10KM/07 | Kanady cross Road to Magalingeshwarar kovil Road | Batticaloa | Batticaloa | Motec Engineering & Construction | 5% | 25946118 | 36198556.07 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/15/25/10KM/08/BTC | RR/RDA/15/25/10KM/08 | Poosakar Road, Kannakipuram, Mahiloor | Batticaloa | Batticaloa | Nathan's Construction | 95% | 27673151 | 40745256.81 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-24 | 2026-10-23
RR/RDA/17/25/01/EP/TRN | RR/RDA/17/25/01 | Pillayar Road Renovation | Trincomalee | Trincomalee | Rina Construction | 100% | 23425921.56 | 30058596.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/02/EP/TRN | RR/RDA/17/25/02 | Kathirkamathambi Road | Trincomalee | Trincomalee | Fareed | 100% | 28809738 | 38871590.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/03/EP/TRN | RR/RDA/17/25/03 | Hospital Road | Trincomalee | Trincomalee | Pragash Construction | 100% | 18557253.77 | 23553502.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2025-12-15
RR/RDA/17/25/05/EP/TRN | RR/RDA/17/25/05 | Improvement to Jeyanthiwewa to Track 12 Main Road | Trincomalee | Trincomalee | Nirupama Construction | 65% | 103260000 | 160000893.78 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-12 | 2027-03-11 | 2026-09-15
RR/RDA/17/25/06/EP/TRN | RR/RDA/17/25/06 | Malporuwa to Thalgaswewa | Trincomalee | Trincomalee | Jeezan Trading and Transport | 7% | 109630000 | 163676063.08 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-03-12 | 2027-03-11 | 2026-10-15
RR/RDA/17/25/07/EP/TRN | RR/RDA/17/25/07 | Kanthamalawa Main Road | Trincomalee | Trincomalee | SSK Construction | 100% | 9161570 | 17579515.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-04-23 | 2026-07-23
RR/RDA/17/25/09/EP/TRN | RR/RDA/17/25/09 | School-Galmetiyawa Main Internal Road | Trincomalee | Trincomalee | Zaka Engineering Consultancy | 50% | 53122107.5 | 77200000 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21 | 2026-07-31
RR/RDA/17/25/10/EP/TRN | RR/RDA/17/25/10 | From Medagama temple to Peramaduwa | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 24197635 | 31162876.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-20 | 2026-01-30
RR/RDA/17/25/11/EP/TRN | RR/RDA/17/25/11 | Development of Road from near the Fair | Trincomalee | Trincomalee | MS Construction | 15% | 25280343.6 | 37892493.36 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/17/25/12/EP/TRN | RR/RDA/17/25/12 | Improvement of RDS Road | Trincomalee | Trincomalee | MTA Construction | 100% | 30166053 | 38673984.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-04 | 2026-02-03 | 2025-12-15
RR/RDA/17/25/13/EP/TRN | RR/RDA/17/25/13 | Concreting from School junction to Boovidya Office | Trincomalee | Trincomalee | Hana Construction (Pvt) Ltd. | 100% | 38264100 | 49104899.44 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-07-31
RR/RDA/17/25/14/EP/TRN | RR/RDA/17/25/14 | Amaithusha Road (School road to Vaithiyar road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 5006100 | 6650570.02 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-21 | 2026-02-19 | 2026-05-30
RR/RDA/17/25/15/EP/TRN | RR/RDA/17/25/15 | Cemetery Road (Sajahan Mowlavi's house to Thajudeen shop) | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 100% | 21774456 | 27637562.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-04 | 2026-02-04
RR/RDA/17/25/16/EP/TRN | RR/RDA/17/25/16 | Valuvar Road (Main road to Kovil road) | Trincomalee | Trincomalee | Shaniff Construction | 100% | 10783850 | 13997601.51 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/17/25/18/EP/TRN | RR/RDA/17/25/18 | Sooranagar Main Road (Muththuchenai Junction to Thuvaraka Vithiyalayam)-Concrete | Trincomalee | Trincomalee | SSK Construction | 100% | 25155240 | 38483392.5 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-02 | 2026-09-01
RR/RDA/17/25/19/EP/TRN | RR/RDA/17/25/19 | Periya Suwami Kovil Road-Concrete | Trincomalee | Trincomalee | Motec Engineering & Construction | 20% | 25774146 | 39914113.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03
RR/RDA/SP/17/25/01/EP/TRN | RR/RDA/SP/17/25/01 | Alankerny faisal Main Road (Koof Nagar) | Trincomalee | Trincomalee | NAS Construction | 100% | 26879843.97 | 35125795.85 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-12-02 | 2026-03-02 | 2026-01-30
RR/RDA/SP/17/25/03/EP/TRN | RR/RDA/SP/17/25/03 | Hajra Road (Alhira Jalaira Road) | Trincomalee | Trincomalee | STAAR Construction | 40% | 38692742 | 51948669.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-05-22 | 2026-08-21
RR/RDA/STAII/17/25/03/EP/TRN | RR/RDA/STA II/17/25/03 | From No.908 house to No.904 house road | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 15% | 10476638.8 | 14487311.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/STAII/17/25/04/EP/TRN | RR/RDA/STA II/17/25/04 | From No.851 house to Rajaela road | Trincomalee | Trincomalee | ARN Engineering & Construction | 15% | 10452104.5 | 13792738.83 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/17/25/10KM/01/EP/TRN | RR/RDA/17/25/10KM/01 | Road behind th hospital up to the morgue junction | Trincomalee | Trincomalee | Soyuru Sampath Construction & Suppliers | 10% | 13214817 | 15950150.82 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/02/EP/TRN | RR/RDA/17/25/10KM/02 | LB cannel bridge to pachchimarama temple | Trincomalee | Trincomalee | Rina Construction | 5% | 16850648.32 | 19678704.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/03/EP/TRN | RR/RDA/17/25/10KM/03 | Ethabendiwewa Second Lane | Trincomalee | Trincomalee | Nathan's Construction | 90% | 38931574 | 46705794.64 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-07 | 2026-11-05
RR/RDA/17/25/10KM/04/EP/TRN | RR/RDA/17/25/10KM/04 | Kajuwaththa gama meda road | Trincomalee | Trincomalee | NMST Construction | 5% | 22770000 | 29466015.3 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/06/EP/TRN | RR/RDA/17/25/10KM/06 | Budu pilima and 4th lane road | Trincomalee | Trincomalee | RS Construction | 15% | 17520285.64 | 28351870.49 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-07-31 | 2026-10-29
RR/RDA/17/25/10KM/07/EP/TRN | RR/RDA/17/25/10KM/07 | Kawanthissa mawatha and in front of the cementerv road | Trincomalee | Trincomalee | Rina Construction | 20% | 15075988.4 | 20683158.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-10 | 2026-11-08
RR/RDA/17/25/10KM/08/EP/TRN | RR/RDA/17/25/10KM/08 | Paththini Amman Kevil road | Trincomalee | Trincomalee | Alpha Engineering Services & Suppliers | 25% | 30365709 | 46089014.73 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/17/25/10KM/09/EP/TRN | RR/RDA/17/25/10KM/09 | Bazar mosque road | Trincomalee | Trincomalee | MTA Construction | 40% | 32616074.7 | 44293054.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-08-04 | 2026-11-03
RR/RDA/16/25/05 |  | Jannah Road from Annor Road to Jannah Mosque Junction | Ampara | Akkaraipattu |  | 100% | 15746511.36 | 15746511.36 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-21 | 2025-09-30
RR/RDA/16/25/06 |  | Improvement of Mosque Lane from beach Road to Jummah Mosque Lane (0+500)m | Ampara | Kalmunai |  | 100% | 22306322.17 | 22306322.17 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-23 | 2025-09-30
RR/RDA/SP/16/25/02 |  | Karana junction south pahalawela palanoya road (From near Pahalalanda post office junction to Karanagama) | Ampara | Ampara |  | 100% | 171722366.66 | 171722366.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-22 |  | 2025-11-15
RR/RDA/16/25/02 |  | Muwagammana First Lane to Cemetry | Ampara | Dehiaattakandiya |  | 100% | 37324257.12 | 37324257.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-16 | 2025-11-30
RR/RDA/STA II/17/25/01 |  | Hira Village Road | Ampara | Kalmunai |  | 100% | 48842501.78 | 48842501.78 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2025-11-30
RR/RDA/16/25/10KM/10 |  | Imam Roomy School Road | Ampara | Kalmunai |  | 100% | 13946909.31 | 13946909.31 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-10 |  | 2026-03-15
RR/RDA/16/25/10KM/12 |  | Kalyana Road | Ampara | Kalmunai |  | 100% | 36778852.24 | 36778852.24 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-10 |  | 2026-03-15
RR/RDA/15/25/08 |  | Kumpila Madu Road | Batticaloa | Batticaloa |  | 100% | 32424899.67 | 32424899.67 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/17/25/04 |  | Cemetry Road (Poompuhr) | Trincomalee | Trincomalee |  | 100% | 32194573.49 | 32194573.49 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/15/25/10 |  | Concreting to Internal at MMV School | Batticaloa | Batticaloa |  | 95% | 33890314.66 | 33890314.66 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-15 | 2026-03-15
RR/RDA/17/25/17 |  | Furkaniya Marcus connection road (S.M.Unithu house to Market main road) | Trincomalee | Trincomalee |  | 100% | 15444993.23 | 15444993.23 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-30
RR/RDA/17/25/08 |  | Concreting of Play Ground Road Mahadiulwewa Stage II | Trincomalee | Trincomalee |  | 90% | 43210842.75 | 43210842.75 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-02 | 2026-03-31 | 2026-03-31