## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/15/25/10 |  | Concreting to Internal at MMV School | Batticaloa | Batticaloa |  | 95% | 33890314.66 | 33890314.66 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-15 | 2026-03-15
RR/RDA/17/25/08 |  | Concreting of Play Ground Road Mahadiulwewa Stage II | Trincomalee | Trincomalee |  | 90% | 43210842.75 | 43210842.75 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-02 | 2026-03-31 | 2026-03-31