## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/18/25/02/NWP/KRG | RR/RDA/18/25/02 | Road from Parakumpura to Yaya 04 | Kurunegala | Maho | Ingress Engineering | 100% | 20126522.24 | 24748740.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-29 | 2026-02-04 | 2025-12-28
RR/RDA/18/25/08/NWP/KRG | RR/RDA/18/25/08 | Paving of road from Nammuawa to Nagansole temple | Kurunegala | Maho | Omega Construction (Pvt) Ltd | 100% | 33899382 | 49176148.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-04 | 2026-03-07 | 2025-12-20
RR/RDA/18/25/16/NWP/KRG | RR/RDA/18/25/16 | Development of concrete road from near Wadawa temple to the lake | Kurunegala | Kuliyapitiya | Jayawardana Constructions (Pvt) Ltd. | 100% | 25583393 | 31595236.77 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-15 | 2025-12-15
RR/RDA/18/25/24/NWP/KRG | RR/RDA/18/25/24 | Paving and developing the road from Seelarathana Mawatha to Girana Junction | Kurunegala | Kuliyapitiya | Senerath Engineering (pvt) Ltd | 100% | 37201129.8 | 57963603.67 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-03 | 2026-03-05 | 2026-04-02
RR/RDA/18/25/104/NWP/KRG | RR/RDA/18/25/104 | Pinnagolla Junction to Kokowaththa Junction VIA Alakolapelessa | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 24010872.6 | 30550483.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-21 | 2025-12-20 | 2025-12-20
RR/RDA/18/25/106/NWP/KRG | RR/RDA/18/25/106 | Thagahinna Temple Road | Kurunegala | Kurunegala | Jayawansa Construction (PVT) Ltd | 100% | 13370813.5 | 16225030.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2026-03-09 | 2025-12-15
RR/RDA/18/25/NWP/KRG/10 | RR/RDA/18/25/107 | Uyandana Yaggapitiya | Kurunegala | Kurunegala | Senerath Engineering (pvt) Ltd | 100% | 45801928.2 | 71428674.02 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-12-04 | 2026-03-03 | 2026-05-07
RR/RDA/18/25/136/NWP/KRG | RR/RDA/18/25/136 | Ranasinghe Hotel Asalin Koralaya Waththe sita Panwala Kubura Dakwa Diwena Margaya Kapat Kirima | Kurunegala | Kuliyapitiya | Jayasinghe Contractors (Pvt) Ltd. | 100% | 21718130.5 | 22994794.21 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-07 | 2026-04-07 | 2026-04-07
RR/RDA/19/25/26/NWP/PUT | RR/RDA/19/25/26 | Abayarama Mawatha Bomimakka Kovil Road to Sembandaluwa Temple Road | Puttalam | Puttalam | Sampath Construction | 100% | 26275458.07 | 42010632 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-05 | 2026-02-05 | 2026-02-03
RR/RDA/19/25/28/NWP/PUT | RR/RDA/19/25/28 | Samagi Mawatha | Puttalam | Puttalam | Ranuja Construction | 100% | 25908850 | 36001594.79 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
RR/RDA/19/25/29/NWP/PUT | RR/RDA/19/25/29 | Development of the road from Galkuliya Welameda to Mrs. Deepani's house | Puttalam | Puttalam | Sampath Construction | 100% | 8675871.6 | 13481102.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-01-15 | 2026-04-15 | 2026-06-15
RR/RDA/18/25/12 |  | Anura Mahaththayalage niwase sita Nalalida dakwa kadurugaha ela dakwa margaya (Ganewatte) | Kurunegala | Kurunegala |  | 100% | 23242484.2 | 23242484.2 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/05 |  | 158 Digana Grama niladari wasame 3 patumaga (vawa dakwa) (Yapahuwa) | Kurunegala | Maho |  | 100% | 11774916.28 | 11443000 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/23 |  | Horagasagara Nawarathna handiye sita Ihala kadigamuwa handiya dakwa margaya (Bingiriya) | Kurunegala | Kuliyapitiya |  | 100% | 61588475.92 | 61588475.92 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/18/25/99 |  | Rajanganaya reservoir to Parakumpura Junction (Left bank Road) | Kurunegala | Maho |  | 100% | 312810182.55 | 312810182.55 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 |  | 2026-02-28
RR/RDA/19/25/09 |  | Water front Mawatha (wennappuwa) | Puttalam | Chilaw |  | 100% | 12072583.1 | 12072583.1 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/19/25/03 |  | Nawagattegama Rohala Pare sita Thapal Karyalaya Dakwa margaya (Nawagattegama) | Puttalam | Puttalam |  | 100% | 23512239.79 | 23512239.79 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/18/25/06 |  | Walaliya Piduruwellewa road to the middle of the village | Kurunegala | Maho |  | 100% | 19431074.96 | 19537451.95 | Awarded | DL Stage 02 | Yes | Yes | Yes
RR/RDA/18/25/17 |  | No. 245 from near Jeevan Lasantha's house no. 37 Development of the main road up to Mr. Nihal's house with five (5) side roads. | Kurunegala | Kuliyapitiya |  | 100% | 51911526.67 | 51911526.67 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-10-30 | 2025-11-15
RR/RDA/18/25/21 |  | Wattakkawatta Road - Paving of Road (ABC Paving) from near Kelimune Pustalaya. | Kurunegala | Kurunegala |  | 100% | 39422351.32 | 39422351.32 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 | 2025-09-10
RR/RDA/18/25/103 |  | Wellawa Thalatuwa Junction to Gepellawa Road | Kurunegala | Kurunegala |  | 100% | 31387050.89 | 31387050.89 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-04 | 2025-09-30
RR/RDA/18/25/105 |  | Thihawa Junction to Mailamada | Kurunegala | Kurunegala |  | 100% | 33866057.61 | 33866057.61 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-07 |  | 2025-10-31
RR/RDA/19/25/02 |  | Concrete development of the road from Hopper Kada junction to Elu Farm. | Puttalam | Puttalam |  | 100% | 33229489.54 | 33229489.54 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2026-01-31
RR/RDA/19/25/07 |  | Development of the road from near Kalegama School to Erungwila. | Puttalam | Chilaw |  | 100% | 55009126.14 | 55009126.14 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 |  | 2025-10-31
RR/RDA/19/25/25 |  | Development of Mada Koswadiya Bogaha Road | Puttalam | Chilaw |  | 100% | 25235881.81 | 25235881.81 | Awarded | DL Stage 03 | Yes | Yes | Yes |  |  | 2025-11-05
RR/RDA/18/25/314 |  | Road from Nugawela Junction in Walagane to Maspotha Crematorium via Temple | Kurunegala | Kurunegala |  | 100% | 41562875.57 | 41562875.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/18/25/317 |  | Lakee Land Road in Wilattawa Division | Kurunegala | Kurunegala |  | 100% | 9799762.91 | 9799762.91 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-16 |  | 2026-03-31
RR/RDA/18/25/319 |  | Kabaledevgama 3rd Lane and 4 Lane in Kaballewa Division of Kaballewa Division | Kurunegala | Kurunegala |  | 100% | 21709247.87 | 21709247.87 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-26 |  | 2026-03-31
RR/RDA/18/25/311 |  | Road from Kopihena Junction to Dangolla in Damunugala Division of Piduruwella Division | Kurunegala |  |  | 100% | 55494114.67 | 55494114.67 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-04-10
RR/RDA/18/25/312 |  | Junction in front of Narampola Thoraya Muslim College to Budanapartiya Road via Narampola | Kurunegala |  |  | 100% | 43368925.99 | 43368925.99 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-04-10
RR/RDA/19/25/35 |  | Carpeting & Development of Kolithatissa Mawatha | Puttalam | Puttalam |  | 100% | 10359335.01 | 10359335.01 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31