## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/25/24/02/SBP/RTP | RR/RDA/25/24/02 | Thundola Varathenna Road | Ratnapura | Embilipitiya | Siri Construction | 35% | 123540895.5 | 122516687.81 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-01 | 2026-05-02 | 2026-04-27
RR/RDA/24/25/21/SBP/RTP | RR/RDA/24/25/21 | Sudagala Grama Seva Division, From Sudagala to Tunudola Road up the mountain to near the cooperative | Ratnapura | Ratnapura | DKS Construction | 0% | 35222472.34 | 42448062.24 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/24/25/25/SBP/RTP | RR/RDA/24/25/25 | From the point where the Bulathgama-Pallevela road starts from Rasagala Road | Ratnapura | Pelmadulla | Sathira Construction | 0% | 7273850 | 9080628.78 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/24/25/28/SBP/RTP | RR/RDA/24/25/28 | From near Kalal Ella Rubber Store to Narangalla via Navinikanda Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 18880633.26 | 24660700.4 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-11 | 2026-11-09
RR/RDA/24/25/31/SBP/RTP | RR/RDA/24/25/31 | Development of Koratuwegoda Road from Main Road | Ratnapura | Pelmadulla | KEP Construction | 0% | 19882000.02 | 29632612.99 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-04 | 2026-12-03
RR/RDA/24/25/32/SBP/RTP | RR/RDA/24/25/32 | Weligepola to Nitta Kumbura Road | Ratnapura | Pelmadulla | Sasiri Construction | 0% | 14421268 | 18898027.21 | Awarded | Tender Below 50Mn |  |  |  | 2026-08-24 | 2026-11-22
RR/RDA/24/25/34/SBP/RTP | RR/RDA/24/25/34 | Matuwagala Mudun Kotu Road | Ratnapura | Ratnapura | DKS Construction | 0% | 0 | 33238726.51 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-15 | 2026-10-13
RR/RDA/25/25/02/SBP/KGL | RR/RDA/25/25/02 | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | Kegalle | Kegalle | EHL Constructions | 85% | 36210751.61 | 52222845.54 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-02-03 | 2026-05-04
RR/RDA/25/25/34/SBP/KGL | RR/RDA/25/25/34 | Road Connecting Ihala Palampitiya and Pahala Palampitiya | Kegalle | Ruwanwella | DKS Nishantha Construction | 0% | 26331747.62 | 36648120.48 | Awarded | Tender Below 50Mn |  |  |  | 2026-07-24 | 2026-10-22
RR/RDA/25/25/35/SBP/KGL | RR/RDA/25/25/35 | Kudadeniya Adurapola Watta Road | Kegalle | Ruwanwella | TMT Construction | 60% | 29362927.93 | 41661137.53 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-04 | 2026-06-02
RR/RDA/25/24/35 |  | Ilumba Kanda Road from Milinduthalawa Temple | Ratnapura | Embilipitiya |  | 30% | 24709638.71 | 24709638.71 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/17 |  | Pahalawaththa to Batahenkanda Road | Ratnapura | Embilipitiya |  | 10% | 112040241.38 | 112040241.38 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/19 |  | Wijeriya Iththekanda Margaya Sanwardanaya Kirima | Ratnapura | Embilipitiya |  | 35% | 72158727.69 | 72158727.69 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10
RR/RDA/25/24/20 |  | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) | Ratnapura | Embilipitiya |  | 15% | 126132479.8 | 126132479.8 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-31 | 2026-04-10