## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/02/SP/GAL | RR/RDA/07/25/02 | Delgahabedda-Kirimatiya Margaya | Galle | Galle | Dissanayaka Builders | 93% | 26404581.16 | 50069275.91 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-31
RR/RDA/07/25/05/SP/GAL | RR/RDA/07/25/05 | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Galle | Galle | Dissanayaka Builders | 95% | 25809376.97 | 45727567.86 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-28
RR/RDA/07/25/06/SP/GAL | RR/RDA/07/25/06 | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Galle | Galle | Star Light Construction | 100% | 13805759 | 22862917.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-06
RR/RDA/07/25/08/SP/GAL | RR/RDA/07/25/08 | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | Galle | Hiniduma | EHL Constructions | 100% | 27637049 | 39100160.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-09
RR/RDA/07/25/09/SP/GAL | RR/RDA/07/25/09 | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Galle | Hiniduma | DGSD Construction | 98% | 28039359.88 | 42959652.18 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-03-31
RR/RDA/07/25/11/SP/GAL | RR/RDA/07/25/11 | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Galle | Galle | Jayathissa Construction | 100% | 20801618.2 | 32148979.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-29
RR/RDA/07/25/12/SP/GAL | RR/RDA/07/25/12 | Galandeniya Margaya | Galle | Galle | Star Light Construction | 100% | 26433958.63 | 44471797.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/13/SP/GAL | RR/RDA/07/25/13 | Aganaketiya Anuruddagama Mansandiye sita Samagipura dakwa Pradana Maragaya | Galle | Galle | EHL Constructions | 0% | 66310000 | 73974599.04 | Awarded | Tender Above 50Mn
RR/RDA/07/25/15/SP/GAL | RR/RDA/07/25/15 | Dikhena Margaya | Galle | Hiniduma | Thilak Kumara Builders | 100% | 34817376.22 | 51022213.05 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/17/SP/GAL | RR/RDA/07/25/17 | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Galle | Galle | P.H. Engineering Construction (Pvt) Ltd | 47% | 20798250 | 33516218.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/19/SP/GAL | RR/RDA/07/25/19 | SuriEla Margaya | Galle | Galle | A.D. Herath Engineering | 96% | 14387747 | 18573267.25 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-09 | 2026-01-08 | 2026-02-27
RR/RDA/07/25/20/SP/GAL | RR/RDA/07/25/20 | Road from Kammale Kadaya Junction to Udumalagala Juunction | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 100% | 25272045.84 | 40743279.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-30
RR/RDA/07/26/10KM/05 | RR/RDA/07/26/10KM/05 | Widening and Development of the road from Angaliya Junction to Akuratiya Hill with culverts | Galle | Hiniduma | EHL Constructions | 0% | 36101846 | 32752577.91 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/08 | RR/RDA/07/26/10KM/08 | Development of 700 meters from Baddegama Vanduramba Road near Kola Kids Preschool and 300 meters from Temple Junction towards Dolahena | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 16745721.52 | 19813729.63 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/12 | RR/RDA/07/26/10KM/12 | 9 Pillar Junction to Mr. Asanka's Shop on Udubattawa Watta Road | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 0% | 17311725.2 | 19631662.62 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-16 | 2026-12-16
RR/RDA/07/26/10KM/14 | RR/RDA/07/26/10KM/14 | Kodagoda Thudugala Road | Galle | Galle | Jayathissa Construction | 0% | 43914369.51 | 49447887.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/07/26/10KM/18 | RR/RDA/07/26/10KM/18 | Expansion of Alikehena Road from Thalawa Junior College to Atakohota border | Galle | Galle | S.A.Construction | 0% | 32247273.3 | 34701241.47 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-24 | 2026-12-24
RR/RDA/07/26/10KM/20 | RR/RDA/07/26/10KM/20 | Development of Paramount City Road. | Galle | Galle | EHL Constructions | 0% | 17088929 | 21005952.76 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21
RR/RDA/07/26/10KM/21 | RR/RDA/07/26/10KM/21 | Concretisation of Dikhena Welamedda road up to Addunkelle with 2 culverts and side walls on both sides. | Galle | Galle | Isula Construction | 0% | 37684669 | 44235916.42 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-21 | 2026-12-21
RR/RDA/07/26/10KM/22 | RR/RDA/07/26/10KM/22 | Kapalwila Olympus Waththa I.K. Road from Mr. Sunil's house to Rakshana Village Bodhi near Ketagoda Kada. | Galle | Hiniduma | Woshitha Engineering(Pvt)Ltd | 0% | 18381732.6 | 22218525.7 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-18 | 2026-12-18
RR/RDA/25/08/03/SP/MTR | RR/RDA/25/08/03 | Wattakgoda Ayurvedha Rohala Margaya Sanwardanay kirima | Matara | Matara | Visula Construction | 100% | 33591312.7 | 40420715.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-24
RR/RDA/25/08/08/SP/MTR | RR/RDA/25/08/08 | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Matara | Deniyaya | Induwara Construction | 100% | 11168036 | 14394112.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-16
RR/RDA/25/08/10/SP/MTR | RR/RDA/25/08/10 | Arapotha Belideniya Margaya Carpet athura Sanwardanaya Kirima | Matara | Matara | Rathna Construction | 100% | 22859983.85 | 32189689.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-23 | 2025-12-23 | 2026-01-08
RR/RDA/25/08/12/SP/MTR | RR/RDA/25/08/12 | Nawalahena Palamu Para Sanwardanaya Kirima (Jagath Mahathage Niwasa asala sita Kuruppu Mahathage Niwasa Dakwa) | Matara | Matara | Rathnayake Construction | 100% | 5399259.8 | 7523859.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-01-22
RR/RDA/08/25/13/SP/MTR | RR/RDA/08/25/13 | Heelakanda Kanishta Vidyalaya asala sita Budu Medura Dakwa margaya Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 8331854.95 | 12476822.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-01-17
RR/RDA/08/25/14/SP/MTR | RR/RDA/08/25/14 | Kanaththewatta kade asala sita Mulana Ela Margaya Dakwa Sanwardanaya Kirima (Pethibemi Sahithawa) | Matara | Matara | Madurapperuma Construction & Supply | 100% | 12885039.94 | 18602255.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-02-11
RR/RDA/08/25/15/SP/MTR | RR/RDA/08/25/15 | Pasal Mawathe Weerathunga Petti Bokkuwa Asala Sita Iriyagaha Mulana Bokkuwa Dakwa Pethi Bemi yoda Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 20214236.58 | 32183364.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-02-06
RR/RDA/08/25/16/SP/MTR | RR/RDA/08/25/16 | Walgama Saddathissa Mawathe Primesity Niwasa Sankeernaye Prawesha Margaya Kapat yoda Sanwardanaya kirima | Matara | Matara | Jagath construction | 100% | 7623062.15 | 13010600.06 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23 | 2025-01-07
RR/RDA/08/25/18/SP/MTR | RR/RDA/08/25/18 | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Matara | Matara | Dashodhaya (Pvt)Ltd | 0% | 4080866.9 | 6117703.11 | Awarded | Tender Below 50Mn |  |  |  | 2025-10-09 | 2026-01-08 | 2025-12-16
RR/RDA/08/25/19/SP/MTR | RR/RDA/08/25/19 | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Matara | Deniyaya | Gamage Builders | 100% | 10371473.2 | 14049577.09 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-12-16
RR/RDA/08/25/20/SP/MTR | RR/RDA/08/25/20 | Naymbala kendawala haraha wellethota margaye wedugoda sthanaye pethi bemma sahithawa Sanwardanaya kirima | Matara | Matara | Rathnayake Construction | 100% | 3502675 | 4877230.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-15 | 2026-01-14 | 2025-12-12
| RR/RDA/08/25/26 | Development of the road by laying Asphalt starting from near Saddhatissa Junior College on the Panattiyana-Weligama road up to Barawadeniya Junction | Matara |  | GEL Construction | 0% | 135290000 | 159903564.25 | Awarded | Tender Above 50Mn
| RR/RDA/08/25/27 | Development of the Pathegama Temple Road (Massalatiya Road) by carpeting | Matara |  | GEL Construction | 0% | 81100000 | 86763583.11 | Awarded | Tender Above 50Mn
RR/RDA/09/25/08/SP/HMB | RR/RDA/09/25/08 | Carpeting Pissubedda Medagamgoda road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 98% | 28923336.75 | 46881232.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-03-20 | 2026-06-19
RR/RDA/09/25/09/SP/HMB | RR/RDA/09/25/09 | Development of the road in front of Godawela School to Ambussa Wela | Hambantota | Tangalle | A.T.L. Construction | 60% | 34500631 | 47452621.54 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-07 | 2026-07-23 | 2026-08-31
RR/RDA/09/25/11/SP/HMB | RR/RDA/09/25/11 | Development of Walasmulla Daluwakgoda School Road | Hambantota | Tangalle | Samarasinghe Construction(Pvt)Ltd | 20% | 34814777.8 | 48463720.72 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-06-04 | 2026-09-03 | 2026-09-03
RR/RDA/09/25/13/SP/HMB | RR/RDA/09/25/13 | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | Hambantota | Tangalle | A.T.L. Construction | 60% | 23847807.5 | 30673898.39 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2026-05-06 | 2026-07-22 | 2026-08-31
RR/RDA/09/26/01 | RR/RDA/09/26/01 | From near the Bedigama North Health Center to Indimandiya | Hambantota | Tangalle | Isula Construction | 0% | 31524955 | 31310907.66 | Awarded | Tender Below 50Mn |  |  |  | 2026-09-24 | 2026-12-24
RR/RDA/08/25/Si |  | Sithulpauwa Rajamaha Viharaye Katharagama Para | Hambantota | Hambantota |  | 100% | 3969390.34 | 3969390.34 | Awarded | DL Stage 01 | Yes | Yes | Yes |  | 2025-08-15
RR/RDA/07/25/07 |  | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Galle | Galle |  | 100% | 27520890.73 | 27520890.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/07/25/16 |  | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima | Galle | Hiniduma |  | 100% | 30597079.78 | 30597079.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/25/08/07 |  | Ovitigamuwa Alahenpita margaya Sanwardanaya Kirima (RDA yatathe Idikirima Arambha kara atharamaga nawatha etha) | Matara | Matara |  | 100% | 29034089.99 | 29034089.99 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/25/08/01 |  | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara | Matara | Deniyaya |  | 100% | 78061393.44 | 78061393.44 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-15 | 2026-01-31
RR/RDA/08/25/04 |  | Vigamuwa Pattiyapola Road from Vigamuwa School | Hambantota | Tangalle |  | 100% | 74802039.66 | 74802039.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/09/25/01 |  | Karametiya Road | Hambantota | Hambantota |  | 100% | 74446690.12 | 74446690.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/07/25/03 |  | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Galle | Galle |  | 100% | 26781909.97 | 26781909.97 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/07/25/04 |  | Galwehera C.P. the Silva Mawatha Carpet kirima | Galle | Galle |  | 100% | 30571235.08 | 30571235.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/18 |  | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima | Galle | Hiniduma |  | 100% | 27525465.5 | 27525465.5 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/25/08/06 |  | Samarasinghe Mawathw Ithiri Kotasa Sanwardanaya Kirima | Matara | Matara |  | 100% | 17005961.71 | 16851257.35 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-11-15
RR/RDA/25/08/11 |  | Thambagala Margaya Sanwardanaya Kirima (Highway pitawime sthanayen arambha vi Pradeepa Mahathmiyage Niwasa dakwa Kotasa) | Matara | Matara |  | 100% | 9396645.17 | 9425286.29 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/09/25/02 |  | Wam Iwura Janawasa Margaya | Hambantota | Hambantota |  | 100% | 37666563.49 | 37666563.49 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-10-25
RR/RDA/08/25/23 |  | Epitakaduwa Krishantha Senarath Yapa Road (Eptakaduwa Budu medura to Mr. LG Jagath Yapa home) | Matara | Matara |  | 100% | 7231417.22 | 7231417.22 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2025-10-31
RR/RDA/07/25/14 |  | Moonugoda Road | Galle | Galle |  | 100% | 21211506.6 | 21211506.6 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16
RR/RDA/08/25/05 |  | Koggalla bus stand to Sooriyawewa Road | Hambantota | Tangalle |  | 95% | 127573213.52 | 127573213.52 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-02-28
RR/RDA/07/25/22 |  | Asphalting Meepawala henegewaththa road | Galle | Galle |  | 100% | 21395564.1 | 21395564.1 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-19 | 2026-02-27 | 2026-02-28
RR/RDA/07/25/21 |  | Asphalting Newungala Na tree to Bedimeda road | Galle | Hiniduma |  | 100% | 35369824.16 | 35369824.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-18 | 2026-03-20 | 2026-02-15
RR/RDA/07/25/01 |  | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) | Galle | Galle |  | 98% | 76680545.16 | 76680545.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/08/25/22 |  | Kirinda Roundabout Road with drainages | Matara | Matara |  | 100% | 23083588.28 | 23083588.28 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/08/25/02 |  | Andaledduwa Road | Matara | Matara |  | 100% | 24533049.28 | 24533049.28 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-02-28
RR/RDA/09/25/12 |  | Development of the road from Lunugamwehera Jadura Lake to Udaeva | Hambantota | Hambantota |  | 92% | 66506406.57 | 66506406.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/09/25/06 |  | Raluwa main road | Hambantota | Tangalle |  | 70% | 17377865.99 | 17377865.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-12-01 |  | 2026-03-31
RR/RDA/09/25/07 |  | Carpeting Dabewelena Gravel Road | Hambantota | Hambantota |  | 98% | 54766473.95 | 54766473.95 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-10-18 | 2025-12-31 | 2026-03-31
RR/RDA/09/25/14 |  | Development of road near Olu ara School | Hambantota | Tangalle |  | 90% | 101801692.33 | 101801692.33 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/09/25/10 |  | Development of Valasmulla Pallekanda road from 3 km post to 5 km post | Hambantota | Tangalle |  | 95% | 84525263.23 | 84525263.23 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-10 |  | 2026-03-31