## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/07/25/06/SP/GAL | RR/RDA/07/25/06 | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Galle | Galle | Star Light Construction | 100% | 13805759 | 22862917.58 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-06
RR/RDA/07/25/08/SP/GAL | RR/RDA/07/25/08 | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | Galle | Hiniduma | EHL Constructions | 100% | 27637049 | 39100160.8 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-09
RR/RDA/07/25/11/SP/GAL | RR/RDA/07/25/11 | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Galle | Galle | Jayathissa Construction | 100% | 20801618.2 | 32148979.96 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2025-12-29
RR/RDA/07/25/12/SP/GAL | RR/RDA/07/25/12 | Galandeniya Margaya | Galle | Galle | Star Light Construction | 100% | 26433958.63 | 44471797.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/15/SP/GAL | RR/RDA/07/25/15 | Dikhena Margaya | Galle | Hiniduma | Thilak Kumara Builders | 100% | 34817376.22 | 51022213.05 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-30
RR/RDA/07/25/20/SP/GAL | RR/RDA/07/25/20 | Road from Kammale Kadaya Junction to Udumalagala Juunction | Galle | Hiniduma | Kumarage Enterprises(Pvt)Ltd | 100% | 25272045.84 | 40743279.23 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-10 | 2026-01-09 | 2026-01-30
RR/RDA/25/08/03/SP/MTR | RR/RDA/25/08/03 | Wattakgoda Ayurvedha Rohala Margaya Sanwardanay kirima | Matara | Matara | Visula Construction | 100% | 33591312.7 | 40420715.27 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-16 | 2025-12-16 | 2026-01-24
RR/RDA/25/08/08/SP/MTR | RR/RDA/25/08/08 | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Matara | Deniyaya | Induwara Construction | 100% | 11168036 | 14394112.26 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-02-16
RR/RDA/25/08/10/SP/MTR | RR/RDA/25/08/10 | Arapotha Belideniya Margaya Carpet athura Sanwardanaya Kirima | Matara | Matara | Rathna Construction | 100% | 22859983.85 | 32189689.87 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-09-23 | 2025-12-23 | 2026-01-08
RR/RDA/25/08/12/SP/MTR | RR/RDA/25/08/12 | Nawalahena Palamu Para Sanwardanaya Kirima (Jagath Mahathage Niwasa asala sita Kuruppu Mahathage Niwasa Dakwa) | Matara | Matara | Rathnayake Construction | 100% | 5399259.8 | 7523859.66 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-17 | 2026-01-16 | 2026-01-22
RR/RDA/08/25/13/SP/MTR | RR/RDA/08/25/13 | Heelakanda Kanishta Vidyalaya asala sita Budu Medura Dakwa margaya Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 8331854.95 | 12476822.24 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-01-17
RR/RDA/08/25/14/SP/MTR | RR/RDA/08/25/14 | Kanaththewatta kade asala sita Mulana Ela Margaya Dakwa Sanwardanaya Kirima (Pethibemi Sahithawa) | Matara | Matara | Madurapperuma Construction & Supply | 100% | 12885039.94 | 18602255.2 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2026-02-11
RR/RDA/08/25/15/SP/MTR | RR/RDA/08/25/15 | Pasal Mawathe Weerathunga Petti Bokkuwa Asala Sita Iriyagaha Mulana Bokkuwa Dakwa Pethi Bemi yoda Sanwardanaya Kirima | Matara | Matara | Madurapperuma Construction & Supply | 100% | 20214236.58 | 32183364.43 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-02-06
RR/RDA/08/25/16/SP/MTR | RR/RDA/08/25/16 | Walgama Saddathissa Mawathe Primesity Niwasa Sankeernaye Prawesha Margaya Kapat yoda Sanwardanaya kirima | Matara | Matara | Jagath construction | 100% | 7623062.15 | 13010600.06 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-24 | 2026-01-23 | 2025-01-07
RR/RDA/08/25/19/SP/MTR | RR/RDA/08/25/19 | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Matara | Deniyaya | Gamage Builders | 100% | 10371473.2 | 14049577.09 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-06 | 2026-01-05 | 2025-12-16
RR/RDA/08/25/20/SP/MTR | RR/RDA/08/25/20 | Naymbala kendawala haraha wellethota margaye wedugoda sthanaye pethi bemma sahithawa Sanwardanaya kirima | Matara | Matara | Rathnayake Construction | 100% | 3502675 | 4877230.33 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-15 | 2026-01-14 | 2025-12-12
RR/RDA/08/25/Si |  | Sithulpauwa Rajamaha Viharaye Katharagama Para | Hambantota | Hambantota |  | 100% | 3969390.34 | 3969390.34 | Awarded | DL Stage 01 | Yes | Yes | Yes |  | 2025-08-15
RR/RDA/07/25/07 |  | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Galle | Galle |  | 100% | 27520890.73 | 27520890.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/07/25/16 |  | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima | Galle | Hiniduma |  | 100% | 30597079.78 | 30597079.78 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-31
RR/RDA/25/08/07 |  | Ovitigamuwa Alahenpita margaya Sanwardanaya Kirima (RDA yatathe Idikirima Arambha kara atharamaga nawatha etha) | Matara | Matara |  | 100% | 29034089.99 | 29034089.99 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-22
RR/RDA/25/08/01 |  | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara | Matara | Deniyaya |  | 100% | 78061393.44 | 78061393.44 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-15 | 2026-01-31
RR/RDA/08/25/04 |  | Vigamuwa Pattiyapola Road from Vigamuwa School | Hambantota | Tangalle |  | 100% | 74802039.66 | 74802039.66 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/09/25/01 |  | Karametiya Road | Hambantota | Hambantota |  | 100% | 74446690.12 | 74446690.12 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/07/25/03 |  | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Galle | Galle |  | 100% | 26781909.97 | 26781909.97 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/07/25/04 |  | Galwehera C.P. the Silva Mawatha Carpet kirima | Galle | Galle |  | 100% | 30571235.08 | 30571235.09 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/07/25/18 |  | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima | Galle | Hiniduma |  | 100% | 27525465.5 | 27525465.5 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30
RR/RDA/25/08/06 |  | Samarasinghe Mawathw Ithiri Kotasa Sanwardanaya Kirima | Matara | Matara |  | 100% | 17005961.71 | 16851257.35 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-11-15
RR/RDA/25/08/11 |  | Thambagala Margaya Sanwardanaya Kirima (Highway pitawime sthanayen arambha vi Pradeepa Mahathmiyage Niwasa dakwa Kotasa) | Matara | Matara |  | 100% | 9396645.17 | 9425286.29 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-15
RR/RDA/09/25/02 |  | Wam Iwura Janawasa Margaya | Hambantota | Hambantota |  | 100% | 37666563.49 | 37666563.49 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-10-30 | 2025-10-25
RR/RDA/08/25/23 |  | Epitakaduwa Krishantha Senarath Yapa Road (Eptakaduwa Budu medura to Mr. LG Jagath Yapa home) | Matara | Matara |  | 100% | 7231417.22 | 7231417.22 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16 | 2025-10-31
RR/RDA/07/25/14 |  | Moonugoda Road | Galle | Galle |  | 100% | 21211506.6 | 21211506.6 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-16
RR/RDA/07/25/22 |  | Asphalting Meepawala henegewaththa road | Galle | Galle |  | 100% | 21395564.1 | 21395564.1 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-19 | 2026-02-27 | 2026-02-28
RR/RDA/07/25/21 |  | Asphalting Newungala Na tree to Bedimeda road | Galle | Hiniduma |  | 100% | 35369824.16 | 35369824.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-11-18 | 2026-03-20 | 2026-02-15
RR/RDA/07/25/01 |  | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) | Galle | Galle |  | 98% | 76680545.16 | 76680545.16 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/08/25/22 |  | Kirinda Roundabout Road with drainages | Matara | Matara |  | 100% | 23083588.28 | 23083588.28 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-02-28
RR/RDA/08/25/02 |  | Andaledduwa Road | Matara | Matara |  | 100% | 24533049.28 | 24533049.28 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-02-28
RR/RDA/09/25/12 |  | Development of the road from Lunugamwehera Jadura Lake to Udaeva | Hambantota | Hambantota |  | 92% | 66506406.57 | 66506406.57 | Awarded | DL Stage 04 | Yes | Yes | Yes |  |  | 2026-03-31
RR/RDA/09/25/06 |  | Raluwa main road | Hambantota | Tangalle |  | 70% | 17377865.99 | 17377865.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2025-12-01 |  | 2026-03-31
RR/RDA/09/25/14 |  | Development of road near Olu ara School | Hambantota | Tangalle |  | 90% | 101801692.33 | 101801692.33 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/09/25/10 |  | Development of Valasmulla Pallekanda road from 3 km post to 5 km post | Hambantota | Tangalle |  | 95% | 84525263.23 | 84525263.23 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-02-10 |  | 2026-03-31