## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/22/25/01/UP/BDL | RR/RDA/22/25/01 | Kirikoonthenna Gamata piwisena Margaya | Badulla | Mahiyanganaya | Ema Constructions (Pvt) Ltd | 100% | 15276800 | 22562884.94 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/02/UP/BDL | RR/RDA/22/25/02 | 23 Ela Krushi Margaya | Badulla | Mahiyanganaya | Priyankara Industries and Contractors | 100% | 22422274.05 | 34734403.93 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/04/UP/BDL | RR/RDA/22/25/04 | Buluwa Margaya | Badulla | Mahiyanganaya | Samadhi Construction | 100% | 19800000 | 27796703.13 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
RR/RDA/22/25/08/UP/BDL | RR/RDA/22/25/08 | Maragaha ella Margaya Concrete Kireema | Badulla | Bandarawela | Priyantha Rathnayaka | 100% | 5650802.3 | 9166668.15 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/12/UP/BDL | RR/RDA/22/25/12 | Galwelagama Margaye Pansala Asala Kotasa | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 16955320.78 | 19698086.11 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-14 | 2026-02-13
RR/RDA/22/25/14/UP/BDL | RR/RDA/22/25/14 | Pulleyar Kadura sita Keselwaththa Dakwa Piwisena Athrur Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 6085915 | 7780120.14 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/15/UP/BDL | RR/RDA/22/25/15 | Gallulla sita Galwelagama Margaya | Badulla | Badulla | Ema Constructions (Pvt) Ltd | 100% | 15696340 | 19949882.12 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-07 | 2026-01-06
RR/RDA/22/25/18/UP/BDL | RR/RDA/22/25/18 | Pelgahathenna Vidyalaya asalin Landewela dakwa athi Margaya | Badulla | Badulla | Prasad Builders | 100% | 5317232 | 6839881.74 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-11 | 2026-02-10
RR/RDA/22/25/19/UP/BDL | RR/RDA/22/25/19 | Tholabowaththa sita Meedumpitiya Dakwa yana Athuru Margaya | Badulla | Badulla | Priyankara Industries and Contractors | 100% | 30478561.74 | 47901120.62 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-11-06 | 2026-02-05
| RR/RDA/23/25/44 | Kiriibban wewa Ayurweda road | Monaragala | Monaragala | U P Ranugge Construction (Pvt) Ltd | 100% | 34095028 | 53343034.36 | Awarded | Tender Above 50Mn | Yes | Yes | Yes | 2026-01-12
RR/RDA/22/25/32 |  | Asphalt laying and Development of Haddaththawa 80 Acre road | Badulla | Mahiyanganaya |  | 100% | 93242250.14 | 93242250.14 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/22/25/03 |  | Hubaslinda Meda Margaya | Badulla | Mahiyanganaya |  | 100% | 19159838.84 | 19159838.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25 | 2025-10-31
RR/RDA/22/25/16 |  | Dameria Handiye sita wathu Karyalaya Dakwa Margaya | Badulla | Badulla |  | 100% | 12215323.92 | 12215323.92 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/22/26/01 |  | Rajamawatha Road | Badulla | Bandarawela |  | 100% | 15077652.84 | 15077652.84 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-25
RR/RDA/23/25/01 |  | Puwakgoda Uramada Margaya K.M.Thilak Bandara Mahathage niwasa idiripita sita ema Margayema R.M.Punchi Nona Mahathmiyage Niwasa Dakwa Margaya | Monaragala | Bibile |  | 100% | 64599474.91 | 64599474.91 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15
RR/RDA/23/25/04 |  | Walawegaga Asala (Nildiya Mankada) Sita Udawalawa Bant eka Dakwa | Monaragala | Monaragala |  | 100% | 74104374.63 | 74104374.63 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-15 | 2025-10-31
RR/RDA/22/25/13 |  | Peessa Pradana Margaye Abalan wu Ellanda Marga Kotasa | Badulla | Badulla |  | 100% | 13192586.35 | 13192586.35 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2026-02-06
RR/RDA/22/25/10 |  | Kosgolla Edaru Ulpatha Margaya | Badulla | Bandarawela |  | 100% | 13085885.7 | 13085885.7 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-20
RR/RDA/23/25/03 |  | Liyangolla Lolla Margaya | Monaragala | Bibile |  | 100% | 38879897 | 38879897 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-30
RR/RDA/23/25/02 |  | Uduwara wewa Handiya sita Athula Margaya | Monaragala | Bibile |  | 100% | 34079767.34 | 34079767.34 | Awarded | DL Stage 02 | Yes | Yes | Yes |  | 2025-10-30 | 2025-11-30