## Awarded Projects
Contract No. | Package No. | Contract Name | District | EE Division | Contractor | Progress (%) | LOA Amount (LKR) | Estimate Amount (LKR) | Status | Method | Mobilized | Kick Off | Active | Date of Commencement | Date of Completion | Anticipated Completion Date
RR/RDA/01/25/03/WP/COL | RR/RDA/01/25/03 | Appropriate development of road from Maligagodella lake crossing near Isuri Motors to junction with Chandrika Kumaratunga Mawatha | Colombo | Colombo | Jayasinghe Contractors (Pvt) Ltd. | 100% | 23009836.05 | 31303935.95 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-16 | 2026-01-29
RR/RDA/01/25/09/WP/COL | RR/RDA/01/25/09 | Kottawa Malabe Road Sirimalwatta 1 Main road carpeted and developed | Colombo | Avissawella | Accon Engineering (PVT) LTD | 100% | 2424881.23 | 2804484.03 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-14 | 2025-11-30
RR/RDA/01/25/12/WP/COL | RR/RDA/01/25/12 | 550 A Lakshapathi North Sri Lanka Army Electrical and Mechanical Engineering Base Workshop (Katupedda) to be carpeted and developed from Galle Road. | Colombo | Colombo | Accon Engineering (PVT) LTD | 100% | 8465142.73 | 11014256.76 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-02-12 | 2025-12-29
RR/RDA/02/25/05/WP/GMP | RR/RDA/02/25/05 | Improvements to 70/A Pahala Kandawala Grama Niladharee wasame suuriya mawathe athuru mawathak wana jayashantha mahathaage niwasa asalin athi para praja shaalawa dakwaa saha dakunu pasata thi wiharasthanaya dakwa kotasa | Gampaha | Negombo | Jeyanthan Construction | 100% | 16250193.4 | 21560731.47 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-23
RR/RDA/03/25/02/WP/KTR | RR/RDA/03/25/02 | Concreting of the first side road on the left side of Rasik Road | Kalutara | Kalutara | Develco Engineering (PVT) LTD | 100% | 7705537.2 | 11126896.75 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/03/WP/KTR | RR/RDA/03/25/03 | Carpeting of Uswatta Lane | Kalutara | Kalutara | Ramano Engineers | 100% | 6059612.5 | 7444801.7 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2025-12-29
RR/RDA/03/25/05/WP/KTR | RR/RDA/03/25/05 | From near Mr. Abeywardena's house on the Yawita Kammalgoda road block stones and development (first phase) | Kalutara | Horana | Develco Engineering (PVT) LTD | 100% | 21827299.85 | 31800339.88 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/03/25/08/WP/KTR | RR/RDA/03/25/08 | Asphalting from near Valkandala transformer to Panthiya Watta (Malamiriskanda road) | Kalutara | Agalawatta | Accon Engineering (PVT) LTD | 100% | 14577590.15 | 22843424.38 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29 | 2025-12-15
RR/RDA/03/25/09/WP/KTR | RR/RDA/03/25/09 | Concreting of Weedahena road | Kalutara | Agalawatta | Develco Engineering (PVT) LTD | 100% | 15010244 | 19919301.67 | Awarded | Tender Below 50Mn | Yes | Yes | Yes | 2025-10-30 | 2026-01-29
RR/RDA/01/25/11 |  | Vijitha Salawa asala sita Kothalawala Vidyalaya Asalin Gothami Viharaya dakva Margaya | Colombo | Colombo |  | 100% | 17512654.33 | 17512654.33 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/01/25/07 |  | 428/B Ihala Kosgama Grama Niladhari Wasame Praja Shalawa Pahala Margaya | Colombo | Avissawella |  | 100% | 51557606.95 | 51557606.95 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-10-17
RR/RDA/02/25/02 |  | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Gampaha | Gampaha |  | 100% | 10523274.77 | 10523274.77 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-08-15
RR/RDA/02/25/01 |  | Heendeniya Dumriya Sthanaya Dakwa Margaya | Gampaha | Nittambuwa |  | 100% | 13144147.11 | 13144147.11 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-07-09
RR/RDA/02/25/04 |  | Delpe Kadawara sita Nelumwaththa margaya arambaye sita Dewadasa mahathage niwasa dakwa Margaya | Gampaha | Negombo |  | 100% | 26006255.54 | 26006255.54 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-10
RR/RDA/03/25/01 |  | Asphalting Samagipura Road (LECO office to Maha ela) | Kalutara | Kalutara |  | 100% | 25713214.4 | 25713214.4 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/03/25/04 |  | Development of the Kotupathgoda road by asphalting | Kalutara | Horana |  | 100% | 32439574.76 | 32439574.76 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21 | 2025-11-15
RR/RDA/03/25/36 |  | 10 Mw T Jayarathne mahathge niwas asala concrete kara nawatha ati sthanaya sita nawa margaya desata | Kalutara | Agalawatta |  | 100% | 34917696.41 | 34917696.41 | Awarded | DL Stage 01 | Yes | Yes | Yes | 2025-06-21 | 2025-09-21
RR/RDA/01/25/02 |  | Paving and developing the road from North Borella Ganga Lower Vivekaramaya Temple to Siwali Lane No. 241/35D. | Colombo | Colombo |  | 100% | 3636186.59 | 3636186.59 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-09-17
RR/RDA/01/25/06 |  | Development of Rambutan gahamula Suramya Mawatha using carpet in Magammana East Grama Niladhari Domain | Colombo | Avissawella |  | 100% | 16341118.27 | 16341118.27 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-08-09 | 2025-11-07 | 2025-11-15
RR/RDA/03/25/07 |  | Carpeting of Shekmadara Road | Kalutara | Kalutara |  | 100% | 14674228.65 | 14674228.65 | Awarded | DL Stage 02 | Yes | Yes | Yes | 2025-07-14 | 2025-08-07
RR/RDA/01/25/17 |  | Access road to Polgasowita Dikhena Aranya | Colombo | Avissawella |  | 100% | 7965231.1 | 7965231.1 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-26 | 2025-11-15 | 2025-11-15
RR/RDA/02/25/07 |  | Road near Ozon Educational Institiute | Gampaha | Gampaha |  | 100% | 12058540.61 | 12058540.61 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-10-27 |  | 2025-11-05
RR/RDA/03/25/11 |  | Jilani road in Darga Town | Kalutara | Kalutara |  | 100% | 14759196.13 | 14759196.13 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 | 2025-11-17 | 2025-11-25
RR/RDA/03/25/13 |  | Morapitiya Aluth Mawatha to 1st mile post via Rankoth lane | Kalutara | Agalawatta |  | 100% | 38713954.65 | 38713954.65 | Awarded | DL Stage 03 | Yes | Yes | Yes | 2025-09-16 |  | 2026-02-28
RR/RDA/01/25/16 |  | Bangalawa Road from 01st Gate to 04th Gate | Colombo | Colombo |  | 100% | 18170451.82 | 18170451.82 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01
RR/RDA/02/25/20 |  | St. Lazarus Road (Depot Road) | Gampaha | Negombo |  | 100% | 26943025.76 | 23521864.99 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 |  | 2026-03-31
RR/RDA/03/25/20 |  | Development of Gemunu Mawatha by laying 500 meters of carpet | Kalutara | Kalutara |  | 100% | 12547527.78 | 12547527.78 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-01-01 | 2026-03-12 | 2026-01-31
RR/RDA/01/25/24 |  | Development of the road from the beginning of the Horahena road from Wanaguru Mawatha in the Hokandara East Division to the Hokandara Pasmanhandiya with a carpet | Colombo | Colombo |  | 100% | 3140831.06 | 3140831.06 | Awarded | DL Stage 04 | Yes | Yes | Yes | 2026-03-07 |  | 2026-04-12
RR/RDA/01/26/10KM/04 |  | Carpeting and development of Vijithapura Liyanage Mawatha and 3rd Lane | Colombo | Colombo |  | 100% | 1560361.91 | 1560361.91 | Awarded | DL Stage 04 | Yes | Yes | Yes