## Sheet1
All Projects
Date: 2026-11-04
Contract No | Contract Name | Province | District | PD Region | CE Region | EE Division | Implementation Method | Category | Programme | Contractor | Consultant | Estimate (LKR) | Contract Amount (LKR) | Status | Progress % | LOA Date | Planned Finish
RR/RDA/04/25/13/CP/KY | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | Dharshana Construction |  | 42644514.03 | 35195820 | Awarded | 37% | 2026-04-24 | 2026-08-21
RR/RDA/04/25/15/CP/KY | Madolkale sita Huluganga dakwa yana athuru margaye Bandaranayakapura gam kotasata adala Margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | UGD Constructions |  | 20856501.79 | 12711509.59 | Awarded | 100% | 2025-09-17 | 2025-12-31
| Palawa ihala meda Wijitha mawatha Waliyangadeniya margaya yakarana athuru Margaya | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Tender Below 50Mn | Tender | Rural Road | Galahitiyawa Builders |  | 16221430 | 12240493.1 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/04/25/17/CP/KY | Nuganga Margaya | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Tender Below 50Mn | Tender | Rural Road | Weebedda Construction |  | 15455845 | 9650635.5 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/04/25/19/CP/KY | Mulgama viduhala Asala sita lewalan dakwa | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road | The Wise Lanka Construction Company (Pvt) Ltd |  | 46131296.3 | 25917512.5 | Awarded | 35% | 2025-09-17 | 2026-01-14
RR/RDA/04/25/20/CP/KY | Carpeting road Ratemulla to Wendesiwaththa End | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Below 50Mn | Tender | Rural Road | Wiscon (Pvt) Ltd |  | 40119276.86 | 36995817.1 | Awarded | 45% | 2025-10-24 | 2026-02-05
RR/RDA/04/25/21/CP/KY | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road | UGD Constructions |  | 40719533.36 | 22711029 | Awarded | 80% | 2025-09-17 | 2025-12-31
RR/RDA/04/25/22/CP/KY | Rambukwella viharasthanaya asala sita Dodamgolla Rambukwella nagenhira haraha Udispaththuwa dakwa diwena Margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | The Wise Lanka Construction Company (Pvt) Ltd |  | 26802449.26 | 15056107 | Awarded | 100% | 2025-09-17 | 2025-12-31
RR/RDA/04/25/23/CP/KY | Minuwangamuwa gammada margaye Aberathne mahathage niwasa asala sita Abesinha Banda mahathage Niwasa dakwa | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | The Wise Lanka Construction Company (Pvt) Ltd |  | 49079937.23 | 27734432.55 | Awarded | 100% | 2025-09-17 | 2026-01-14
RR/RDA/04/25/24/CP/KY | Galamuduna gamata pivisena Margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Above 50Mn | Tender | Rural Road | NAGMA ENGINEERING (PVT) LTD |  | 201921834.86 | 157638978.9 | Awarded | 0% | 2026-01-14
RR/RDA/04/25/25/CP/KY | Delgasthenna Road | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Above 50Mn | Tender | Rural Road | NAGMA ENGINEERING (PVT) LTD |  | 78736509.47 | 56035922.24 | Awarded | 0% | 2025-11-19 | 2026-05-06
RR/RDA/04/25/27/CP/KY | Dadahogama pitiye gedara pathibami sahitha Margaya | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Below 50Mn | Tender | Rural Road | Nimsara Construction & Holdings (PVT) Ltd |  | 14990258.08 | 12532355 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/04/25/28/CP/KY | Dehideniya sita Hedeniya dakwa Margaya | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 41827394.04 | 38495776 | Awarded | 35% | 2025-09-26 | 2026-01-23
RR/RDA/04/25/31/CP/KY | Shantha Janapada Village middle road | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 47278636.42 | 42357645 | Awarded | 100% | 2025-11-20 | 2026-03-05
RR/RDA/04/25/31(1)/CP/KY | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Above 50Mn | Tender | Rural Road | Central Engineering Services Pvt Ltd. (CESL) |  | 65989182.36 | 50476865.28 | Awarded | 30% | 2026-01-29 | 2026-07-07
RR/RDA/04/25/32/CP/KY | Pilawala Navodya pasala asala sita Nelumpathhinna pansala dakwa margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 19939938.98 | 18059531.27 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/04/25/33/CP/KY | New forest kotase Jana Udana gammana margaya | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road | The Wise Lanka Construction Company (Pvt) Ltd |  | 12512939.76 | 6992144.5 | Awarded | 100% | 2025-09-17 | 2025-12-31
RR/RDA/04/25/34/CP/KY | Liyandeniya wewa margya | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Tender Below 50Mn | Tender | Rural Road | Nimsara Construction & Holdings (PVT) Ltd |  | 11711039.23 | 9134433 | Awarded | 100% | 2025-09-26 | 2026-01-28
RR/RDA/04/25/35/CP/KY | Gamunupura Gonawatta pradana margaye Gamunupura pera pasala asala sita idiriyata pradana margaya | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 34175878.49 | 30043716.01 | Awarded | 100% | 2025-09-26 | 2026-01-08
RR/RDA/04/25/41/CP/KY | Karyala handiya pahala margya concrete kirima | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road | UGD Constructions |  | 39022781.94 | 22047564 | Awarded | 85% | 2025-09-17 | 2026-01-14
RR/RDA/04/25/43/CP/KY | Dodamgolla kowila asla sita hindu susana boomiya dakwa margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | The Wise Lanka Construction Company (Pvt) Ltd |  | 26797465.46 | 14680539.5 | Awarded | 100% | 2025-09-17 | 2025-12-31
| Development of the road from the junction at Ratkondawa to the Weralugaha junction with carpeting | Central Province | Kandy | Central Province | Kandy | Kadugannawa | Tender Below 50Mn | Tender | Rural Road |  |  | 10988812.92 |  | Pending | 0%
| Ambakote Road | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road | Dharshana Construction |  | 31070808.88 | 32019889 | Awarded | 5% | 2026-08-17
| Development of the remaining section of the rural road including the bridge near the Grama Niladhari office on the road to Beerahena | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road |  |  | 30655557.8 |  | Pending | 0%
RR/RDA/04/25/52/CP/KY | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 72631674.77 | 50478905 | Awarded | 60% | 2026-02-06 | 2026-08-22
RR/RDA/04/25/53/CP/KY | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Below 50Mn | Tender | Rural Road | Tiasa Construction (Pvt) Ltd |  | 39182935.51 | 29850460.2 | Awarded | 40% | 2026-04-24 | 2026-09-08
| Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Above 50Mn | Tender | Rural Road | Ajith Construction |  | 73819405.52 | 65808186.5 | Awarded | 20% | 2026-05-25 | 2026-10-05
| Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Central Province | Kandy | Central Province | Kandy | Kandy | Tender Above 50Mn | Tender | Rural Road | Southern Group Civil Construction (Pvt) Ltd. |  | 98049399.56 | 83080000 | Awarded | 40% | 2026-02-06 | 2026-08-07
| Renovation of road Haidri estate to Barcapal | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Above 50Mn | Tender | Rural Road | Ajith Construction |  | 56051060.7 | 51476130 | Awarded | 25% | 2026-05-08 | 2026-11-20
| The road to the village of Hydari Colony | Central Province | Kandy | Central Province | Kandy | Gampola | Tender Below 50Mn | Tender | Rural Road |  |  | 31437081.48 |  | Pending | 0%
| Carpeting of the road connecting Ahas Pokuna North 613 Road from 11 Pole Junction via Ahas Pokunagama to the front of Ahas Pokuna North Sevapiyasa Field and the beginning of Digana Madawala 613 Road from the east. | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Above 50Mn | Tender | Rural Road |  |  | 59264668.89 |  | Pending | 0%
| Development of Wattegama Atalogoda Road | Central Province | Kandy | Central Province | Kandy | Kundasale | Tender Below 50Mn | Tender | Rural Road |  |  | 26342945.9 |  | Pending | 0%
RR/RDA/05/25/01/CP/MTL | Moragahamada pasala asalin arambhawa Rajagammana gama madin Madawala adawala para dakwa pradana athuru Margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 60115019.16 | 41535473.64 | Awarded | 100% | 2025-11-12 | 2026-05-26
RR/RDA/05/25/02/CP/MTL | Lakshahena maragaya Mathalapitiya margaye sita Lakshahena Kosgolla dakwa Margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 50437576.84 | 36743107.5 | Awarded | 100% | 2025-09-17 | 2025-12-31
RR/RDA/05/25/04/CP/MTL | Aiththaliyadda sita Porcilain eka dakwa Margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 33583183.3 | 27015791 | Awarded | 100% | 2025-09-26 | 2026-01-07
RR/RDA/05/25/07/CP/MTL | Uladawa Mansandiye sita Homapola Janapadaye Saukkaya Maddayasthanaya dakawa Diwena Udurmpelessa thek Diwena Margaya Kapat Kirima | Central Province | Matale | Central Province | Matale | Nalanda | Tender Above 50Mn | Tender | Rural Road | Ajith Construction |  | 84423480.85 | 92740000 | Awarded | 0% | 2026-09-18
RR/RDA/05/25/08/CP/MTL | Senagama Adawala para Ambana palama asala sita Senagama haraha Andawala desata idiriyta kotasa | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road |  |  | 126940194.73 |  | Rebid | 0%
RR/RDA/05/25/09/CP/MTL | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Pragathi Civil Contractor |  | 41365188.3 | 38748820 | Awarded | 80% | 2025-09-23 | 2026-01-23
RR/RDA/05/25/10/CP/MTL | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | Central Province | Matale | Central Province | Matale | Nalanda | Tender Above 50Mn | Tender | Rural Road | NAGMA ENGINEERING (PVT) LTD |  | 79104652.3 | 56167707.75 | Awarded | 70% | 2025-11-12 | 2026-04-27
RR/RDA/05/25/11/CP/MTL | Hunukete sita Elagala dakwa Pradana Margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 108683600.82 | 82470143.89 | Awarded | 50% | 2025-11-12 | 2026-03-26
RR/RDA/05/25/12/CP/MTL | A9 pare Kist biscuit factoryata meha sithuwam kanda board eka (savikara athi) Nalanda wattata yana para | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Senevirathna Enterprise |  | 14006802.35 | 10340000 | Awarded | 100% | 2025-09-26 | 2026-01-05
RR/RDA/05/25/13/CP/MTL | A9 pare Elik Aluvihare niwasa lagin arambha wee Hunugalwala dakwa margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 27383521.12 | 19486197.5 | Awarded | 100% | 2025-09-26 | 2026-01-08
RR/RDA/05/25/16/CP/MTL | Dangan pedesa Mithragama margya Kurunegala margaye sita Mithragama | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 33031745.33 | 23856545.35 | Awarded | 100% | 2025-09-26 | 2026-01-08
RR/RDA/05/25/17/CP/MTL | Ambagastenna to gurubebila temple via Polwaththa nikawella | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 73216443.75 | 56391365.63 | Awarded | 100% | 2025-11-12 | 2026-03-25
RR/RDA/05/25/18/CP/MTL | Bandarapola Ulpathapitiya haraha Kiula margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 34151478.52 | 26720870 | Awarded | 100% | 2025-09-26 | 2026-01-07
RR/RDA/05/25/19/CP/MTL | Katudeniya bahukarya godanagilla asala Hettiyawatta dakwa margaya | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 17556901.6 | 13129506.5 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/05/25/20/CP/MTL | Harispattuwa margaya arambaka mansandiye sita Thusitha maranadara godanagilla dakwa | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 21943997.74 | 15584937.5 | Awarded | 100% | 2025-09-26 | 2026-01-07
RR/RDA/05/25/22/CP/MTL | Sigirimulla sita Mailetthewa Aluthyaya dakwa margaya | Central Province | Matale | Central Province | Matale | Nalanda | Tender Below 50Mn | Tender | Rural Road | Asiri Contractor and Designers |  | 48133410.98 | 33057264.9 | Awarded | 100% | 2025-09-26 | 2026-01-23
RR/RDA/05/25/24/CP/MTL | Pahala Hombawa palama dakwa Daduwagolla kanaththa langa sita | Central Province | Matale | Central Province | Matale | Nalanda | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 49816825.04 | 35817952.5 | Awarded | 100% | 2025-09-25 | 2026-01-23
RR/RDA/05/25/26/CP/MTL | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Central Province | Matale | Central Province | Matale | Nalanda | Tender Below 50Mn | Tender | Rural Road | Jayaru Engineering (Pvt) Ltd |  | 30575367.23 | 18760083.54 | Awarded | 60% | 2025-09-16 | 2025-12-31
RR/RDA/05/25/27/CP/MTL | Welemulla sita Kandewaththa | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 32539052.69 | 23207525 | Awarded | 100% | 2025-09-26 | 2026-01-09
RR/RDA/05/25/29/CP/MTL | Pitawala handiye sita pitawala desata | Central Province | Matale | Central Province | Matale | Matale | Tender Below 50Mn | Tender | Rural Road | Lahiru Construction & Consultants (PVT) Ltd |  | 38781690.92 | 37136372.9 | Awarded | 100% | 2025-09-26 | 2026-01-23
RR/RDA/05/25/30/CP/MTL | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Central Province | Matale | Central Province | Matale | Nalanda | Tender Above 50Mn | Tender | Rural Road | Lahiru Construction & Consultants (PVT) Ltd |  | 77270301.29 | 59540000 | Awarded | 60% | 2026-02-23 | 2026-08-10
| From Matalapitiya road through Idamgama village to Aluthwattha village to Kurunegala main road | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road |  |  | 62213974.01 |  | Pending | 0%
| From the last tarred point in Ussattauwa to the three-way junction near the Wemadilla Tank Church | Central Province | Matale | Central Province | Matale | Nalanda | Not Specified | Tender | Rural Road |  |  | 85667338.13 |  | Pending | 0%
| The road from Maraka Hospital Junction to Gangaya T-junction | Central Province | Matale | Central Province | Matale | Nalanda | Not Specified | Tender | Rural Road |  |  | 123618878.51 |  | Pending | 0%
| The road from near the Pradeshiya Sabha to Rattota town | Central Province | Matale | Central Province | Matale | Matale | Tender Above 50Mn | Tender | Rural Road |  |  | 59738937.37 |  | Pending | 0%
RR/RDA/06/25/32/CP/NE | Nanuoya Glaso pahala kotasa Margaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Tender Below 50Mn | Tender | Rural Road | wiscon (pvt) ltd |  | 43085721.61 | 38841280.5 | Awarded | 5% | 2026-02-06 | 2026-05-20
RR/RDA/06/25/34/CP/NE | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Above 50Mn | Tender | Rural Road | NAGMA ENGINEERING (PVT) LTD |  | 84599211.7 | 54639783.83 | Awarded | 0% | 2025-11-19 | 2026-05-06
RR/RDA/06/25/37/CP/NE | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Below 50Mn | Tender | Rural Road | Ajith Construction |  | 31658635.8 | 28282100 | Awarded | 100% | 2025-09-26 | 2026-01-23
RR/RDA/06/25/38/CP/NE | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Above 50Mn | Tender | Rural Road | NAGMA ENGINEERING (PVT) LTD |  | 54713411.13 | 38465634.79 | Awarded | 0% | 2025-11-19 | 2026-05-06
RR/RDA/06/25/40/CP/NE | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Below 50Mn | Tender | Rural Road | UGD Constructions |  | 35044851.53 | 31672222.12 | Awarded | 10% | 2025-09-26 | 2026-01-09
RR/RDA/06/25/41/CP/NE | Nayapana Gammada tharapara sanwardhanaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | Tender Above 50Mn | Tender | Rural Road | Central Engineering Services Pvt Ltd. (CESL) |  | 64794731.2 | 51754603.52 | Awarded | 35% | 2026-01-14 | 2026-07-29
RR/RDA/06/25/42/CP/NE | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Above 50Mn | Tender | Rural Road | UKS Lanka Engineering Pvt Ltd. |  | 276005265.17 | 220116957.84 | Awarded | 50% | 2025-11-07 | 2026-08-22
| Carpeting of road from Bambaragama Moragollahinna to Karamidula | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Above 50Mn | Tender | Rural Road | Ajith Construction |  | 68311664.39 | 61551869.38 | Awarded | 10% | 2026-02-06 | 2026-06-05
| Carpeting of Mahathenna to Hapugasdeniya Main Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Above 50Mn | Tender | Rural Road | Ajith Construction |  | 79957655.08 | 68070000 | Awarded | 73% | 2026-02-19 | 2026-06-05
| Development of Waralgala Road from near 09 acre kovil | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Below 50Mn | Tender | Rural Road |  |  | 22542053.72 |  | Pending | 0%
| Development of Wahalawela Agricultural Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Below 50Mn | Tender | Rural Road |  |  | 27342983 |  | Pending | 0%
| Carpeting and development of Liyanwela Alama Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | Tender Below 50Mn | Tender | Rural Road |  |  | 10539406.39 |  | Pending | 0%
| Pitawala Junction to Yahinda Colony Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Above 50Mn | Tender | Rural Road |  |  | 134169507.68 |  | Pending | 0%
| Castleree Junction to Castleree Estate Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Above 50Mn | Tender | Rural Road |  |  | 89398720.97 |  | Pending | 0%
| Kotagala Yetanside Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Above 50Mn | Tender | Rural Road |  |  | 76535492.86 |  | Pending | 0%
| Road from Kahahena Junction to Thispane | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | Tender Above 50Mn | Tender | Rural Road |  |  | 60167046.87 |  | Pending | 0%
RR/RDA/16/25/04/AKK/AMP | Pokunugama near Mr. Dinesh Tharaga House to Road (From Pokunugama Pre School to up to Mr. Dinesh Tharaga House) | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | Tender Below 50Mn | Tender | Rural Road | Harischandra Idikirim |  | 10039653.26 | 6435000 | Awarded | 100% | 2025-09-26 | 2025-12-10
RR/RDA/16/25/01/AKK/AMP | Samanalathenna- Road from House No.63 To the Monastery Muwagammana -From First Lane to Cemetry | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | Vithu Construction |  | 36719169.87 | 21336681.87 | Awarded | 100% | 2025-09-26 | 2025-12-24
RR/RDA/16/25/03/AKK/AMP | Polbedda Junction to Galwalayaya Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | MOTEC Engineering & Construction |  | 24800970.39 | 17506335 | Awarded | 52% | 2025-11-27 | 2026-03-10
RR/RDA/SP/16/25/01/AKK/AMP | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | Tender Above 50Mn | Tender | Rural Road | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd |  | 306475548.92 | 222189859.13 | Awarded | 34% | 2025-12-18 | 2026-06-30
RR/RDA/STA II/16/25/02/AKK/AMP | Concreting entrance road with culvert at Dehiaththakandiya Kelegama | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | Vithu Construction |  | 47778623.73 | 30737790.6 | Awarded | 100% | 2025-12-03 | 2026-03-16
RR/RDA/STA II/16/25/03/AKK/AMP | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Above 50Mn | Tender | Rural Road | Vithu Construction |  | 60426139.14 | 39470000 | Awarded | 65% | 2026-02-06 | 2026-05-26
RR/RDA/STA II/16/25/04/AKK/AKK | Lahugala Hulannuge Roundabout road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | Tender Below 50Mn | Tender | Rural Road | Zaka Engineering Consultancy |  | 36508598.9 | 26597958.2 | Awarded | 100% | 2025-12-03 | 2026-03-16
RR/RDA/16/25/10KM/01/AKK/AMP | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | Sawsiri Construction |  | 34027781.43 | 24113338.37 | Awarded | 17% | 2026-02-23 | 2026-05-26
RR/RDA/16/25/10KM/02/AKK/AMP | Road from Nelum Cafe Junction to Neeththa | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | Tender Below 50Mn | Tender | Rural Road | Gama Construction & Consultant pvt Ltd |  | 29760217.62 | 19318560.1 | Awarded | 20% | 2026-02-23 | 2026-06-05
RR/RDA/16/25/10KM/03/AKK/AMP | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | Sawsiri Construction |  | 32963348.47 | 21202726.44 | Awarded | 55% | 2026-02-23 | 2026-05-25
RR/RDA/16/25/10KM/04/AKK/AMP | Vevinna Boogas Junction Inner Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | Tender Below 50Mn | Tender | Rural Road | Gama Construction & Consultant pvt Ltd |  | 14460000 | 9692957.45 | Awarded | 15% | 2026-02-23 | 2026-05-08
RR/RDA/16/25/10KM/05/AKK/AMP | Road from Dorapaha Junction to Navagiriya Lake | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | Tender Below 50Mn | Tender | Rural Road | Ema Constructions (Pvt) Ltd |  | 28554939.58 | 18058942 | Awarded | 10% | 2026-02-23 | 2026-06-07
RR/RDA/16/25/10KM/06/AKK/AKK | Hulannuge School Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | Tender Below 50Mn | Tender | Rural Road | Gama Construction & Consultant pvt Ltd |  | 17414587.68 | 11406166.73 | Awarded | 100% | 2026-02-23 | 2026-04-27
RR/RDA/16/25/10KM/07/AKK/AMP | Bedirakka Malgastalawa Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | Tender Below 50Mn | Tender | Rural Road | Pearl Construction |  | 28483156.49 | 16362791.5 | Awarded | 0% | 2026-02-23 | 2026-05-15
RR/RDA/16/25/10KM/08/AKK/AKK | RDS Road Addalachena 6, 8 | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | Tender Below 50Mn | Tender | Rural Road | MLH & sons Construction |  | 29731841.59 | 18326682.5 | Awarded | 0% | 2026-02-23 | 2026-05-27
RR/RDA/16/25/10KM/09/AKK/AKK | Road behind Necode Institute (Navatkadu Akkarapattu) | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | Tender Below 50Mn | Tender | Rural Road | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd |  | 24614649.47 | 15228903.25 | Awarded | 100% | 2026-02-23 | 2026-04-29
RR/RDA/16/25/10KM/11/AKK/AKK | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | Tender Below 50Mn | Tender | Rural Road | Zaka Engineering Consultancy |  | 32835450.73 | 20596083.2 | Awarded | 10% | 2026-02-23 | 2026-06-06
RR/RDA/16/25/10KM/13/AKK/AKK | Jaica - Tsunami Village Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | Tender Below 50Mn | Tender | Rural Road | Gama Construction & Consultant pvt Ltd |  | 39951889.78 | 26167747.32 | Awarded | 70% | 2026-02-23 | 2026-06-13
RR/RDA/16/25/10KM/14/AKK/AKK | Bolivalian 5th Cross Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | Tender Below 50Mn | Tender | Rural Road |  |  | 36532125.31 |  | Pending | 0%
RR/RDA/15/25/01/EP/BTC | Concreting to Vipulananthar road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | SSK Construction |  | 44424075.79 | 29074090.89 | Awarded | 100% | 2025-10-22 | 2026-02-04
RR/RDA/15/25/02/EP/BTC | Concreting to Samurthi 1st Cross road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Kumaran Construction and Civil Works |  | 42354466.51 | 22158474.12 | Awarded | 20% | 2025-10-24 | 2025-02-06
RR/RDA/15/25/15/EP/BTC | Concrete to the Majma Nagar Mullivattuvan at paper town 210B | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | KMC Construction |  | 44093282.42 | 25270404.71 | Awarded | 80% | 2025-10-24 | 2026-02-06
RR/RDA/15/25/04/EP/BTC | Concreting to Maruthanagar Cemetery Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 62899992.75 |  | Rebid | 0%
RR/RDA/15/25/05/EP/BTC | Concreting to Mailanthanai Sri Muththumariyamman Main Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Kumaran Construction and Civil Works |  | 44365292.45 | 23225083.2 | Awarded | 50% | 2025-10-24 | 2026-02-06
RR/RDA/15/25/07/EP/BTC | Concreting to Thakwa masjith Cross Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Nazeeha Hardware and Construction |  | 36804461.32 | 22206567.3 | Awarded | 100% | 2025-11-07 | 2026-02-20
RR/RDA/15/25/09/EP/BTC | Concreting to NHDA Housing Scheme Internal Road 1st 2nd Cross | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | DKJ Construction |  | 16362900.23 | 7972333.63 | Awarded | 40% | 2025-10-24 | 2026-02-06
RR/RDA/15/25/11/EP/BTC | Concreting to Kali Kovil Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Jeezan Trading and Transport |  | 27925821.51 | 14105564 | Awarded | 5% | 2025-10-24 | 2026-02-06
RR/RDA/15/25/12/EP/BTC | Concreting to Muthalaikuda to Munnaikkadu Boundary Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Kumaran Construction and Civil Works |  | 47720744.3 | 26564874.51 | Awarded | 40% | 2025-11-07 | 2026-02-20
RR/RDA/15/25/13/EP/BTC | Concreting to Sangarpuram- Vilavadi | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Kumaran Construction and Civil Works |  | 46948339.52 | 24189660 | Awarded | 10% | 2025-11-07 | 2026-02-20
RR/RDA/15/25/14/EP/BTC | Concreting to Agriculture Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Jeezan Trading and Transport |  | 21690291.65 | 10593750 | Awarded | 60% | 2025-10-24 | 2026-02-06
RR/RDA/15/25/10KM/01/BTC | Sooriya farm Road sathurukondan | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Ganan Construction |  | 29978952.9 | 20565497.24 | Awarded | 50% | 2026-07-10 | 2026-10-23
RR/RDA/15/25/10KM/02/BTC | Iruthayapuram west 8th cross | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Sanju Civil Construction |  | 37780902.59 | 27156544.25 | Awarded | 30% | 2026-07-10 | 2026-10-23
RR/RDA/15/25/10KM/03/BTC | 8th mile post Thamotharam Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 121221913.9 |  | Pending | 0%
RR/RDA/15/25/10KM/04/BTC | Widening and asphalting to Veechukalmunai Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 61829043.98 |  | Pending | 0%
RR/RDA/15/25/10KM/05/BTC | Vivasaya Road, Mavadiyodai | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 50450979.87 |  | Pending | 0%
RR/RDA/15/25/10KM/06/BTC | Al Ameen Vidyaya Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Nathan's Construction |  | 48327996.29 | 32841084.21 | Awarded | 20% | 2026-07-27 | 2026-11-08
RR/RDA/15/25/10KM/07/BTC | Kanady cross Road to Magalingeshwarar kovil Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Motec Engineering & Construction |  | 36198556.07 | 25946118 | Awarded | 5% | 2026-07-21 | 2026-11-03
RR/RDA/15/25/10KM/08/BTC | Poosakar Road, Kannakipuram, Mahiloor | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Below 50Mn | Tender | Rural Road | Nathan's Construction |  | 40745256.81 | 27673151 | Awarded | 95% | 2026-07-10 | 2026-10-23
RR/RDA/15/25/10KM/09/BTC | Kokuvil 1st cross Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 79113347.52 |  | Pending | 0%
RR/RDA/15/25/10KM/10/BTC | Thiraimadu H Zone Cross Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | Tender Above 50Mn | Tender | Rural Road |  |  | 98159612.95 |  | Pending | 0%
RR/RDA/17/25/01/EP/TRN | Pillayar Road Renovation | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Rina Construction |  | 30058596.03 | 23425921.56 | Awarded | 100% | 2025-10-22 | 2026-02-04
RR/RDA/17/25/02/EP/TRN | Kathirkamathambi Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Fareed |  | 38871590.79 | 28809738 | Awarded | 100% | 2025-10-22 | 2026-02-04
RR/RDA/17/25/03/EP/TRN | Hospital Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Pragash Construction |  | 23553502.5 | 18557253.77 | Awarded | 100% | 2025-10-22 | 2026-02-04
RR/RDA/17/25/05/EP/TRN | Improvement to Jeyanthiwewa to Track 12 Main Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road | Nirupama Construction |  | 160000893.78 | 103260000 | Awarded | 65% | 2026-02-26 | 2027-03-11
RR/RDA/17/25/06/EP/TRN | Malporuwa to Thalgaswewa | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road | Jeezan Trading and Transport |  | 163676063.08 | 109630000 | Awarded | 7% | 2026-02-26 | 2027-03-11
RR/RDA/17/25/07/EP/TRN | Kanthamalawa Main Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | SSK Construction |  | 17579515.67 | 9161570 | Awarded | 100% | 2026-04-09 | 2026-07-23
RR/RDA/17/25/09/EP/TRN | School-Galmetiyawa Main Internal Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road | Zaka Engineering Consultancy |  | 77200000 | 53122107.5 | Awarded | 50% | 2026-05-08 | 2026-08-21
RR/RDA/17/25/10/EP/TRN | From Medagama temple to Peramaduwa | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Soyuru Sampath Construction & Suppliers |  | 31162876.79 | 24197635 | Awarded | 100% | 2025-11-07 | 2026-02-20
RR/RDA/17/25/11/EP/TRN | Development of Road from near the Fair | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | MS Construction |  | 37892493.36 | 25280343.6 | Awarded | 15% | 2026-05-21 | 2026-09-03
RR/RDA/17/25/12/EP/TRN | Improvement of RDS Road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | MTA Construction |  | 38673984.79 | 30166053 | Awarded | 100% | 2025-10-22 | 2026-02-03
RR/RDA/17/25/13/EP/TRN | Concreting from School junction to Boovidya Office | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Hana Construction (Pvt) Ltd. |  | 49104899.44 | 38264100 | Awarded | 100% | 2025-11-07 | 2026-02-19
RR/RDA/17/25/14/EP/TRN | Amaithusha Road (School road to Vaithiyar road) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Shaniff Construction |  | 6650570.02 | 5006100 | Awarded | 100% | 2025-11-07 | 2026-02-19
RR/RDA/17/25/15/EP/TRN | Cemetery Road (Sajahan Mowlavi's house to Thajudeen shop) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Soyuru Sampath Construction & Suppliers |  | 27637562.79 | 21774456 | Awarded | 100% | 2025-10-22 | 2026-02-04
RR/RDA/17/25/16/EP/TRN | Valuvar Road (Main road to Kovil road) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Shaniff Construction |  | 13997601.51 | 10783850 | Awarded | 100% | 2025-11-18 | 2026-03-02
RR/RDA/17/25/18/EP/TRN | Sooranagar Main Road (Muththuchenai Junction to Thuvaraka Vithiyalayam)-Concrete | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | SSK Construction |  | 38483392.5 | 25155240 | Awarded | 100% | 2026-05-19 | 2026-09-01
RR/RDA/17/25/19/EP/TRN | Periya Suwami Kovil Road-Concrete | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Motec Engineering & Construction |  | 39914113.43 | 25774146 | Awarded | 20% | 2026-05-21 | 2026-09-03
RR/RDA/SP/17/25/01/EP/TRN | Alankerny faisal Main Road (Koof Nagar) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | NAS Construction |  | 35125795.85 | 26879843.97 | Awarded | 100% | 2025-11-18 | 2026-03-02
RR/RDA/SP/17/25/02/EP/TRN | Annal nagar cross Road (Madena Nagar) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road |  |  | 85556800.53 |  | Rebid | 0%
RR/RDA/SP/17/25/03/EP/TRN | Hajra Road (Alhira Jalaira Road) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road | STAAR Construction |  | 51948669.36 | 38692742 | Awarded | 40% | 2026-05-08 | 2026-08-21
RR/RDA/STAII/17/25/01/EP/TRN | Dondrai main road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road |  |  | 25470558.11 |  | Pending | 25%
RR/RDA/STAII/17/25/02/EP/TRN | Wickrama Village Road from No:459 near the house to UK Dadu house | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road |  |  | 12045481.09 |  | Pending | 10%
RR/RDA/STAII/17/25/03/EP/TRN | From No.908 house to No.904 house road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Soyuru Sampath Construction & Suppliers |  | 14487311.88 | 10476638.8 | Awarded | 15% | 2026-07-24 | 2026-11-05
RR/RDA/STAII/17/25/04/EP/TRN | From No.851 house to Rajaela road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | ARN Engineering & Construction |  | 13792738.83 | 10452104.5 | Awarded | 15% | 2026-07-24 | 2026-11-05
RR/RDA/17/25/10KM/01/EP/TRN | Road behind th hospital up to the morgue junction | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Soyuru Sampath Construction & Suppliers |  | 15950150.82 | 13214817 | Awarded | 10% | 2026-07-27 | 2026-11-08
RR/RDA/17/25/10KM/02/EP/TRN | LB cannel bridge to pachchimarama temple | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Rina Construction |  | 19678704.72 | 16850648.32 | Awarded | 5% | 2026-07-27 | 2026-11-08
RR/RDA/17/25/10KM/03/EP/TRN | Ethabendiwewa Second Lane | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Nathan's Construction |  | 46705794.64 | 38931574 | Awarded | 90% | 2026-07-24 | 2026-11-05
RR/RDA/17/25/10KM/04/EP/TRN | Kajuwaththa gama meda road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | NMST Construction |  | 29466015.3 | 22770000 | Awarded | 5% | 2026-07-16 | 2026-10-29
RR/RDA/17/25/10KM/05/EP/TRN | 31-H Kawanthissapura main road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road |  |  | 103675299.1 |  | Pending | 0%
RR/RDA/17/25/10KM/06/EP/TRN | Budu pilima and 4th lane road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | RS Construction |  | 28351870.49 | 17520285.64 | Awarded | 15% | 2026-07-16 | 2026-10-29
RR/RDA/17/25/10KM/07/EP/TRN | Kawanthissa mawatha and in front of the cementerv road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Rina Construction |  | 20683158.47 | 15075988.4 | Awarded | 20% | 2026-07-27 | 2026-11-08
RR/RDA/17/25/10KM/08/EP/TRN | Paththini Amman Kevil road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | Alpha Engineering Services & Suppliers |  | 46089014.73 | 30365709 | Awarded | 25% | 2026-07-21 | 2026-11-03
RR/RDA/17/25/10KM/09/EP/TRN | Bazar mosque road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Below 50Mn | Tender | Rural Road | MTA Construction |  | 44293054.87 | 32616074.7 | Awarded | 40% | 2026-07-21 | 2026-11-03
RR/RDA/17/25/10KM/10/EP/TRN | Kuttikkarachchi Bridge to Al bud I street junction | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road |  |  | 55735826.03 |  | Pending | 0%
RR/RDA/17/25/10KM/11/EP/TRN | Pudavaikkattu Jumma Masjith near road | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | Tender Above 50Mn | Tender | Rural Road |  |  | 90714544.96 |  | Pending | 0%
RR/RDA/20/25/01/NCP/ANP | Road from Thambuttegama - Nochchiyagama road to the road near the DIG's office of Thambuthegama Rajanganaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Above 50Mn | Tender | Rural Road | Creates Consultant and Construction |  | 147079527.92 | 96940000 | Awarded | 30% | 2026-02-19 | 2026-09-03
RR/RDA/20/25/03/NCP/ANP | Thalawa - Eppawala margaye kele Amunukola handiyen aramba vee kele amunukola viddiyalayen divena margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 41286372.1 | 26155768.37 | Awarded | 40% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/04/NCP/ANP | A - 9 maragayen aramba vee wale kade dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 43911304.25 | 27008370.51 | Awarded | 45% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/05/NCP/ANP | Meda oyamaduwa handiye sita ehetuwawa dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Above 50Mn | Tender | Rural Road | D.M.C. CONSTRUCTION (PVT) LTD |  | 56374105.66 | 37593399.55 | Awarded | 100% | 2025-11-10 | 2026-02-23
RR/RDA/20/25/06/NCP/ANP | Ududumbara boogas handiye sita sarakkugala pasal handiya dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 44183866.35 | 26692661.01 | Awarded | 0% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/10/NCP/ANP | Manewe sita machchiyagama dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road | Sawsiri Construction |  | 39026908.38 | 31702147.54 | Awarded | 100% | 2025-10-14 | 2026-01-20
RR/RDA/20/25/11/NCP/ANP | Palayakulama sita halmillakulama dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 33233870.01 | 20887268.2 | Awarded | 75% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/12/NCP/ANP | Thalakolawewa carpert margaye awasanaye sita kudagama haraha dakunu ela iuwra margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | CS Construction |  | 49135056.85 | 37091276.8 | Awarded | 100% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/13/NCP/ANP | Maradankadawala Habarana pare kaudawa handiyen patangena rambewa gammanaya dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road | Sawsiri Construction |  | 26367721.95 | 21609366.35 | Awarded | 100% | 2025-10-14 | 2026-01-20
RR/RDA/20/25/14/NCP/ANP | Kukulewa pansala asalin arambavee samadhigama haraha seeppukulama rambewa maragaya dakwa divena pare pasala asala sita margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Kumari Konthrathkaruwo |  | 44635822.37 | 29296077 | Awarded | 100% | 2025-10-21 | 2026-01-27
RR/RDA/20/25/16/NCP/ANP | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 59684748.55 | 33000000 | Awarded | 80% | 2025-11-19 | 2026-03-04
RR/RDA/20/25/18/NCP/ANP | Pahala Talawa road of Thalawa Andarawewa road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | HPS Construction |  | 46999616.7 | 32443580.5 | Awarded | 80% | 2026-03-24 | 2026-06-30
RR/RDA/20/25/20/NCP/ANP | Development of the road from near the Siri Sambodhi Viharaya, 4th Mile post, on the Airport Roundabout Road to the house of Mr. Peme | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Above 50Mn | Tender | Rural Road | HPS Construction |  | 58718404.54 | 38820000 | Awarded | 70% | 2026-06-02 | 2026-12-15
RR/RDA/20/25/22/NCP/ANP | Development of the road starting from Mahamankadawala School and extending to Yalegama | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Above 50Mn | Tender | Rural Road | D.M.C. CONSTRUCTION (PVT) LTD |  | 66243138.27 | 2824695 | Awarded | 0% | 2026-08-31
RR/RDA/20/25/25/NCP/ANP | Development of road from Vihara Palugama Junction towards Medavachchiya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Above 50Mn | Tender | Rural Road |  |  | 59689954.3 |  | Pending | 0%
RR/RDA/20/25/26/NCP/ANP | Development of IV lane from Nuwara Road to Mihinthalaya Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 38283840.94 | 29650453.29 | Awarded | 6% | 2026-07-27 | 2026-11-02
RR/RDA/20/25/27/NCP/ANP | Development of the road from Mr. Nishanka's tire shop junction to Nambakada school on the entrance road of Nambakada village. | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Above 50Mn | Tender | Rural Road |  |  | 59567890.65 |  | Rebid | 0%
RR/RDA/20/25/28/NCP/ANP | Development of Rathnayake Mawatha | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 30142796.86 | 23041750.8 | Awarded | 5% | 2026-07-27 | 2026-02-11
RR/RDA/20/25/29/NCP/ANP | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 32982943.17 | 27986392.06 | Awarded | 0% | 2026-07-27 | 2026-11-02
| Development of the road starting from Padaviya Kabithigollewa Road to Buddhangala Temple | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | NMST Contractor |  | 36058233.51 | 29529900.12 | Awarded | 20% | 2026-06-18
| Development of road from Sripura main road to 38 Kolaniya Cemetery | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | NMST Contractor |  | 33546861.12 | 27971333.13 | Awarded | 2% | 2026-07-16 | 2026-10-22
| Development of road from Wahalkada D6 to Thalapakattialam on Punchimudagama road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 40137233.68 | 33242915.64 | Awarded | 5% | 2026-07-27 | 2026-11-02
| Development of first phase of road from Punewa to Warakwewa | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | RSW Engineering |  | 34843454.4 | 29762232.5 | Awarded | 25% | 2026-07-15 | 2026-10-21
| Development of the road from Punewa Junction to Kudahalmillewa Lake | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 33620055.04 | 28506545 | Awarded | 25% | 2026-07-27 | 2026-11-02
| Development of the road from near Ikirigollawa Muslim Maha Vidyalaya to Ratmalgahawewa main road from near Ikirigollawa dam to Ratmalgahawa road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | WGL Holdings |  | 14249058.84 | 10767548 | Awarded | 30% | 2026-07-27 | 2026-11-02
| Development of road from Kadawata Lake junction to village end | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| From Makicchawa Junction to Temple (to Kulumiwakada Junction) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road | Priyantha Civil Engineering |  | 37056005 | 29006146.8 | Awarded | 35% | 2026-07-27 | 2026-11-02
| Development of the road from near Mr. Nasurdeen's house in Thimbiriyathalawatta to Muslim Mawatha Wewa Mr. Arfan's house | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Above 50Mn | Tender | Rural Road |  |  | 58844572.42 |  | Pending | 0%
| Development of Rathmulwetia Road from Huruluwewa South Canal via Kumbukwewa | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Above 50Mn | Tender | Rural Road |  |  | 122442620.21 |  | Pending | 0%
| Paddy Depot Road near Padaviya Divisional Secretariat to the entrance road to the archaeological reserve. | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Below 50Mn | Tender | Rural Road | Pathiraja Construction |  | 40024610.35 | 37594579 | Awarded | 0% | 2026-10-14
| Thakshilawa Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Below 50Mn | Tender | Rural Road |  |  | 24209080.01 |  | Pending | 0%
| road from near Mekichchawa Temple to Gammehegewewa. | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Below 50Mn | Tender | Rural Road | Kumari Konthrathkaruwo |  | 41217426.95 | 39727992.71 | Awarded | 0% | 2026-10-14
| Ulpataha road from Yakkala Junction. | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Tender Above 50Mn | Tender | Rural Road |  |  | 150479783 |  | Pending | 0%
| Road from near Nugagasa to the house of Mr. Wickramapala, where the village of Kahatagasdigiliya begins. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | Tender Below 50Mn | Tender | Rural Road |  |  | 9080364.52 |  | Pending | 0%
| the road from Vijaya Mawatha to Chulani Mawatha near the Teacher's House. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 30277077.11 |  | Pending | 0%
| Thanthirimalai Thanthirimalaya Road near Thanthirimala Hospital and thence to Medawachchiya Eliya Road. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 31550201.54 |  | Pending | 0%
| Entrance road of Eppawala Shariah Rahula Primary School starting from Thalawa Kekirawa main road. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 12525362.34 |  | Pending | 0%
| the road starting from near Sathosa in front of the Economic Centre to the Galnewa road through Thammannapura village. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 22072714.2 |  | Pending | 0%
| Road from the house of Mr. L.P. Chandrasiri to the house of Mr. Herathbanda. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 21826450.74 |  | Pending | 0%
| Road from Malbaligala Junction to Sirimagama Grama Niladhari Office. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road |  |  | 24052451.48 |  | Pending | 0%
| Road from the Yogoda Ela Bridge to Mrs. Renuka's house in the middle of Pugollagama village. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road |  |  | 43634696.07 |  | Pending | 0%
| Maradankulam Weerakele Temple Road. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road | Lisal Construction |  | 37321017.6 | 34408719.4 | Awarded | 0% | 2026-10-14
| Pairimaduwa School Road. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Above 50Mn | Tender | Rural Road |  |  | 51256089.38 |  | Pending | 0%
| Udugama Colony Rural Road from near A9 road to in front of Mr. Somarathna Senaratne's house | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road |  |  | 43084597.45 |  | Pending | 0%
| Forward section of the Samagi Avenue from the place where the Interlock pavingl is currently held and stopped with culverts. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Below 50Mn | Tender | Rural Road |  |  | 37407985.98 |  | Pending | 0%
| Habaraththawala Rural Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | Tender Above 50Mn | Tender | Rural Road |  |  | 99235134.87 |  | Pending | 0%
| Remaining section from near the 260 Yodha Canal Bridge to the Mandagala Carpet Road. | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Tender Below 50Mn | Tender | Rural Road |  |  | 36265107.93 |  | Pending | 0%
| Second phase from Godage Mawatha, Priman Mawatha to Court Roundabout | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Udangawa rural road | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| The road from near Pandukabhaya Public Stadium to Mr. Tillakaratne's shop | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| The first lane leading to Devanam Piyathissapura village | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Development of the road running along the embankment of the carpet road from near the Ralapanawa Colony Textile Center | North Central Province | Anuradhapura | North Central Province | Anuradhapura |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/21/25/03/NCP/POL | Mahasenpura pradeepika kadaya asala sita Katukeliyawa dakwa margaya Carpart kireema | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | Tender Above 50Mn | Tender | Rural Road | Nadun Construction (Pvt) Ltd |  | 53473343.43 | 33480137.33 | Awarded | 80% | 2025-11-26 | 2026-03-11
RR/RDA/21/25/04/NCP/POL | 10th Canal Lake Road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Below 50Mn | Tender | Rural Road | Nadun Construction (Pvt) Ltd |  | 33113556.37 | 18877127 | Awarded | 100% | 2025-10-14 | 2026-01-20
RR/RDA/21/25/06/NCP/POL | Rathmalyaya nila sewana sita thalakolawewa wasama Arambaya Dakwa Maragaya | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | Tender Above 50Mn | Tender | Rural Road |  |  | 95369443.81 |  | Rebid | 0%
RR/RDA/21/25/17/NCP/POL | Development of the road from Kaduruwela Muslim Kolaniya road to Pachcha Palliya | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Central Engineering Services Pvt Ltd. (CESL) |  | 75598504.72 | 53880000 | Awarded | 80% | 2026-05-11 | 2026-08-24
RR/RDA/21/25/17/NCP/POL | Development of 1 canal Road from Kadurwela Muslim Kolaniya Road to Parakum Mawatha | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Nadun Construction (Pvt) Ltd |  | 62351983.93 | 54640000 | Awarded | 45% | 2026-06-18 | 2026-10-01
| Development of the road from near the Pimburatthewa Mahaweli Resort to the Aralaganwila Maha Oya main road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Sawsiri Construction |  | 64012244.55 | 59570000 | Awarded | 7% | 2026-09-16 | 2026-12-30
| Development of the road from near the railway on the entrance road to the house of Mrs. 286 Latha in Boatta village | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Nathan's Construction |  | 84585495.48 | 73470000 | Awarded | 3% | 2026-09-01 | 2026-12-15
| Development of the road from the main road to near the Kadawala Wewa School | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Nadun Construction (Pvt) Ltd |  | 108995356.01 | 93990000 | Awarded | 5% | 2026-09-01 | 2026-12-15
| Development of the road from near the house at Pulastigama 156 to Sungawila 1 Canal Junction | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | Tender Above 50Mn | Tender | Rural Road | Nadun Construction (Pvt) Ltd |  | 78477567.56 | 67120000 | Awarded | 5% | 2026-09-01 | 2026-12-15
| Road from near the Wota Gedi Bridge to Dambalu Stores | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | Tender Above 50Mn | Tender | Rural Road | Nathan's Construction |  | 83988418 | 69810000 | Awarded | 3% | 2026-09-01 | 2026-12-15
RR/RDA/18/25/01/NWP/KRG | Development of Egodagama Talakolawewa road | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road | Sri Ram Constructions |  | 156184445.89 | 98323766.14 | Awarded | 60% | 2025-11-25 | 2026-05-06
RR/RDA/18/25/02/NWP/KRG | Road from Parakumpura to Yaya 04 | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Below 50Mn | Tender | Rural Road | Ingress Engineering |  | 24748740.38 | 20126522.24 | Awarded | 100% | 2025-09-15 | 2026-02-04
RR/RDA/18/25/04/NWP/KRG | The road from Hunugallewa road junction to Madadenigama Hunugallewa Mahamaruwa Beligahaya to Mee Oya bridge | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road | Shanho Enterprises Pvt Ltd. |  | 85865152.06 | 59066766.74 | Awarded | 40% | 2026-02-18 | 2026-06-09
RR/RDA/18/25/07/NWP/KRG | Road from Moragolla Junction to Nabadewa Girilla Carpet Road via Kirinda | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road | Jayasinghe Constructions (Pvt) Ltd. |  | 79393864.19 | 59247280.29 | Awarded | 75% | 2025-11-25 | 2026-05-12
RR/RDA/18/25/08/NWP/KRG | Paving of road from Nammuawa to Nagansole temple | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Below 50Mn | Tender | Rural Road | Omega Construction (Pvt) Ltd |  | 49176148.86 | 33899382 | Awarded | 100% | 2025-09-20 | 2026-03-07
RR/RDA/18/25/09/NWP/KRG | Paving the road from Pahala Galapitiyagama to Tharanagolla Sports Ground | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 81982091.15 | 70405428.6 | Awarded | 0% | 2025-11-19 | 2026-03-03
RR/RDA/18/25/11/NWP/KRG | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Above 50Mn | Tender | Rural Road | Shanho Enterprises Pvt Ltd. |  | 64750199.52 | 46193949.68 | Awarded | 65% | 2026-02-18 | 2026-07-01
RR/RDA/18/25/16/NWP/KRG | Development of concrete road from near Wadawa temple to the lake | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Below 50Mn | Tender | Rural Road | Jayawardana Constructions (Pvt) Ltd. |  | 31595236.77 | 25583393 | Awarded | 100% | 2025-09-02 | 2025-12-15
RR/RDA/18/25/22/NWP/KRG | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Above 50Mn | Tender | Rural Road | Jayasinghe Constructions (Pvt) Ltd. |  | 77881819.09 | 67074479.55 | Awarded | 65% | 2025-11-20 | 2026-06-04
RR/RDA/18/25/24/NWP/KRG | Paving and developing the road from Seelarathana Mawatha to Girana Junction | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 57963603.67 | 37201129.8 | Awarded | 100% | 2025-11-20 | 2026-03-05
RR/RDA/18/25/104/NWP/KRG | Pinnagolla Junction to Kokowaththa Junction VIA Alakolapelessa | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 30550483.75 | 24010872.6 | Awarded | 100% | 2025-09-09 | 2025-12-20
RR/RDA/18/25/106/NWP/KRG | Thagahinna Temple Road | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road | Jayawansa Construction (PVT) Ltd |  | 16225030.21 | 13370813.5 | Awarded | 100% | 2025-09-02 | 2026-03-09
RR/RDA/18/25/NWP/KRG/10 | Uyandana Yaggapitiya | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Above 50Mn | Tender | Rural Road | Senerath Engineering (pvt) Ltd |  | 71428674.02 | 45801928.2 | Awarded | 100% | 2025-11-20 | 2026-03-03
RR/RDA/18/25/135/NWP/KRG | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Above 50Mn | Tender | Rural Road | Jayasinghe Contractors (Pvt) Ltd. |  | 55779764.12 | 41750386.7 | Awarded | 20% | 2026-02-06 | 2026-05-20
RR/RDA/18/25/136/NWP/KRG | Ranasinghe Hotel Asalin Koralaya Waththe sita Panwala Kubura Dakwa Diwena Margaya Kapat Kirima | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Below 50Mn | Tender | Rural Road | Jayasinghe Contractors (Pvt) Ltd. |  | 22994794.21 | 21718130.5 | Awarded | 100% | 2025-12-24 | 2026-04-07
RR/RDA/18/25/137/NWP/KRG | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road | W P J Engineering(Pvt)Ltd |  | 23865719.81 | 18425029.46 | Awarded | 45% | 2025-12-23 | 2026-04-06
RR/RDA/18/25/138/NWP/KRG | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road | W P J Engineering(Pvt)Ltd |  | 39359193.23 | 30650394.06 | Awarded | 20% | 2025-12-24 | 2026-04-07
RR/RDA/18/25/139/NWP/KRG | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road | Jayawansa Construction (PVT) Ltd |  | 41102824.35 | 28112995.75 | Awarded | 90% | 2026-02-12 | 2026-05-18
| Road from Madigemidiyala to Polgewilla in Hidagahawewa Division of Palugaswewa Division Proceeding from Galkatuwa Wewa | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Above 50Mn | Tender | Rural Road |  |  | 66921107.93 |  | Rebid | 0%
| Ambawatta Road in Kasikota West Division of Kasikote Division Road from near Mr. Gunaratne's house to Peella Temple | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road |  |  | 63353822.77 |  | Pending | 0%
| Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | Tender Below 50Mn | Tender | Rural Road | Thushara roofing (pvt) ltd |  | 11985499.69 | 10696008.28 | Awarded | 65% | 2026-04-20 | 2026-08-02
| Completion of the remaining section of the road up to Rambadagalla Fisheries Centre in Rambadagalla Division | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Above 50Mn | Tender | Rural Road |  |  | 54075704.54 |  | Pending | 0%
| Road to Ebalayagama Primary Colledge from Thela hela Temple | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | Tender Above 50Mn | Tender | Rural Road |  |  | 57250161.07 |  | Pending | 0%
| Road to Meegasthenna through Dalupothegedara from Ambakote Cooperative shop | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | Tender Below 50Mn | Tender | Rural Road |  |  | 49336140.3 |  | Pending | 0%
| Udawela to Karambalana Road | North Western Province | Kurunegala | North Western Province | Kurunegala |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/19/25/01/NWP/PUT | Development of carpeting the Gammedda road up to Anathapara. | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Chandana Construction |  | 24961884.73 | 27734432.55 | Awarded | 65% | 2025-09-18 | 2025-12-20
RR/RDA/19/25/04/NWP/PUT | Carpeting of green light carpeted road from Bogus Junction (80 acres). | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Above 50Mn | Tender | Rural Road | Sri Ram Constructions |  | 59154724.51 | 34055720.05 | Awarded | 65% | 2025-11-25 | 2026-03-09
RR/RDA/19/25/05/NWP/PUT | Development of the road from near Mr. Chaminda's house to Boga Pathaha | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Above 50Mn | Tender | Rural Road | Sampath Contractors |  | 60367316.08 | 36592843.95 | Awarded | 65% | 2025-11-20 | 2026-03-04
RR/RDA/19/25/08/NWP/PUT | Carpeting of Velasia Main Road from Madurankuliya. | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Above 50Mn | Tender | Rural Road | Sri Ram Constructions |  | 61899364.5 | 39584083.5 | Awarded | 70% | 2025-11-20 | 2026-04-04
RR/RDA/19/25/26/NWP/PUT | Abayarama Mawatha Bomimakka Kovil Road to Sembandaluwa Temple Road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Sampath Construction |  | 42010632 | 26275458.07 | Awarded | 100% | 2025-10-22 | 2026-02-05
RR/RDA/19/25/27/NWP/PUT | The entrance to the Medical Officer's Office in the Galahitiyawa Grama Niladhari Division | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road | Omega Construction (Pvt) Ltd |  | 49714778.94 | 38495776 | Awarded | 60% | 2025-10-22 | 2026-02-03
RR/RDA/19/25/28/NWP/PUT | Samagi Mawatha | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Ranuja Construction |  | 36001594.79 | 25908850 | Awarded | 100% | 2026-01-01 | 2026-04-15
RR/RDA/19/25/29/NWP/PUT | Development of the road from Galkuliya Welameda to Mrs. Deepani's house | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Sampath Construction |  | 13481102.43 | 8675871.6 | Awarded | 100% | 2026-01-01 | 2026-04-15
RR/RDA/19/25/30/NWP/PUT | Development of carpeting from Mihirajthotupola to Serakkuliya 1 on the Serakkuliya main road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Omega Construction (Pvt) Ltd |  | 45465357.54 | 38494009.5 | Awarded | 70% | 2025-12-29 | 2026-04-12
RR/RDA/19/25/31/NWP/PUT | Development of carpeting from the point where carpeting has stopped on the Tammana main road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Sampath Construction |  | 39960885.9 | 26013841.83 | Awarded | 50% | 2026-01-29 | 2026-05-13
RR/RDA/19/25/32/NWP/PUT | Development of the Bammeyaya Road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Jayawardana Constructions (Pvt) Ltd. |  | 17431257.91 | 10904293.4 | Awarded | 50% | 2025-12-29 | 2026-05-12
RR/RDA/19/25/33/NWP/PUT | Development of the road from near the Sugatarama Temple, Periyakulam to Thalgaswewa | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Jayawardana Constructions (Pvt) Ltd. |  | 38370082.14 | 24440875.25 | Awarded | 45% | 2025-12-29 | 2026-04-12
RR/RDA/19/25/34/NWP/PUT | Carpeting & Development of Bodhirajapura 4th Lane | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road | Sampath Construction |  | 19966435.66 | 12568847.5 | Awarded | 70% | 2026-01-29 | 2026-05-12
RR/RDA/19/25/37/NWP/PUT | Lawyer Wijayananda's House Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road | Ponnamperuma Suppliers |  | 9913614.44 | 7763919.68 | Awarded | 70% | 2025-12-30 | 2026-04-14
RR/RDA/19/25/38/NWP/PUT | North Dummaladeniya Cross Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road | Ponnamperuma Suppliers |  | 11621041.2 | 10005001.78 | Awarded | 90% | 2025-12-31 | 2026-04-14
RR/RDA/19/25/39/NWP/PUT | Renovation of Khemananda Road | North Western Province | Puttalam | North Western Province | Chilaw |  | Tender Below 50Mn | Tender | Rural Road | SriLak Import and Export Company |  | 22000226.26 | 19114271.45 | Awarded | 95% | 2026-01-05 | 2026-04-19
| Development of the road from Madurankuliya to Velasiya College | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Above 50Mn | Tender | Rural Road | Sampath Construction |  | 90437412.35 | 55254878 | Awarded | 30% | 2026-02-06 | 2026-05-21
| Road renovation from near the Kivula Katuwa water tank to the Halmillewa junction | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road |  |  | 29985030 |  | Pending | 0%
| Reconstruction of the road on the Anamaduwa-Nawagatthegama road starting from the house of Mr. Karunaratne and extending from the three-way junction in Alankulama Farmer's Village to the shop of Mr. M. M. Wijaya Mannapperuma | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road |  |  | 28323565.38 |  | Pending | 0%
| Development of the road from Devala Mawatha to Vidyala Mawatha | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road |  |  | 27130752.27 |  | Pending | 0%
| Development of Fenando Road - Picchawala Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road | Dilini Builders (PVT) LTD |  | 27030199.65 | 26046308.34 | Awarded | 0% | 2026-05-06 | 2026-08-17
| Development of Anawasala Janasawipura Road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Above 50Mn | Tender | Rural Road |  |  | 54487343.44 |  | Pending | 0%
| Development of Rahumath Nagar First Lane | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road |  |  | 20067410.07 |  | Pending | 0%
| Development of Hijrathpuram Road | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | Tender Below 50Mn | Tender | Rural Road |  |  | 23198335 |  | Pending | 0%
| Development of Karukkuwa Madampe Village Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road |  |  | 14676180.91 |  | Pending | 0%
| Development of Ithigodawela Upper Olindaluwa Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road |  |  | 25208974.38 |  | Pending | 0%
| Development of Sinhapurawattha Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road |  |  | 21401802.02 |  | Pending | 0%
| Development of East Katukenda Mirissankoutuwa Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | Tender Below 50Mn | Tender | Rural Road |  |  | 27324370.66 |  | Pending | 0%
| Galkulama Junction to Kivula road | North Western Province | Puttalam | North Western Province | Chilaw |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Kohombagas Junction to Moonamalagaswewa Temple road | North Western Province | Puttalam | North Western Province | Chilaw |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Sirambiadiya Lunu linda road | North Western Province | Puttalam | North Western Province | Chilaw |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Saliyawewa Junction to Yaya 6 main road | North Western Province | Puttalam | North Western Province | Chilaw |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/10/25/01/NP/JFN | Maveli Periyathurai Road. 3.6509 | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 139756639.65 | 135900000 | Awarded | 20% | 2026-05-25
RR/RDA/10/25/02/NP/JFN | NHDA Housing internal Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road |  |  | 61511620.87 |  | Rebid | 0%
RR/RDA/10/25/03/NP/JFN | Navalar Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | KBS Engineering Solution |  | 16240094.76 | 7919722.64 | Awarded | 100% | 2025-10-31 | 2026-04-01
RR/RDA/10/25/04/NP/JFN | Aluminium Factory Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road | Majurathas Building Contractors |  | 56580112.16 | 36973948 | Awarded | 100% | 2025-11-19 | 2026-04-04
RR/RDA/10/25/05/NP/JFN | Renovation of Kokkuruniya Veethy | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | Majurathas Building Contractors |  | 34746312.4 | 22247557.75 | Awarded | 100% | 2025-10-24 | 2026-02-06
RR/RDA/10/25/06/NP/JFN | Renovation of West beach Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 91211155.29 | 83618425 | Awarded | 10% | 2025-12-22 | 2026-04-18
RR/RDA/10/25/07/NP/JFN | Paththarkerny Veethy | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road |  |  | 70639153.34 |  | Pending | 0%
RR/RDA/10/25/08/NP/JFN | Renovation of Ilanthaikulam Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | KBS Engineering Solution |  | 17821627.52 | 12089810.15 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/10/25/10/NP/JFN | Nayanmar Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | AVP Construction (Pvt) Ltd |  | 27107876.22 | 17917437.01 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/10/25/11/NP/JFN | Amman Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | Thaaru Construction |  | 19749993.06 | 14588981 | Awarded | 100% | 2025-11-20 | 2026-03-05
RR/RDA/10/25/13/NP/JFN | lnbacholai Road (Iththiyadi Muthali Kovilady - Inbacholai Road) | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | AVP Construction (Pvt) Ltd |  | 33467961.12 | 22527821.25 | Awarded | 100% | 2025-10-24 | 2026-05-12
RR/RDA/10/25/14/NP/JFN | Pankuru Veethy | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | Thaaru Construction |  | 47295898.62 | 32829728.8 | Awarded | 60% | 2025-11-20 | 2026-05-26
RR/RDA/10/25/15/NP/JFN | Kadavaippulam Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | KBS Engineering Solution |  | 12352166.19 | 7712452 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/10/25/16/NP/JFN | Kalai Makal Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Below 50Mn | Tender | Rural Road | Jana Civil Work Contractors and Material Suppliers |  | 25146295.8 | 17670712.18 | Awarded | 100% | 2025-10-24 | 2026-02-06
RR/RDA/10/25/18/NP/JFN | Atchuvely Industrial Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 101707442.89 | 72500000 | Awarded | 70% | 2025-12-12 | 2026-04-04
RR/RDA/10/25/20/NP/JFN | Thuvali Veethy | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | Tender Below 50Mn | Tender | Rural Road | Majurathas Building Contractors |  | 47624825.22 | 32948293.95 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/10/25/22/NP/JFN | Anaivilunthan Sudalai Road | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | Tender Above 50Mn | Tender | Rural Road | Yaso Engineering |  | 61126170.56 | 48082026.3 | Awarded | 65% | 2025-11-07 | 2026-04-03
RR/RDA/10/25/25/NP/JFN | Palaiya Vaikal Veeethy | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 79703717.02 | 54450000 | Awarded | 50% | 2025-12-12 | 2026-04-02
RR/RDA/12/25/01/NP/VVN | Thiruchchenthooran mill road NVSTE541 | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | TMC Constructions |  | 100688815.19 | 53290000 | Awarded | 0% | 2026-06-17 | 2026-09-29
RR/RDA/12/25/02/NP/VVN | Eswarypuram housing scheme internal road (NVSTE178) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 40810577.98 | 28833609.2 | Awarded | 100% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/03/NP/VVN | Puthiya manipuram, main road (NVSTE481) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yaso Engineering |  | 41435979.42 | 32481108 | Awarded | 35% | 2025-10-31 | 2026-02-13
RR/RDA/12/25/04/NP/VVN | Suntharapuram main road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 71964095.93 | 162703000 | Awarded | 35% | 2026-02-19 | 2026-06-03
RR/RDA/12/25/17/NP/VVN | Lyca village enterance Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 54064384.24 |  | Awarded | 35% | 2026-02-19 | 2026-06-03
RR/RDA/12/25/22/NP/VVN | Mannankerny road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 51515196.2 |  | Awarded | 50% | 2026-02-19 | 2026-06-03
RR/RDA/12/25/52/NP/VVN | Menanager Malakattu Kalkuwari Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 54861523.89 |  | Awarded | 65% | 2026-02-19 | 2026-06-03
RR/RDA/12/25/05/NP/VVN | Sinnakulam road – laxapana road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Arul Selvi Construction and Hardware |  | 21459717.36 | 16411999.99 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/12/25/07/NP/VVN | Tharanikulam main road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 30580213.01 | 20876280.7 | Awarded | 70% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/08/NP/VVN | Katkulam road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yansika Success Group (Pvt) Ltd |  | 22884956.34 | 18055415.95 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/12/25/10/NP/VVN | Achchipuram amman temble road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ancheneya Constructions |  | 28181354.24 | 19430799.3 | Awarded | 70% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/12/NP/VVN | Nanthimiththiragama 1st | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ancheneya Constructions |  | 30752460 | 24583111.3 | Awarded | 5% | 2025-10-31 | 2026-05-22
RR/RDA/12/25/13/NP/VVN | Nanthimiththiragama 2nd | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ancheneya Constructions |  | 31291948.01 | 24829841.3 | Awarded | 5% | 2025-10-17 | 2026-04-22
RR/RDA/12/25/14/NP/VVN | Nanthimiththiragama 4th | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ancheneya Constructions |  | 30939872.36 | 25113641.3 | Awarded | 5% | 2025-10-17 | 2026-04-22
RR/RDA/12/25/18/NP/VVN | Nedunkerny North sandankulam Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yaso Engineering |  | 46839314.91 | 32829160.1 | Awarded | 35% | 2025-10-31 | 2026-02-12
RR/RDA/12/25/19/NP/VVN | Senaipilavu Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yaso Engineering |  | 43285227.82 | 32576225 | Awarded | 70% | 2025-10-31 | 2026-02-12
RR/RDA/12/25/20/NP/VVN | Puthiyakudiyiruppu parasankulam road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Bapithan Construction |  | 34966229.53 | 23259239.3 | Awarded | 70% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/21/NP/VVN | Bagaswewa 01st 22nd lane | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Bapithan Construction |  | 33747516.65 | 22749983.3 | Awarded | 35% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/24/NP/VVN | Kanagarayankulam puthuvilankulam road (NVVNE073) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Bapithan Construction |  | 46468981.72 | 31165786.3 | Awarded | 70% | 2025-10-31 | 2026-02-13
RR/RDA/12/25/25/NP/VVN | 2nd cross Lane Ginigathhena | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 40686140.26 | 27770291 | Awarded | 70% | 2025-12-09 | 2026-02-21
RR/RDA/12/25/26/NP/VVN | Cemetery Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ranasinghe Construction |  | 23875168.24 | 17011533 | Awarded | 100% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/27/NP/VVN | From Acre 400 7th Lane to cross end of the 2nd internal road close to Andarawewa | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Ranasinghe Construction |  | 57948785.02 | 46360659.24 | Awarded | 30% | 2025-12-02 | 2026-03-03
RR/RDA/12/25/28/NP/VVN | From Janaudanagama 2nd internal road to end of the free school | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 37396800.47 | 26569012.25 | Awarded | 35% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/29/NP/VVN | Kalasiyambalawa Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 19583811.27 | 13504281.45 | Awarded | 50% | 2025-10-31 | 2026-02-13
RR/RDA/12/25/30/NP/VVN | Maradammaduwa Rural Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sevvel Construction & Suppliers |  | 33292513.97 | 25533435.95 | Awarded | 100% | 2025-12-17 | 2026-03-18
RR/RDA/12/25/31/NP/VVN | Mahakachchakodiya to Ettambagaskada | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Yansika Construction |  | 59974624.42 | 45254190.85 | Awarded | 30% | 2025-11-20 | 2026-01-20
RR/RDA/12/25/32/NP/VVN | Kalukummankaduwa to Alagalla Rural Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Yansika Construction |  | 61020259.1 | 36671440.85 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/12/25/33/NP/VVN | Mamaduwa Thiyawaragama Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | 5N Group Construction |  | 26687363.08 | 20811747 | Awarded | 100% | 2025-12-09 | 2026-02-21
RR/RDA/12/25/35/NP/VVN | Awusadapitiya Pubudugama Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 46347432.25 | 32504637.43 | Awarded | 70% | 2025-12-09 | 2026-02-21
RR/RDA/12/25/36/NP/VVN | Mamaduwa to Dikwewa | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 25629657.32 | 18006430.2 | Awarded | 100% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/37/NP/VVN | Parakumawatha | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Ranasinghe Construction |  | 34830175.61 | 26672047.6 | Awarded | 100% | 2025-10-10 | 2026-01-23
RR/RDA/12/25/38/NP/VVN | Salalinigama 11 lane | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 40853027.3 | 30830906.7 | Awarded | 50% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/39/NP/VVN | Madukanda lake side road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 31883174.61 | 22687590.2 | Awarded | 100% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/40/NP/VVN | Halabagaswewa | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 36283467.53 | 25032191.25 | Awarded | 5% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/41/NP/VVN | Arasadikulam - veerapuram road (2km) veerapuram 1st lane (NVVPE227) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | Omega Construction (Pvt) Ltd |  | 64674542.81 | 45800000 | Awarded | 0% | 2026-06-17
RR/RDA/12/25/42/NP/VVN | Veerapuram main road (veerapuram 2nd 3rd lane) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yaso Engineering |  | 25380543.51 | 19745000 | Awarded | 100% | 2025-10-24 | 2026-02-06
RR/RDA/12/25/43/NP/VVN | Pavatkulam tack 5 vaarikuttiyoor | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 25717072.9 | 17351705.25 | Awarded | 70% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/46/NP/VVN | Sinnasippikulam to neriyakulam road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 21276360.97 | 14561522.25 | Awarded | 100% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/48/NP/VVN | Mukaththankulam 7th lane (NVVPE173) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 28294497.45 | 18900081.2 | Awarded | 70% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/51/NP/VVN | Adappankulam aladi road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | North Construction (Pvt) Ltd |  | 19573472.29 | 13383862.25 | Awarded | 70% | 2025-12-09 | 2026-02-22
RR/RDA/12/25/53/NP/VVN | Ethawetunuwewa Temple Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Shiyamala Construction |  | 12174775.32 | 9515000 | Awarded | 100% | 2025-10-24 | 2026-02-05
RR/RDA/12/25/54/NP/VVN | Nikawewa Right Village Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yansika Construction |  | 22922029.4 | 17143053.95 | Awarded | 70% | 2025-10-24 | 2026-02-05
RR/RDA/12/25/55/NP/VVN | Mayawewa to Namalpura Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yansika Construction |  | 22825561.83 | 17639615.95 | Awarded | 100% | 2025-10-24 | 2026-02-05
RR/RDA/12/25/56/NP/VVN | From Nikawewa Post Office to Nikawewa Right Village | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yansika Construction |  | 23412051.37 | 17924713.95 | Awarded | 100% | 2025-10-24 | 2026-02-05
RR/RDA/12/25/57/NP/VVN | Nikawewa Right to Sapumalthanna | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Yansika Construction |  | 15184106.87 | 11848115.95 | Awarded | 100% | 2025-10-24 | 2026-02-05
RR/RDA/12/25/58/NP/VVN | Preschool Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | 5N Group Construction |  | 28313232.5 | 21518222 | Awarded | 100% | 2025-10-24 | 2026-02-08
RR/RDA/12/25/59/NP/VVN | Kalyanipura 2nd lane | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | 5N Group Construction |  | 37048858.38 | 28184992 | Awarded | 100% | 2025-10-31 | 2026-02-12
RR/RDA/12/25/60/NP/VVN | Salalinigama lane 12 | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 33827661.22 | 23397220 | Awarded | 15% | 2026-03-20 | 2026-07-03
RR/RDA/12/25/61/NP/VVN | Namalgama lane 20 | Northern Province | Vavuniya | Northern Province | Vavuniya |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/12/25/62/NP/VVN | Periyavilathikulam | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Omega Construction (Pvt) Ltd |  | 23338487.33 | 16916712.5 | Awarded | 35% | 2026-03-20 | 2026-07-03
RR/RDA/12/25/63/NP/VVN | 1st Cross Street Alakarai Road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Above 50Mn | Tender | Rural Road | North Construction |  | 55600429.77 | 38912500 | Awarded | 30% | 2026-02-06 | 2026-05-21
RR/RDA/12/25/64/NP/VVN | Nedunkulama | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | Tender Below 50Mn | Tender | Rural Road | Arul Selvi Construction and Hardware |  | 22278087.37 | 15902966.56 | Awarded | 70% | 2026-03-20 | 2026-07-03
RR/RDA/13/25/01/NP/MUL | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 188808095.02 | 145000000 | Awarded | 0% | 2025-11-18 | 2026-03-02
RR/RDA/13/25/03/NP/MUL | Navatkadu Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | TMC Constructions |  | 77969519 | 50363687 | Awarded | 60% | 2025-12-18 | 2026-04-01
RR/RDA/13/25/06/NP/MUL | Pandaravanniyan Silaiyadi Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 113438730.78 | 83700000 | Awarded | 40% | 2025-12-18 | 2026-03-26
RR/RDA/13/25/07/NP/MUL | Kanagarayankulam District Boundary Road (Old Kandy road) | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 220671169.9 | 159972500 | Awarded | 60% | 2025-12-18 | 2026-03-26
RR/RDA/13/25/08/NP/MUL | Kumulamunai Akkarayan road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 198505802.7 | 148861042 | Awarded | 70% | 2025-12-18 | 2026-04-01
RR/RDA/13/25/10/NP/MUL | Pandiyankulam Neddankandal Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 191627958.51 | 144696282.5 | Awarded | 70% | 2025-12-18 | 2026-04-01
RR/RDA/13/25/11/NP/MUL | Ethawetuvuwewa to Sampathnuwara | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 141810206.62 | 110422944.5 | Awarded | 30% | 2026-03-12 | 2026-06-22
| Akkaraiveli Paraiyanaru (Vilaththiyad) Road 3 Package 1 | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road |  |  | 130603950.3 |  | Pending | 0%
| Neththaliyaru School Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Tender Below 50Mn | Tender | Rural Road |  |  | 42078543.48 |  | Pending | 0%
| Udanka Road Package I | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road |  |  | 86129968.91 |  | Pending | 0%
| Kalvilan 1 st Lane | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Above 50Mn | Tender | Rural Road |  |  | 51243975.25 |  | Pending | 0%
| Naddankandal 3rd Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | Tender Below 50Mn | Tender | Rural Road |  |  | 47474958.76 |  | Pending | 0%
| Karmanthapura to Kalyanipura - Pillaiyara Kovil Road Package I | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 84581356.3 |  | Pending | 0%
| Vattappalai - Mulliyawalai 10th Cross Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Sivanagar - Ananthapuram Kirusnar Kovill Ampalavanpokkanai link Road Package 1 | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 65350903.39 |  | Pending | 0%
| Panankamam Sivan Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Tender Below 50Mn | Tender | Rural Road |  |  | 40823329.68 |  | Pending | 0%
| Iyankankulam Village Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RDA/GOSL/NP/RR/LCB/PACKAGE 2(MU) | Thapaalaga veethi Section I &II, 2nd Cross Road, Kallappadu kadtkarai Main Road, Koolamurippu kerudamadu enaippu veethi and Olumadu Pullmachchinathikulam Ampakamam Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu |  | PIU | Tender | Rural Road | RR Construction (Pvt) Ltd. |  | 586656287.93 | 659118972.33 | Awarded | 0% | 2026-10-02
RR/RDA/11/25/01/NP/MNR | Mahilankulam Pallamadhu road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | George Steuart Engineering (Pvt)Ltd |  | 274228723.54 | 189602588.3 | Awarded | 50% | 2026-01-29 | 2026-05-25
RR/RDA/11/25/02/NP/MNR | Piramanayankulam Parappukadanthan road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | George Steuart Engineering (Pvt)Ltd |  | 244135763.06 | 169538631.82 | Awarded | 55% | 2026-01-29 | 2026-05-25
RR/RDA/11/25/03/NP/MNR | Kaddadivayal Ramayankulam Naddankandal road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 534364027.24 | 397160000 | Awarded | 0% | 2026-08-14
RR/RDA/11/25/04/NP/MNR | Tharavankottai to Keeri Main Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | VN Construction JV |  | 76333504.2 | 146489579.5 | Awarded | 60% | 2026-02-19 | 2026-06-04
RR/RDA/11/25/07/NP/MNR | Avithappar Panimayam Internal Road with Culvert - Pesalai | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | VN Construction JV |  | 85087335.02 |  | Awarded | 70% | 2026-02-19 | 2026-06-04
RR/RDA/11/25/11/NP/MNR | Eruvittan - Vellalakaddu Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | VN Construction JV |  | 57826727.83 |  | Awarded | 5% | 2026-02-19 | 2026-06-04
RR/RDA/11/25/05/NP/MNR | Konnayan Kudiyiruppu Internal Main Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 135947165.98 | 90000000 | Awarded | 5% | 2026-01-29 | 2026-05-09
RR/RDA/11/25/06/NP/MNR | Martin Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Pastini Construction Material Supply |  | 41945343.47 | 26739158.6 | Awarded | 60% | 2026-03-20
RR/RDA/11/25/09/NP/MNR | Renovation of Mathirikiramam internal Road Naruvilikulam | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 40820067.58 | 28422878 | Awarded | 70% | 2025-11-26 | 2026-03-11
RR/RDA/11/25/10/NP/MNR | Malikaippiddy 1st 2nd 3rd 4th Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Vision Lanka Engineering (Pvt) Ltd |  | 30421965.37 | 22726000 | Awarded | 100% | 2025-11-20
RR/RDA/11/25/13/NP/MNR | Variveli Pandaraveli Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Sanjeeve Construction Work |  | 42658765.29 | 29619833.65 | Awarded | 100% | 2025-10-31 | 2026-01-30
RR/RDA/11/25/14/NP/MNR | Pichaivanifa Nedunkulam Scheme Internal Road 2 | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Fahim Builders |  | 22523861.72 | 14944097.22 | Awarded | 100% | 2026-03-20
RR/RDA/11/25/15/NP/MNR | Veppankulam Scheme Internal Road (Mosque) 3 | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Sanjeeve Construction Work |  | 24802089.31 | 17836311.35 | Awarded | 100% | 2025-10-24 | 2026-01-23
RR/RDA/11/25/16/NP/MNR | P.P.Potkerny Scheme Internal Road 1 | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 20672459.81 | 14295963 | Awarded | 70% | 2025-11-26 | 2026-04-02
RR/RDA/11/25/18/NP/MNR | Akaththimurippu Internal Road 3 | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 23278986.71 | 15815393 | Awarded | 70% | 2025-11-26 | 2026-04-02
RR/RDA/11/25/19/NP/MNR | Chilawathurai Maiyavadi Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 34056451.63 | 22899536 | Awarded | 100% | 2025-11-26
RR/RDA/11/25/20/NP/MNR | Kondachchi to Pasithenral Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 28462180.38 | 18513473 | Awarded | 70% | 2025-11-26
RR/RDA/11/25/22/NP/MNR | School back side road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Below 50Mn | Tender | Rural Road | Sintha Construction (Pvt) Ltd |  | 24840827.25 | 17295437.5 | Awarded | 30% | 2026-03-20
RR/RDA/11/25/23/NP/MNR | Palakaimunai Beach Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 184321656.31 | 111500000 | Awarded | 20% | 2025-11-26
RR/RDA/11/25/24/NP/MNR | Murukan Kovil Main Road | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | Tender Above 50Mn | Tender | Rural Road | Abdul Cader Constructions |  | 59821861.03 | 36558775 | Awarded | 100% | 2025-12-12
| Pallavarayankaddu Junction - Kiranchi - Ponnaveli Road | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | Nimna Holdings (Pvt) Ltd |  | 237551577.31 | 206440000 | Awarded | 0% | 2026-10-13
RR/RDA/14/25/06/NP/KLN | Skanthapuram Kannan Temple road | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | Sun Constructions (Pvt) Ltd. |  | 214117844.07 | 138750000 | Awarded | 35% | 2025-11-19 | 2026-03-03
RR/RDA/14/25/07/NP/KLN | Mayilvakanapuram kolunthupulavu road | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | RR Construction (Pvt) Ltd. |  | 353834298.91 | 224197154.05 | Awarded | 30% | 2026-02-26
RR/RDA/14/25/08/NP/KLN | Kalmadu 7th unit 3rd lane | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | Kanola Constructions & Engineering (Pvt) Ltd |  | 92284361.31 | 58116410 | Awarded | 20% | 2025-11-19 | 2026-03-03
RR/RDA/14/25/09/NP/KLN | Neliyai Amman kovil road | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | Kanola Constructions & Engineering (Pvt) Ltd |  | 182796432.72 | 113238042.5 | Awarded | 0% | 2025-11-26 | 2026-03-10
RR/RDA/10/25/24/NP/KLN | Kevil Nithtiyaveddai Road 2.150 | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | Tender Above 50Mn | Tender | Rural Road | Kanola Constructions & Engineering (Pvt) Ltd |  | 112111761.11 | 67998480 | Awarded | 0% | 2025-11-26 | 2026-03-10
| Main Road (Wireless Road) | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Below 50Mn | Tender | Rural Road |  |  | 49788531 |  | Pending | 0%
| Pallavarayan Sollai Nila Road | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 108583291.75 |  | Pending | 0%
| Inthirapuram internal road (Vempedukerny Puliyady Road) | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Below 50Mn | Tender | Rural Road |  |  | 36278221.16 |  | Pending | 0%
| Sakthypuram Main Road | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 118367133.03 |  | Pending | 0%
| Zone 3,6,7 Main Road | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 194943451.8 |  | Pending | 0%
RR/RDA/14/25/10KM/06/NP/KLN | Piramanthanaru road | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | Tender Above 50Mn | Tender | Rural Road |  |  | 62208115.04 |  | Pending | 0%
RDA/GOSL/NP/RR/LCB/PACKAGE 1(KN) | Vannerikulam Jeyapuram Road, Anaikkaddy Road, Veddukkaddu Road Sec.i & iii and Sekkalai Mudkompan Road | Northern Province | Kilinochchi | Northern Province | Mullaitivu |  | PIU | Tender | Rural Road | RR Construction (Pvt) Ltd. |  | 758268144.22 | 801739984.32 | Awarded | 0% | 2026-10-02
RR/RDA/25/24/01/SBP/RTP | From Delgas Junction To Vilehena Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | Siri Construction |  | 43303726.54 | 30346327.41 | Awarded | 90% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/02/SBP/RTP | Thundola Varathenna Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | Tender Above 50Mn | Tender | Rural Road | Siri Construction |  | 122516687.81 | 123540895.5 | Awarded | 35% | 2025-12-24 | 2026-05-02
RR/RDA/25/24/03/SBP/RTP | From Thunaghahena To Temple Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | Siri Construction |  | 27753891.86 | 20065425.82 | Awarded | 95% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/04/SBP/RTP | Keenagahawila Kanuggala Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | SSP Engineering |  | 49180179.81 | 33392908.77 | Awarded | 100% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/05/SBP/RTP | From Nadurana Kosgas Junction to Bathalakotuwa Via Kiriporuwa Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | SSP Engineering |  | 30993635.49 | 21592962.26 | Awarded | 100% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/06/SBP/RTP | Hewainna Koshenagama Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | Asela Construction |  | 26723132.29 | 18485912.16 | Awarded | 100% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/10/SBP/RTP | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Above 50Mn | Tender | Rural Road | Sam Dam |  | 50516461.34 | 31673916.45 | Awarded | 95% | 2025-11-19 | 2026-04-27
RR/RDA/25/24/13/SBP/RTP | Henyaya - Mirishena South Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | SSP Engineering |  | 13467295.53 | 10331554.6 | Awarded | 100% | 2025-11-06 | 2026-02-19
RR/RDA/25/24/14/SBP/RTP | Pimbura- Peelwatta Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | SSP Engineering |  | 19335843.37 | 15010646.74 | Awarded | 100% | 2025-11-06 | 2026-02-19
RR/RDA/25/24/16/SBP/RTP | Kalawana Salgaha Yata Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | SSP Engineering |  | 50567711.43 | 34292579.12 | Awarded | 100% | 2025-09-12 | 2025-12-15
RR/RDA/25/24/18/SBP/RTP | City Garden Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Below 50Mn | Tender | Rural Road |  |  | 7422727.84 |  | Pending | 0%
RR/RDA/24/25/21/SBP/RTP | Sudagala Grama Seva Division, From Sudagala to Tunudola Road up the mountain to near the cooperative | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | DKS Construction |  | 42448062.24 | 35222472.34 | Awarded | 0% | 2026-07-01 | 2026-10-13
| The road from near Diyabandihena Watta to Guruluwana junction on the Kuruwita Siripagama main road. | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Above 50Mn | Tender | Rural Road |  |  | 159598630.54 |  | Pending | 0%
| Development of carpeting on Laduyaya Borangamuwa road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/24/25/25/SBP/RTP | From the point where the Bulathgama-Pallevela road starts from Rasagala Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Below 50Mn | Tender | Rural Road | Sathira Construction |  | 9080628.78 | 7273850 | Awarded | 0% | 2026-08-10 | 2026-11-22
RR/RDA/24/25/28/SBP/RTP | From near Kalal Ella Rubber Store to Narangalla via Navinikanda Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Below 50Mn | Tender | Rural Road | KEP Construction |  | 24660700.4 | 18880633.26 | Awarded | 0% | 2026-07-28 | 2026-11-09
| Kahawatta Kurugammodara Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Above 50Mn | Tender | Rural Road |  |  | 82619762.22 |  | Pending | 0%
RR/RDA/24/25/31/SBP/RTP | Development of Koratuwegoda Road from Main Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Below 50Mn | Tender | Rural Road | KEP Construction |  | 29632612.99 | 19882000.02 | Awarded | 0% | 2026-08-21 | 2026-12-03
RR/RDA/24/25/32/SBP/RTP | Weligepola to Nitta Kumbura Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | Tender Below 50Mn | Tender | Rural Road | Sasiri Construction |  | 18898027.21 | 14421268 | Awarded | 0% | 2026-08-10 | 2026-11-22
| Eheliyagoda Asgangula Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Above 50Mn | Tender | Rural Road |  |  | 79199533.54 |  | Pending | 0%
RR/RDA/24/25/34/SBP/RTP | Matuwagala Mudun Kotu Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Below 50Mn | Tender | Rural Road | DKS Construction |  | 33238726.51 |  | Awarded | 0% | 2026-07-01 | 2026-10-13
RR/RDA/24/25/35/SBP/RTP | Induruwa Junction to Kadawatha junction road joining Kuruwita - Siripagama road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | Tender Above 50Mn | Tender | Rural Road | Creates Consultant and Construction |  | 101561648.5 | 70340000 | Awarded | 0% | 2026-04-27
| Panagamuwa Talagahawatta Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | Tender Above 50Mn | Tender | Rural Road |  |  | 123296168.25 |  | Rebid | 0%
| Gallinthanna Road from Juul Katiya Junction | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | Tender Above 50Mn | Tender | Rural Road |  |  | 193492340.36 |  | Pending | 0%
| Dorapane Road through Omalpe, Dadayamkanda, Morawadiya | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | Tender Above 50Mn | Tender | Rural Road |  |  | 268968392.71 |  | Pending | 0%
| Polgahamada Nawinna road in Panamura | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura |  | PIU | Tender | Rural Road |  |  |  |  | Pending | 0%
| Pallebedda Galpaya main road with culverts | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura |  | PIU | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/25/25/01/SBP/KGL | Hulankapolla To Ganthuna Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Above 50Mn | Tender | Rural Road |  |  | 51518594.22 |  | Rebid | 0%
RR/RDA/25/25/02/SBP/KGL | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Above 50Mn | Tender | Rural Road | EHL Constructions |  | 52222845.54 | 36210751.61 | Awarded | 85% | 2026-01-20 | 2026-05-04
RR/RDA/25/25/03/SBP/KGL | From Kehelpannala Junction to Pahala Kabawita Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Above 50Mn | Tender | Rural Road | SF Constructions |  | 96478103.45 | 71786959.2 | Awarded | 95% | 2025-12-22 | 2026-04-30
RR/RDA/25/25/05/SBP/KGL | Siyabalangamuwa Kudumbuwa Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road | Shanho Engineering |  | 46027479.81 | 39262197.06 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/25/25/06/SBP/KGL | From Dombemada Post Office to Sillugala Via Wedollamada well | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road | Shanho Engineering |  | 45066393.95 | 37416631.86 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/25/25/09/01/SBP/KGL | The first phase of the Matiyagane-Berawandare road from Mas Potha via Haliyagoda | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road | Samindra construction |  | 28713235.52 | 26656967.36 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/25/25/09/02/SBP/KGL | The first phase of the Gaitahpura road via Ambagala on the Warakapola Technical College Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road |  |  | 47360768.89 |  | Awarded | 0%
RR/RDA/25/25/10/SBP/KGL | Elipangamuwa School Road through Pananawaththa | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road | DHP Construction |  | 33397400.45 | 23988665.8 | Awarded | 100% | 2025-10-20 | 2026-02-01
RR/RDA/25/25/15/SBP/KGL | Moraliya Gagaboda Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | DHP Construction |  | 48285852.39 | 38093328.62 | Awarded | 90% | 2025-10-20 | 2026-02-01
RR/RDA/25/25/20/SBP/KGL | Neluwakkana gama meda Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | Loshitha Construction |  | 33221060.47 | 23823804.13 | Awarded | 95% | 2025-11-06 | 2026-02-18
| Panawaththa Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Above 50Mn | Tender | Rural Road |  |  | 80232196.86 |  | Pending | 0%
RR/RDA/25/25/27/SBP/KGL | Yatiyanthota Meegasthanna Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road |  |  | 49891809.39 |  | Pending | 0%
RR/RDA/25/25/28/SBP/KGL | Naagas thenna Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Above 50Mn | Tender | Rural Road | Jayasinghe Contractors (Pvt) Ltd. |  | 103886540.99 | 102000742.36 | Awarded | 90% | 2026-02-19 | 2026-08-12
RR/RDA/25/25/31/SBP/KGL | Developing the section connecting the road from the old office in Yatawala to the road in Beraliyahinna | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | DHP Construction |  | 14520809.96 | 13369909.3 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/25/25/32/SBP/KGL | Concreting the unconcreted areas of the Hingurana road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | DHP Construction |  | 17242742.81 | 15740043.19 | Awarded | 100% | 2025-11-20 | 2026-03-04
RR/RDA/25/25/33/SBP/KGL | Rehabilitation of Kahatapanawa Kajugahamula road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | Jayabima Engineering |  | 16993706.54 | 12423785 | Awarded | 100% | 2025-11-06 | 2026-02-18
RR/RDA/25/25/34/SBP/KGL | Road Connecting Ihala Palampitiya and Pahala Palampitiya | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | DKS Nishantha Construction |  | 36648120.48 | 26331747.62 | Awarded | 0% | 2026-07-10 | 2026-10-22
RR/RDA/25/25/35/SBP/KGL | Kudadeniya Adurapola Watta Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | TMT Construction |  | 41661137.53 | 29362927.93 | Awarded | 60% | 2026-02-18 | 2026-06-02
| Kendal Oya Marga | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Above 50Mn | Tender | Rural Road |  |  | 109854068.22 |  | Rebid | 0%
RR/RDA/25/25/38/SBP/KGL | Development of the road near the closed tea factory on Edurapola Watta main road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | TMT Construction |  | 30599205.16 | 22209331.1 | Awarded | 95% | 2026-02-18 | 2026-06-04
RR/RDA/25/25/39/SBP/KGL | Development of Gatayamulla Jagatpura Pannala Rasnadeniya road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | Samindra Construction |  | 32775992.83 | 31491651.4 | Awarded | 95% | 2026-05-19 | 2026-08-31
RR/RDA/25/25/40/SBP/KGL | Kabagamuwa 17 Acres Road Development | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | Tender Below 50Mn | Tender | Rural Road | TMT Construction |  | 18604688.76 | 14823379.41 | Awarded | 95% | 2026-02-15 | 2026-05-28
RR/RDA/25/25/41/SBP/KGL | Puwakdeniya gama meda road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | Tender Below 50Mn | Tender | Rural Road | Mash Construction |  | 23731882.81 | 18908497.09 | Rebid | 0% | 2026-02-15 | 2026-05-28
| Kadugannawa road through Ganethanna - Udamakadawara Balana | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/07/25/02/SP/GAL | Delgahabedda-Kirimatiya Margaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Above 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 50069275.91 | 26404581.16 | Awarded | 93% | 2025-09-12 | 2025-12-16
RR/RDA/07/25/05/SP/GAL | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Dissanayaka Builders |  | 45727567.86 | 25809376.97 | Awarded | 95% | 2025-09-11 | 2025-12-16
RR/RDA/07/25/06/SP/GAL | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Star Light Construction |  | 22862917.58 | 13805759 | Awarded | 100% | 2025-09-11 | 2025-12-16
RR/RDA/07/25/08/SP/GAL | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | EHL Constructions |  | 39100160.8 | 27637049 | Awarded | 100% | 2025-10-03 | 2026-01-16
RR/RDA/07/25/09/SP/GAL | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | DGSD Construction |  | 42959652.18 | 28039359.88 | Awarded | 98% | 2025-09-12 | 2025-12-16
RR/RDA/07/25/11/SP/GAL | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Jayathissa Construction |  | 32148979.96 | 20801618.2 | Awarded | 100% | 2025-09-09 | 2025-12-16
RR/RDA/07/25/12/SP/GAL | Galandeniya Margaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Star Light Construction |  | 44471797.26 | 26433958.63 | Awarded | 100% | 2025-09-11 | 2025-12-16
RR/RDA/07/25/13/SP/GAL | Aganaketiya Anuruddagama Mansandiye sita Samagipura dakwa Pradana Maragaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Above 50Mn | Tender | Rural Road | EHL Constructions |  | 73974599.04 | 66310000 | Awarded | 0% | 2026-09-29
RR/RDA/07/25/15/SP/GAL | Dikhena Margaya | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Above 50Mn | Tender | Rural Road | Thilak Kumara Builders |  | 51022213.05 | 34817376.22 | Awarded | 100% | 2025-09-11 | 2025-12-16
RR/RDA/07/25/17/SP/GAL | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | P.H. Engineering Construction (Pvt) Ltd |  | 33516218.38 | 20798250 | Awarded | 47% | 2025-09-11 | 2025-12-16
RR/RDA/07/25/19/SP/GAL | SuriEla Margaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | A.D. Herath Engineering |  | 18573267.25 | 14387747 | Awarded | 96% | 2025-09-25 | 2026-01-08
RR/RDA/07/25/20/SP/GAL | Road from Kammale Kadaya Junction to Udumalagala Juunction | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | Kumarage Enterprises(Pvt)Ltd |  | 40743279.23 | 25272045.84 | Awarded | 100% | 2025-09-26 | 2026-01-09
| Development of the Olagoda road from the top of the Olagoda hill to the society hall (including the broken culvert near Mr. Jayatissa's house) | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 27042444.01 |  | Pending | 0%
| Development of the section from the entrance of the second lane of the Cinnamon main road to Mr. Priyantha's house and on the left side of the road to Luxe Hotel with side drains and development of the dilapidated area on the road leading to Your Family River Hotel. | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 16566295.54 |  | Rebid | 0%
| Carpeting and development of 1500 meters of Pelegasketiya road from near Temkope Stone Mill in Mahambana to Kanda Uda Kadaya on Ellakanda road with side walls, culverts and drainage system | Southern Province | Galle | Southern Province | Galle |  | Tender Above 50Mn | Tender | Rural Road |  |  | 70840727.24 |  | Pending | 0%
RR/RDA/07/26/10KM/05 | Widening and Development of the road from Angaliya Junction to Akuratiya Hill with culverts | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | EHL Constructions |  | 32752577.91 | 36101846 | Awarded | 0% | 2026-09-04 | 2026-12-18
| Development of the road starting from Etambagaha Junction on the Ambalangoda-Batapola Thilakapura main road near RTS Wholesale Shop using asphalt/carpet | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 27791636.42 |  | Pending | 0%
| Carpeting and development of the road from near Kahawa Rathanasara Vidyalaya to Kuruppukanda Viharaya | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road |  |  | 18644478.4 |  | Pending | 0%
RR/RDA/07/26/10KM/08 | Development of 700 meters from Baddegama Vanduramba Road near Kola Kids Preschool and 300 meters from Temple Junction towards Dolahena | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | Kumarage Enterprises(Pvt)Ltd |  | 19813729.63 | 16745721.52 | Awarded | 0% | 2026-09-02 | 2026-12-16
| Development of Rejipura Galathota Ring Road with Concrete | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 18825117.04 |  | Rebid | 0%
| Carpeting of the road from near Lenagalpalatha Miris Mudalali Shop to Mr. Ajith's house | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 19652784.44 |  | Rebid | 0%
| The road from the house of Mr. Suduwella Piyavikum in Nalagasdeniya to the house of Mrs. Seetha Balapatabedige in Vavulagoda 1st Lane and up to Mrs. Sujatha's house in Wadugoda 2nd Lane. | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road |  |  | 20284688.43 |  | Pending | 0%
RR/RDA/07/26/10KM/12 | 9 Pillar Junction to Mr. Asanka's Shop on Udubattawa Watta Road | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | Kumarage Enterprises(Pvt)Ltd |  | 19631662.62 | 17311725.2 | Awarded | 0% | 2026-09-02 | 2026-12-16
| Bentota Kommala Sugatha Elders Housing Road | Southern Province | Galle | Southern Province | Galle |  | Tender Above 50Mn | Tender | Rural Road |  |  | 75878547.57 |  | Pending | 0%
RR/RDA/07/26/10KM/14 | Kodagoda Thudugala Road | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Jayathissa Construction |  | 49447887.76 | 43914369.51 | Awarded | 0% | 2026-09-04 | 2026-12-18
| Development of the Kosgahadeniya road from the last point of concretization using concrete. | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Concretisation of the upper part of Kadihingala Dangahena Road | Southern Province | Galle | Southern Province | Galle |  | Tender Below 50Mn | Tender | Rural Road |  |  | 24822005.36 |  | Rebid | 0%
| Development of the canal side road from Milidduwa Bridge to Moragoda Bridge with bays at suitable places | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/07/26/10KM/18 | Expansion of Alikehena Road from Thalawa Junior College to Atakohota border | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | S.A.Construction |  | 34701241.47 | 32247273.3 | Awarded | 0% | 2026-09-10 | 2026-12-24
| ADS Kalansooriya Mawatha | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/07/26/10KM/20 | Development of Paramount City Road. | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | EHL Constructions |  | 21005952.76 | 17088929 | Awarded | 0% | 2026-09-07 | 2026-12-21
RR/RDA/07/26/10KM/21 | Concretisation of Dikhena Welamedda road up to Addunkelle with 2 culverts and side walls on both sides. | Southern Province | Galle | Southern Province | Galle | Galle | Tender Below 50Mn | Tender | Rural Road | Isula Construction |  | 44235916.42 | 37684669 | Awarded | 0% | 2026-09-07 | 2026-12-21
RR/RDA/07/26/10KM/22 | Kapalwila Olympus Waththa I.K. Road from Mr. Sunil's house to Rakshana Village Bodhi near Ketagoda Kada. | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road | Woshitha Engineering(Pvt)Ltd |  | 22218525.7 | 18381732.6 | Awarded | 0% | 2026-09-04 | 2026-12-18
| Kimbulawala to Porawagama Road | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Medagama Ihala Maddegama Pusselkada Maddegama Road | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Kurupanawa Meliban Road | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Halvitigala Janapadaya to Thawalama Mookalana Road | Southern Province | Galle | Southern Province | Galle |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Habarakada Ibbawila Yattapana Road | Southern Province | Galle | Southern Province | Galle | Hiniduma | Tender Below 50Mn | Tender | Rural Road |  |  | 33578781.81 |  | Pending | 0%
RR/RDA/25/08/03/SP/MTR | Wattakgoda Ayurvedha Rohala Margaya Sanwardanay kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Visula Construction |  | 40420715.27 | 33591312.7 | Awarded | 100% | 2025-09-09 | 2025-12-16
RR/RDA/25/08/08/SP/MTR | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Southern Province | Matara | Southern Province | Matara | Deniyaya | Tender Below 50Mn | Tender | Rural Road | Induwara Construction |  | 14394112.26 | 11168036 | Awarded | 100% | 2025-10-03 | 2026-01-16
RR/RDA/25/08/10/SP/MTR | Arapotha Belideniya Margaya Carpet athura Sanwardanaya Kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Rathna Construction |  | 32189689.87 | 22859983.85 | Awarded | 100% | 2025-09-09 | 2025-12-23
RR/RDA/25/08/12/SP/MTR | Nawalahena Palamu Para Sanwardanaya Kirima (Jagath Mahathage Niwasa asala sita Kuruppu Mahathage Niwasa Dakwa) | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Rathnayake Construction |  | 7523859.66 | 5399259.8 | Awarded | 100% | 2025-10-03 | 2026-01-16
RR/RDA/08/25/13/SP/MTR | Heelakanda Kanishta Vidyalaya asala sita Budu Medura Dakwa margaya Sanwardanaya Kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Madurapperuma Construction & Supply |  | 12476822.24 | 8331854.95 | Awarded | 100% | 2025-09-22 | 2026-01-05
RR/RDA/08/25/14/SP/MTR | Kanaththewatta kade asala sita Mulana Ela Margaya Dakwa Sanwardanaya Kirima (Pethibemi Sahithawa) | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Madurapperuma Construction & Supply |  | 18602255.2 | 12885039.94 | Awarded | 100% | 2025-09-22 | 2026-01-05
RR/RDA/08/25/15/SP/MTR | Pasal Mawathe Weerathunga Petti Bokkuwa Asala Sita Iriyagaha Mulana Bokkuwa Dakwa Pethi Bemi yoda Sanwardanaya Kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Madurapperuma Construction & Supply |  | 32183364.43 | 20214236.58 | Awarded | 100% | 2025-09-22 | 2026-01-05
RR/RDA/08/25/16/SP/MTR | Walgama Saddathissa Mawathe Primesity Niwasa Sankeernaye Prawesha Margaya Kapat yoda Sanwardanaya kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Jagath construction |  | 13010600.06 | 7623062.15 | Awarded | 100% | 2025-10-10 | 2026-01-23
RR/RDA/08/25/18/SP/MTR | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Dashodhaya (Pvt)Ltd |  | 6117703.11 | 4080866.9 | Awarded | 0% | 2025-09-25 | 2026-01-08
RR/RDA/08/25/19/SP/MTR | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Southern Province | Matara | Southern Province | Matara | Deniyaya | Tender Below 50Mn | Tender | Rural Road | Gamage Builders |  | 14049577.09 | 10371473.2 | Awarded | 100% | 2025-09-22 | 2026-01-05
RR/RDA/08/25/20/SP/MTR | Naymbala kendawala haraha wellethota margaye wedugoda sthanaye pethi bemma sahithawa Sanwardanaya kirima | Southern Province | Matara | Southern Province | Matara | Matara | Tender Below 50Mn | Tender | Rural Road | Rathnayake Construction |  | 4877230.33 | 3502675 | Awarded | 100% | 2025-10-01 | 2026-01-14
| Development of the Dickwella-Thalahitiyagoda road by laying carpet | Southern Province | Matara | Southern Province | Matara |  | Tender Above 50Mn | Tender | Rural Road |  |  | 115469907.8 |  | Pending | 0%
| Development of the road by laying Asphalt starting from near Saddhatissa Junior College on the Panattiyana-Weligama road up to Barawadeniya Junction | Southern Province | Matara | Southern Province | Matara |  | Tender Above 50Mn | Tender | Rural Road | GEL Construction |  | 159903564.25 | 135290000 | Awarded | 0% | 2026-09-29
| Development of the Pathegama Temple Road (Massalatiya Road) by carpeting | Southern Province | Matara | Southern Province | Matara |  | Tender Above 50Mn | Tender | Rural Road | GEL Construction |  | 86763583.11 | 81100000 | Awarded | 0% | 2026-09-29
| Dehemulla Shop to Ukgashena Kiriweldeniya road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Hamaragoda road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Polgahamulla to Beragammulla road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Dampella 9 post to Horagoda east widapaththa shop road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Kamil pedesa | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Kiriweldola Himburahena road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Pelapelduwa road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Uyanwaththa rounabout road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Carpeting of 1st Cross Road | Southern Province | Matara | Southern Province | Matara |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/09/25/08/SP/HMB | Carpeting Pissubedda Medagamgoda road | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | Tender Below 50Mn | Tender | Rural Road | Samarasinghe Construction(Pvt)Ltd |  | 46881232.95 | 28923336.75 | Awarded | 98% | 2026-03-06 | 2026-06-19
RR/RDA/09/25/09/SP/HMB | Development of the road in front of Godawela School to Ambussa Wela | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | Tender Below 50Mn | Tender | Rural Road | A.T.L. Construction |  | 47452621.54 | 34500631 | Awarded | 60% | 2026-04-23 | 2026-07-23
RR/RDA/09/25/11/SP/HMB | Development of Walasmulla Daluwakgoda School Road | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | Tender Below 50Mn | Tender | Rural Road | Samarasinghe Construction(Pvt)Ltd |  | 48463720.72 | 34814777.8 | Awarded | 20% | 2026-05-21 | 2026-09-03
RR/RDA/09/25/13/SP/HMB | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | Tender Below 50Mn | Tender | Rural Road | A.T.L. Construction |  | 30673898.39 | 23847807.5 | Awarded | 60% | 2026-04-22 | 2026-07-22
RR/RDA/09/26/01 | From near the Bedigama North Health Center to Indimandiya | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | Tender Below 50Mn | Tender | Rural Road | Isula Construction |  | 31310907.66 | 31524955 | Awarded | 0% | 2026-09-10 | 2026-12-24
RR/RDA/22/25/01/UP/BDL | Kirikoonthenna Gamata piwisena Margaya | Uva Province | Badulla | Uva Province | Badulla | Mahiyanganaya | Tender Below 50Mn | Tender | Rural Road | Ema Constructions (Pvt) Ltd |  | 22562884.94 | 15276800 | Awarded | 100% | 2025-10-23 | 2026-02-05
RR/RDA/22/25/02/UP/BDL | 23 Ela Krushi Margaya | Uva Province | Badulla | Uva Province | Badulla | Mahiyanganaya | Tender Below 50Mn | Tender | Rural Road | Priyankara Industries and Contractors |  | 34734403.93 | 22422274.05 | Awarded | 100% | 2025-10-23 | 2026-02-05
RR/RDA/22/25/04/UP/BDL | Buluwa Margaya | Uva Province | Badulla | Uva Province | Badulla | Mahiyanganaya | Tender Below 50Mn | Tender | Rural Road | Samadhi Construction |  | 27796703.13 | 19800000 | Awarded | 100% | 2025-10-23 | 2026-02-05
RR/RDA/22/25/07/UP/BDL | Tharuna Govipola Margaye ithiri Kotasa Sanwardanaya Kirieema | Uva Province | Badulla | Uva Province | Badulla | Bandarawela | Tender Below 50Mn | Tender | Rural Road | Samadhi Construction |  | 15552666.77 | 13290035.01 | Awarded | 0% | 2025-10-31 | 2026-02-13
RR/RDA/22/25/08/UP/BDL | Maragaha ella Margaya Concrete Kireema | Uva Province | Badulla | Uva Province | Badulla | Bandarawela | Tender Below 50Mn | Tender | Rural Road | Priyantha Rathnayaka |  | 9166668.15 | 5650802.3 | Awarded | 100% | 2025-10-28 | 2026-02-10
RR/RDA/22/25/09/UP/BDL | Piyarapandowa Neluwa Margaya | Uva Province | Badulla | Uva Province | Badulla | Bandarawela | Tender Above 50Mn | Tender | Rural Road | Liyanage Contractors |  | 54647573.75 | 38470000 | Awarded | 10% | 2026-03-09
RR/RDA/22/25/12/UP/BDL | Galwelagama Margaye Pansala Asala Kotasa | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Priyankara Industries and Contractors |  | 19698086.11 | 16955320.78 | Awarded | 100% | 2025-10-31 | 2026-02-13
RR/RDA/22/25/14/UP/BDL | Pulleyar Kadura sita Keselwaththa Dakwa Piwisena Athrur Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Priyankara Industries and Contractors |  | 7780120.14 | 6085915 | Awarded | 100% | 2025-10-28 | 2026-02-10
RR/RDA/22/25/15/UP/BDL | Gallulla sita Galwelagama Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Ema Constructions (Pvt) Ltd |  | 19949882.12 | 15696340 | Awarded | 100% | 2025-09-24 | 2026-01-06
RR/RDA/22/25/18/UP/BDL | Pelgahathenna Vidyalaya asalin Landewela dakwa athi Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Prasad Builders |  | 6839881.74 | 5317232 | Awarded | 100% | 2025-10-28 | 2026-02-10
RR/RDA/22/25/19/UP/BDL | Tholabowaththa sita Meedumpitiya Dakwa yana Athuru Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Priyankara Industries and Contractors |  | 47901120.62 | 30478561.74 | Awarded | 100% | 2025-10-23 | 2026-02-05
RR/RDA/22/25/22/UP/BDL | Achchupatti Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | Tender Below 50Mn | Tender | Rural Road | Priyankara Industries and Contractors |  | 30435860.35 | 25269262.7 | Awarded | 20% | 2025-10-23 | 2026-02-05
| Kiriibban wewa Ayurweda road | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Tender Above 50Mn | Tender | Rural Road | U P Ranugge Construction (Pvt) Ltd |  | 53343034.36 | 34095028 | Awarded | 100% | 2026-01-01
| Katupila South Division, Katupila Lake Bogaha Junction to Ispil Canal Road Carpeting | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Tender Above 50Mn | Tender | Rural Road |  |  | 114710727.79 |  | Pending | 0%
| Carpeting of the road in front of the fish board in Kadawara area of ​​Mahagama division | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Tender Above 50Mn | Tender | Rural Road |  |  | 69135399.29 |  | Pending | 0%
| Mahanetola road road up to near Maha Vidyalaya | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Tender Above 50Mn | Tender | Rural Road |  |  | 103185312.51 |  | Pending | 0%
| Road in front of Daraya Arambekema Community Hall | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | Tender Above 50Mn | Tender | Rural Road |  |  | 138681686.49 |  | Pending | 0%
| Aratumedilla - Aguluwanwela Road | Uva Province | Monaragala | Uva Province | Monaragala | Bibile | Tender Above 50Mn | Tender | Rural Road |  |  | 77924916.82 |  | Pending | 0%
RR/RDA/01/25/03/WP/COL | Appropriate development of road from Maligagodella lake crossing near Isuri Motors to junction with Chandrika Kumaratunga Mawatha | Western Province | Colombo | Western Province | Colombo | Colombo | Tender Below 50Mn | Tender | Rural Road | Jayasinghe Contractors (Pvt) Ltd. |  | 31303935.95 | 23009836.05 | Awarded | 100% | 2025-10-09 | 2026-01-16
RR/RDA/01/25/14/WP/COL | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | Western Province | Colombo | Western Province | Colombo | Colombo | Tender Above 50Mn | Tender | Rural Road | W.A. Perera & Company (Pvt) Ltd. |  | 51359519.36 | 33591596.5 | Awarded | 68% | 2026-01-30 | 2026-05-12
RR/RDA/01/25/09/WP/COL | Kottawa Malabe Road Sirimalwatta 1 Main road carpeted and developed | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road | Accon Engineering (PVT) LTD |  | 2804484.03 | 2424881.23 | Awarded | 100% | 2025-10-09 | 2025-12-14
RR/RDA/01/25/12/WP/COL | 550 A Lakshapathi North Sri Lanka Army Electrical and Mechanical Engineering Base Workshop (Katupedda) to be carpeted and developed from Galle Road. | Western Province | Colombo | Western Province | Colombo | Colombo | Tender Below 50Mn | Tender | Rural Road | Accon Engineering (PVT) LTD |  | 11014256.76 | 8465142.73 | Awarded | 100% | 2025-10-09 | 2026-02-12
RR/RDA/01/25/19WP/COL | Puwakpitiya Dharmalapala Mawatha Main Road Development of the road from High Level Road to Elstonwatte Volleyball Court | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road | Asela Construction |  | 11872168.81 | 9189060 | Awarded | 90% | 2026-02-27 | 2026-05-15
| Development of Malabe Chandrika Kumaratunga Road (from near the New Kandy Bridge) up to the Arangala Bridge and the remaining section from the bridge towards Amarakota Road with carpet | Western Province | Colombo | Western Province | Colombo | Colombo | Tender Above 50Mn | Tender | Rural Road |  |  | 62587618.87 |  | Pending | 0%
RR/RDA/01/25/26/WP/COL | Boraluwathenna Pahala Uda Road | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road | Next Engineering Services (PVT) LTD |  | 27759276.9 | 21870721.4 | Awarded | 5% | 2026-02-13 | 2026-05-29
| Dangahadenia Egoda Road in Dambora | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road |  |  | 12771426.58 |  | Pending | 0%
RR/RDA/01/25/30/WP/COL | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Western Province | Colombo | Western Province | Colombo | Colombo | Tender Below 50Mn | Tender | Rural Road | Asset Engineering (Pvt)LTD |  | 22641802.22 | 21619184.95 | Awarded | 0% | 2026-07-17 | 2026-08-29
| Development of Prathibha Mawatha in the Boruketiya, Horagola, Kiriwatthuduwa, Homagama area using carpet. | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road |  |  | 29842698.07 |  | Pending | 0%
| Development of approximately 720 meters from Mangala Mawatha, Ramanayake Mawatha to the end of Delgahawatte Road using carpet. | Western Province | Colombo | Western Province | Colombo | Colombo | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Carpeting and Development of the road section belonging to the Maharagama Divisional Secretariat Division from the beginning of the Horahena Road, which turns south from the Malabe Road in Kottawa, to the Pasman Junction, with drainage system. | Western Province | Colombo | Western Province | Colombo | Avissawella | Tender Below 50Mn | Tender | Rural Road |  |  | 23637229.26 |  | Pending | 0%
| Thunandahena Junction to Delgahawaththa road | Western Province | Colombo | Western Province | Colombo |  | Tender Below 50Mn | Tender | Rural Road |  |  |  |  | Pending | 0%
| Pahalawela road to Japan Mithrathwa road | Western Province | Colombo | Western Province | Colombo |  | Not Specified | Tender | Rural Road |  |  |  |  | Pending | 0%
| Athurugiriya hospital to Galpoththa road | Western Province | Colombo | Western Province | Colombo |  | Tender Below 50Mn | Tender | Rural Road |  |  |  |  | Pending | 0%
RR/RDA/02/25/05/WP/GMP | Improvements to 70/A Pahala Kandawala Grama Niladharee wasame suuriya mawathe athuru mawathak wana jayashantha mahathaage niwasa asalin athi para praja shaalawa dakwaa saha dakunu pasata thi wiharasthanaya dakwa kotasa | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road | Jeyanthan Construction |  | 21560731.47 | 16250193.4 | Awarded | 100% | 2025-10-09 | 2026-01-29
RR/RDA/02/25/03/WP/GMP | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road | Dilini Builders (PVT) LTD |  | 6886574.13 | 5430100 | Awarded | 0% | 2026-06-16 | 2026-09-28
RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Western Province | Gampaha | Western Province | Gampaha | Nittambuwa | Tender Above 50Mn | Tender | Rural Road | Wijerathna Construction |  | 69742766.87 | 44980000 | Awarded | 20% | 2026-02-19 | 2026-06-05
| Development of the Ranaviru Upenda Mawatha | Western Province | Gampaha | Western Province | Gampaha |  | Tender Below 50Mn | Tender | Rural Road |  |  | 10222253.03 |  | Pending | 0%
| The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road | Dilini Builders (PVT) LTD |  | 43987022.27 | 35997890 | Awarded | 0% | 2026-04-30 | 2026-08-12
| Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Western Province | Gampaha | Western Province | Gampaha | Nittambuwa | Tender Below 50Mn | Tender | Rural Road | Jeyanthan Construction |  | 21828855.77 | 15498360 | Awarded | 0% | 2026-04-08 | 2026-07-21
| The road starts from Meeriyagama renda pola Junction Giriulla Road Near the Fuel Station Vidyalaya Mawatha | Western Province | Gampaha | Western Province | Gampaha | Nittambuwa | Tender Below 50Mn | Tender | Rural Road |  |  | 31363069.16 |  | Pending | 0%
| Udupila South Dolewatta | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Tender Below 50Mn | Tender | Rural Road | Creates Consultant and Construction |  | 8968820.62 | 7423117.7 | Awarded | 0% | 2026-04-02 | 2026-07-14
| Near Niwandama Cemetery to Jinaraja College | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road |  |  | 20123986.24 |  | Pending | 0%
| Development of the road from near Jude Church in Thuduwegedara Grama Seva Division to Kebelatta Bridge in Wattala with carpet | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road |  |  | 15735999.24 |  | Pending | 0%
RR/RDA/02/25/18/WP/GAM | Peliyagoda Naranminiya Road | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Tender Below 50Mn | Tender | Rural Road | Ceylux Civil engineering (Pvt) Ltd |  | 24821169.03 | 19082810 | Awarded | 0% | 2026-07-13 | 2026-10-20
| 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road | Jeyanthan Construction |  | 21486157.55 | 15141484.5 | Awarded | 0% | 2026-04-08 | 2026-07-21
| Road from Giridara Malida Bodhi to 2 post | Western Province | Gampaha | Western Province | Gampaha | Nittambuwa | Tender Above 50Mn | Tender | Rural Road |  |  | 54037958.71 |  | Pending | 0%
| 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Western Province | Gampaha | Western Province | Gampaha | Gampaha | Tender Below 50Mn | Tender | Rural Road | Yagoda Construction |  | 12991931.82 | 11473274.8 | Awarded | 0% | 2026-07-15 | 2026-10-29
| Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Western Province | Gampaha | Western Province | Gampaha | Negombo | Tender Below 50Mn | Tender | Rural Road | Jeyanthan Construction |  | 26884145.14 | 19032750 | Awarded | 0% | 2026-03-27 | 2026-07-10
RR/RDA/03/25/02/WP/KTR | Concreting of the first side road on the left side of Rasik Road | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 11126896.75 | 7705537.2 | Awarded | 100% | 2025-10-09 | 2025-12-29
RR/RDA/03/25/03/WP/KTR | Carpeting of Uswatta Lane | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Ramano Engineers |  | 7444801.7 | 6059612.5 | Awarded | 100% | 2025-10-09 | 2025-12-29
RR/RDA/03/25/05/WP/KTR | From near Mr. Abeywardena's house on the Yawita Kammalgoda road block stones and development (first phase) | Western Province | Kalutara | Western Province | Kalutara | Horana | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 31800339.88 | 21827299.85 | Awarded | 100% | 2025-10-09 | 2026-01-29
RR/RDA/03/25/08/WP/KTR | Asphalting from near Valkandala transformer to Panthiya Watta (Malamiriskanda road) | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | Tender Below 50Mn | Tender | Rural Road | Accon Engineering (PVT) LTD |  | 22843424.38 | 14577590.15 | Awarded | 100% | 2025-10-09 | 2026-01-29
RR/RDA/03/25/09/WP/KTR | Concreting of Weedahena road | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 19919301.67 | 15010244 | Awarded | 100% | 2025-10-09 | 2026-01-29
RR/RDA/03/25/12/WP/KTR | Concreting Batawala Road | Western Province | Kalutara | Western Province | Kalutara | Horana | Tender Below 50Mn | Tender | Rural Road | Next Engineering Services (PVT) LTD |  | 26342506.07 | 18670236.2 | Awarded | 39% | 2026-01-08 | 2026-04-21
| Development of 2.64 km section of Neluwa-Karapagala road with carpet | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | Tender Above 50Mn | Tender | Rural Road | EHL Constructions |  | 98008220.84 | 64190000 | Awarded | 0% | 2026-10-15
RR/RDA/03/25/WP/KLT/15 | Development of 1.5 km carpeting of Suduvelipatha Athale road from near Suduvelipatha bodhia towards Athale school | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | Tender Above 50Mn | Tender | Rural Road | EHL Constructions |  | 71868790.07 | 64190000 | Awarded | 0% | 2026-08-04
RR/RDA/03/25/16/WP/KTR | Development of carpeting of 1 km from Gane Aramba Road, Bogalla Junction to Ambepitiya Pinhena | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Asela Construction |  | 37805645.98 | 27990360 | Awarded | 0% | 2026-03-20 | 2026-07-03
| Development of 0.8 km carpeting of Newfa Mawatha | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 8350944.75 | 6972603.95 | Awarded | 0% | 2026-04-09 | 2026-07-22
RR/RDA/03/25/18/WP/KTR | Development of carpeting of the section (length 800 m) from near Minerithenna temple to Jananandanarama temple | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Asela Construction |  | 23076319.79 | 17101775 | Awarded | 0% | 2026-03-20 | 2026-07-03
| Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 9421190.92 | 8285619 | Awarded | 55% | 2026-04-09 | 2026-07-22
| Development of from Lewis Stadium to Heladiva Malshalawa | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Below 50Mn | Tender | Rural Road | Develco Engineering (PVT) LTD |  | 18421245.76 | 15591781.1 | Awarded | 55% | 2026-04-09 | 2026-07-22
| Development of Bulathsinghala road through 3 km carp through Ulavelgama Kallumale estate | Western Province | Kalutara | Western Province | Kalutara | Kalutara | Tender Above 50Mn | Tender | Rural Road |  |  | 168040491.2 |  | Pending | 0%
RDA/GOSL/WP/RR/LCB/Pacakge1(KL) | Harankahapatha road, Kudakalupahana road, Bellana Egoda Watta road and Sirikandura junction to Sandasirigama via Valiketiya road | Western Province | Kalutara | Western Province | Kalutara |  | PIU | Tender | Rural Road |  |  | 734288781.97 |  | Pending | 0%
RDA/GOSL/WP/RR/LCB/Pacakge2(KL) | From Addaragoda Weepella Road via Wedigoda, Gulanwatta Nawala Mandagala Road and Boralugoda Thiniyawala Road | Western Province | Kalutara | Western Province | Kalutara |  | PIU | Tender | Rural Road | RR Construction (Pvt) Ltd. |  | 658255778.54 | 659050604.2 | Awarded | 0% | 2026-10-02
RDA/GOSL/WP/RR/LCB/Pacakge3(KL) | Malliwatta Road via Paraigama Elagiriya, Miriswatta School Road, Maddegama toThalpediwala Road across Meegahathenna, Horana Peruwa Road, Gallemamulla Pansala Road and Neluwa-Karapagala Road | Western Province | Kalutara | Western Province | Kalutara |  | PIU | Tender | Rural Road |  |  | 756465751.92 |  | Pending | 0%
RR/RDA/04/25/42 | Mahanuwara Digana pradana margaye gamudawa jala tankiya asala sita Malgahamula handiya dakwa Margaya | Central Province | Kandy | Central Province | Kandy | Kundasale | DL Stage 01 | Direct Labour | Rural Road |  |  | 21611921.71 | 21611921.71 | Awarded | 100% |  | 2025-07-21
RR/RDA/04/25/45 | Seewalee Kande sits Mahthanna Samadi Senasuna dakwa divena margaya | Central Province | Kandy | Central Province | Kandy | Kandy | DL Stage 01 | Direct Labour | Rural Road |  |  | 40376466.56 | 40376466.56 | Awarded | 100% |  | 2025-08-21
RR/RDA/04/25/18 | Dewaraja Mw (Balance Work) | Central Province | Kandy | Central Province | Kandy | Gampola | DL Stage 01 | Direct Labour | Rural Road |  |  | 29009072.8 | 29009072.8 | Awarded | 100% |  | 2025-07-21
RR/RDA/04/25/30 | Uduwella Ganadevi strachue near the Sahira Estate to Alugolla Road | Central Province | Kandy | Central Province | Kandy | Kadugannawa | DL Stage 01 | Direct Labour | Rural Road |  |  | 19320349.84 | 19320349.84 | Awarded | 100% |  | 2025-08-21
RR/RDA/05/25/03 | Serugolla Middle Road Kanwawala Junction to NawarathnaGoda Main Road | Central Province | Matale | Central Province | Matale | Matale | DL Stage 01 | Direct Labour | Rural Road |  |  | 30080524.87 | 29509544.69 | Awarded | 100% |  | 2025-09-30
RR/RDA/05/25/05 | Near the Old Foodsity to Galwetiyawa Road | Central Province | Matale | Central Province | Matale | Nalanda | DL Stage 01 | Direct Labour | Rural Road |  |  | 35717528.78 | 35717528.78 | Awarded | 100% |  | 2025-08-21
RR/RDA/06/25/33 | Mool oya Main Road Section 1 | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | DL Stage 01 | Direct Labour | Rural Road |  |  | 59668203.37 | 59668203.37 | Awarded | 100% |  | 2025-09-21
RR/RDA/06/25/35 | Gaminipura Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | DL Stage 01 | Direct Labour | Rural Road |  |  | 60272506.06 | 59292443.8 | Awarded | 100% |  | 2025-10-01
RR/RDA/06/25/36 | CWM Factory Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | DL Stage 01 | Direct Labour | Rural Road |  |  | 65323196.31 | 65323196.31 | Awarded | 100% |  | 2025-09-21
RR/RDA/04/25/12 | Wattaranthenna Sri Sumangala Mawatha | Central Province | Kandy | Central Province | Kandy | Kandy | DL Stage 02 | Direct Labour | Rural Road |  |  | 8793978.6 | 8793978.6 | Awarded | 100% |  | 2025-10-11
RR/RDA/04/25/37 | Elkaduwa pare sita Japan para sanwardanaya kirima | Central Province | Kandy | Central Province | Kandy | Kundasale | DL Stage 02 | Direct Labour | Rural Road |  |  | 48931555.87 | 48931555.87 | Awarded | 100% |  | 2025-10-30
RR/RDA/04/25/40 | Lanka bankuwa asala sita Unambuwa dakwa diwena margaya thara damima | Central Province | Kandy | Central Province | Kandy | Gampola | DL Stage 02 | Direct Labour | Rural Road |  |  | 21307459.69 | 21307459.69 | Awarded | 100% |  | 2025-10-01
RR/RDA/04/25/46 | Gelioya to Pahingamuwa Road | Central Province | Kandy | Central Province | Kandy | Kadugannawa | DL Stage 02 | Direct Labour | Rural Road |  |  | 61266480.98 | 61266480.98 | Awarded | 100% |  | 2025-11-30
RR/RDA/05/25/15 | Salagama margaya Nikagolla margaye sita Boraluwa dakwa | Central Province | Matale | Central Province | Matale | Matale | DL Stage 02 | Direct Labour | Rural Road |  |  | 31665473.42 | 31665473.42 | Awarded | 100% |  | 2025-09-30
RR/RDA/06/25/39 | Madakumbura Dunukedeniya haraha Udagama dakwa Margaya | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | DL Stage 02 | Direct Labour | Rural Road |  |  | 40703316.18 | 40703316.18 | Awarded | 100% |  | 2025-11-16
RR/RDA/04/25/38 | Moladanda handiye sita Mangalagama maima dakwa diwena margaya thara dama sanwardanya | Central Province | Kandy | Central Province | Kandy | Kadugannawa | DL Stage 03 | Direct Labour | Rural Road |  |  | 13871976.5 | 13871976.5 | Awarded | 100% |  | 2025-11-10
RR/RDA/04/25/47 | Manikhinna Hurikaduwa Iththamaliyagoda New Temple Access Road | Central Province | Kandy | Central Province | Kandy | Kundasale | DL Stage 03 | Direct Labour | Rural Road |  |  | 10442337.36 | 10442337.36 | Awarded | 100% |  | 2025-11-16
RR/RDA/06/25/43 | Development of Ponnagar Road | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Norwood | DL Stage 03 | Direct Labour | Rural Road |  |  | 37481052.81 | 37481052.81 | Awarded | 100% |  | 2025-11-30
RR/RDA/06/25/44 | Carpeting of Muloya Main Road Section 2 | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | DL Stage 03 | Direct Labour | Rural Road |  |  | 42312390.95 | 42312390.95 | Awarded | 60% |  | 2025-12-31
RR/RDA/06/25/47 | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Hanguranketha | DL Stage 03 | Direct Labour | Rural Road |  |  | 28020844.83 | 28020844.83 | Awarded | 38% |  | 2025-12-31
RR/RDA/06/25/48 | Development of road in front of Divisional Secretariat East of Sangiripalayam Kothmale | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | DL Stage 03 | Direct Labour | Rural Road |  |  | 9106875.1 | 9106875.1 | Awarded | 100% |  | 2025-11-15
RR/RDA/06/25/52 | Development of Chandra Lal Karunarathne Mawatha | Central Province | Nuwara Eliya | Central Province | Nuwara Eliya | Nuwara Eliya | DL Stage 03 | Direct Labour | Rural Road |  |  | 9758284.5 | 9758284.5 | Awarded | 100% |  | 2025-11-15
RR/RDA/05/25/23 | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya | Central Province | Matale | Central Province | Matale | Nalanda | DL Stage 03 | Direct Labour | Rural Road |  |  | 28401905.12 | 28401905.12 | Awarded | 60% |  | 2026-06-13
RR/RDA/05/25/28 | Adawala Udagama Road | Central Province | Matale | Central Province | Matale | Nalanda | DL Stage 04 | Direct Labour | Rural Road |  |  | 56161142.68 | 56161142.68 | Awarded | 75% |  | 2026-02-22
RR/RDA/16/25/05 | Jannah Road from Annor Road to Jannah Mosque Junction | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Akkaraipattu | DL Stage 01 | Direct Labour | Rural Road |  |  | 15746511.36 | 15746511.36 | Awarded | 100% |  | 2025-08-21
RR/RDA/16/25/06 | Improvement of Mosque Lane from beach Road to Jummah Mosque Lane (0+500)m | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | DL Stage 01 | Direct Labour | Rural Road |  |  | 22306322.17 | 22306322.17 | Awarded | 100% |  | 2025-08-23
RR/RDA/SP/16/25/02 | Karana junction south pahalawela palanoya road (From near Pahalalanda post office junction to Karanagama) | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Ampara | DL Stage 01 | Direct Labour | Rural Road |  |  | 171722366.66 | 171722366.66 | Awarded | 100%
RR/RDA/16/25/02 | Muwagammana First Lane to Cemetry | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Ampara | Dehiaattakandiya | DL Stage 01 | Direct Labour | Rural Road |  |  | 37324257.12 | 37324257.12 | Awarded | 100% |  | 2025-09-16
RR/RDA/STA II/17/25/01 | Hira Village Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | DL Stage 03 | Direct Labour | Rural Road |  |  | 48842501.78 | 48842501.78 | Awarded | 100%
RR/RDA/16/25/10KM/10 | Imam Roomy School Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | DL Stage 04 | Direct Labour | Rural Road |  |  | 13946909.31 | 13946909.31 | Awarded | 100%
RR/RDA/16/25/10KM/12 | Kalyana Road | Eastern Province | Ampara | Eastern Province (Akkaraipattu) | Akkaraipattu | Kalmunai | DL Stage 04 | Direct Labour | Rural Road |  |  | 36778852.24 | 36778852.24 | Awarded | 100%
RR/RDA/15/25/08 | Kumpila Madu Road | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | DL Stage 01 | Direct Labour | Rural Road |  |  | 32424899.67 | 32424899.67 | Awarded | 100% |  | 2025-09-15
RR/RDA/17/25/04 | Cemetry Road (Poompuhr) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | DL Stage 01 | Direct Labour | Rural Road |  |  | 32194573.49 | 32194573.49 | Awarded | 100% |  | 2025-08-22
RR/RDA/15/25/10 | Concreting to Internal at MMV School | Eastern Province | Batticaloa | Eastern Province | Batticaloa | Batticaloa | DL Stage 02 | Direct Labour | Rural Road |  |  | 33890314.66 | 33890314.66 | Awarded | 95% |  | 2025-11-15
RR/RDA/17/25/17 | Furkaniya Marcus connection road (S.M.Unithu house to Market main road) | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | DL Stage 02 | Direct Labour | Rural Road |  |  | 15444993.23 | 15444993.23 | Awarded | 100% |  | 2025-09-30
RR/RDA/17/25/08 | Concreting of Play Ground Road Mahadiulwewa Stage II | Eastern Province | Trincomalee | Eastern Province | Trincomalee | Trincomalee | DL Stage 04 | Direct Labour | Rural Road |  |  | 43210842.75 | 43210842.75 | Awarded | 90% |  | 2026-03-31
RR/RDA/20/25/02 | Anuradhapura - Kurunegala pradana pare paththara kade handiyen aramba vee kodigala dakwa diwena margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | DL Stage 01 | Direct Labour | Rural Road |  |  | 50844733.35 | 50844733.35 | Awarded | 100%
RR/RDA/20/25/07 | Road from A9 main road to Karapikkada Carpet Road (0+290 - 0+960) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | DL Stage 01 | Direct Labour | Rural Road |  |  | 21229780.63 | 21229780.63 | Awarded | 100% |  | 2025-10-19
RR/RDA/20/25/15 | Dikediyaya mahaweli pradhana ele sita galewela pradhana margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | DL Stage 01 | Direct Labour | Rural Road |  |  | 36922235.4 | 36922235.4 | Awarded | 100% |  | 2025-10-19
RR/RDA/21/25/02 | 273 Idama Sita Katuwavila Main Road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | DL Stage 01 | Direct Labour | Rural Road |  |  | 61265788.54 | 61265788.54 | Awarded | 100% |  | 2025-09-13
RR/RDA/21/25/05 | Ketayam Kade asala sita Rampanam oya Dhakwa Margaya | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 01 | Direct Labour | Rural Road |  |  | 62573316.72 | 62573316.72 | Awarded | 100% |  | 2025-09-13
RR/RDA/20/25/21 | Pawithrapura Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | DL Stage 02 | Direct Labour | Rural Road |  |  | 32078244.1 | 32078244.1 | Awarded | 100%
RR/RDA/20/25/08 | Jaya mawatha sita Kaththaragama pansala dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Maradankadawala | DL Stage 02 | Direct Labour | Rural Road |  |  | 15557589.26 | 15557589.26 | Awarded | 100%
RR/RDA/20/25/09 | Padavi para Rambukepuwewa mansandiye sita Elapath wewa margaya dakwa margaya | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | DL Stage 02 | Direct Labour | Rural Road |  |  | 36917003.94 | 36917003.94 | Awarded | 100%
RR/RDA/21/25/01 | Ganangolla pradhana para sihala moola asala sita sirisena mahathage niwasa dakwa margaya | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | DL Stage 02 | Direct Labour | Rural Road |  |  | 34916075.79 | 34916075.79 | Awarded | 100% |  | 2026-01-22
RR/GA/21/25/CC/13 | Sathutugama Nidahas mawatha sanwardhanaya kireema | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 02 | Direct Labour | Rural Road |  |  | 53733874.7 | 53733874.7 | Awarded | 100% |  | 2026-01-20
RR/RDA/20/25/17 | Galwaduwawa Junction to Yaya 02 road of Thambuththegama Eppawala Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | DL Stage 03 | Direct Labour | Rural Road |  |  | 64398698.77 | 64398698.77 | Awarded | 100%
RR/RDA/20/25/24 | Konketiyawa School to Mayilankulama Vilage road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | DL Stage 03 | Direct Labour | Rural Road |  |  | 35296893.96 | 35296893.96 | Awarded | 100%
RR/RDA/21/25/AC/15 | Aralaganwila Allewewa road Balance Section | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | DL Stage 03 | Direct Labour | Rural Road |  |  | 51779609.7 | 51779609.7 | Awarded | 100%
RR/GA/21/25/CC/12 | Girithale janapadaya pasal mawatha carpet kara ithiri kotasa wana D.G. Jayasiri mahathage niwasa asala sita Akkara 15 handiya Jhon Raja mahathage niwasa dakwa margaya | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 03 | Direct Labour | Rural Road |  |  | 42689736.99 | 42689736.99 | Awarded | 100%
RR/RDA/21/25/16 | Diyabeduma to Jamburewela Road | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 03 | Direct Labour | Rural Road |  |  | 122382954.72 | 122382954.72 | Awarded | 100%
RR/RDA/21/25/28 | Development of the road Sathutugama nidahas Mawatha Balance Section from the house of Mr. Lahiru Madhusanka to the house of Mr. Navaratne in the area of ​​Giritale. | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 03 | Direct Labour | Rural Road |  |  | 32617373.22 | 29829563.55 | Awarded | 100%
RR/RDA/20/25/19 | Thalawa Tsunami junction to Indigaspathana road of Padeniya Anuradhapura Road | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | DL Stage 04 | Direct Labour | Rural Road |  |  | 64760087.22 | 64760087.22 | Awarded | 100%
RR/RDA/20/25/23 | Megichchawa Junction to Temple Road (Kulumeewakada Junction) | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Medawachchiya | DL Stage 04 | Direct Labour | Rural Road |  |  | 37500731.47 | 37500731.47 | Awarded | 100%
RR/RDA/20/26/23 | First phase of Priman Mawatha via the by-road behind Kumbichchankulama tank | North Central Province | Anuradhapura | North Central Province | Anuradhapura | Anuradhapura | DL Stage 04 | Direct Labour | Rural Road |  |  | 57387404.38 | 57387404.38 | Awarded | 0%
RR/RDA/21/25/25 | School Main Road (Old Jumma Mosque Road) | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Polonnaruwa | DL Stage 04 | Direct Labour | Rural Road |  |  | 43759842.36 | 43759842.36 | Awarded | 100%
RR/RDA/21/25/17 | Hingurakgoda Samupakara Road to Bubula | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 04 | Direct Labour | Rural Road |  |  | 174553300.63 | 174553300.63 | Awarded | 80%
RR/RDA/21/25/46 | Girithale janapadaya pasal mawatha starting Section | North Central Province | Polonnaruwa | North Central Province | Polonnaruwa | Habarana | DL Stage 04 | Direct Labour | Rural Road |  |  | 22545305.56 | 22545305.56 | Awarded | 100%
RR/RDA/18/25/12 | Anura Mahaththayalage niwase sita Nalalida dakwa kadurugaha ela dakwa margaya (Ganewatte) | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 01 | Direct Labour | Rural Road |  |  | 23242484.2 | 23242484.2 | Awarded | 100% |  | 2025-09-21
RR/RDA/18/25/05 | 158 Digana Grama niladari wasame 3 patumaga (vawa dakwa) (Yapahuwa) | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | DL Stage 01 | Direct Labour | Rural Road |  |  | 11443000 | 11774916.28 | Awarded | 100% |  | 2025-09-21
RR/RDA/18/25/23 | Horagasagara Nawarathna handiye sita Ihala kadigamuwa handiya dakwa margaya (Bingiriya) | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | DL Stage 01 | Direct Labour | Rural Road |  |  | 61588475.92 | 61588475.92 | Awarded | 100% |  | 2025-08-31
RR/RDA/18/25/99 | Rajanganaya reservoir to Parakumpura Junction (Left bank Road) | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | DL Stage 01 | Direct Labour | Rural Road |  |  | 312810182.55 | 312810182.55 | Awarded | 100%
RR/RDA/19/25/09 | Water front Mawatha (wennappuwa) | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | DL Stage 01 | Direct Labour | Rural Road |  |  | 12072583.1 | 12072583.1 | Awarded | 100% |  | 2025-09-21
RR/RDA/19/25/03 | Nawagattegama Rohala Pare sita Thapal Karyalaya Dakwa margaya (Nawagattegama) | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | DL Stage 01 | Direct Labour | Rural Road |  |  | 23512239.79 | 23512239.79 | Awarded | 100% |  | 2025-09-21
RR/RDA/18/25/06 | Walaliya Piduruwellewa road to the middle of the village | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | DL Stage 02 | Direct Labour | Rural Road |  |  | 19537451.95 | 19431074.96 | Awarded | 100%
RR/RDA/18/25/17 | No. 245 from near Jeevan Lasantha's house no. 37 Development of the main road up to Mr. Nihal's house with five (5) side roads. | North Western Province | Kurunegala | North Western Province | Kurunegala | Kuliyapitiya | DL Stage 02 | Direct Labour | Rural Road |  |  | 51911526.67 | 51911526.67 | Awarded | 100% |  | 2025-10-30
RR/RDA/18/25/21 | Wattakkawatta Road - Paving of Road (ABC Paving) from near Kelimune Pustalaya. | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 02 | Direct Labour | Rural Road |  |  | 39422351.32 | 39422351.32 | Awarded | 100% |  | 2025-09-10
RR/RDA/18/25/103 | Wellawa Thalatuwa Junction to Gepellawa Road | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 02 | Direct Labour | Rural Road |  |  | 31387050.89 | 31387050.89 | Awarded | 100% |  | 2025-09-30
RR/RDA/18/25/105 | Thihawa Junction to Mailamada | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 02 | Direct Labour | Rural Road |  |  | 33866057.61 | 33866057.61 | Awarded | 100%
RR/RDA/19/25/02 | Concrete development of the road from Hopper Kada junction to Elu Farm. | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | DL Stage 02 | Direct Labour | Rural Road |  |  | 33229489.54 | 33229489.54 | Awarded | 100%
RR/RDA/19/25/07 | Development of the road from near Kalegama School to Erungwila. | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | DL Stage 02 | Direct Labour | Rural Road |  |  | 55009126.14 | 55009126.14 | Awarded | 100%
RR/RDA/19/25/25 | Development of Mada Koswadiya Bogaha Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | DL Stage 03 | Direct Labour | Rural Road |  |  | 25235881.81 | 25235881.81 | Awarded | 100%
RR/RDA/18/25/314 | Road from Nugawela Junction in Walagane to Maspotha Crematorium via Temple | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 04 | Direct Labour | Rural Road |  |  | 41562875.57 | 41562875.57 | Awarded | 100%
RR/RDA/18/25/309 | From near Kongaha in Waudagama on the Katupotha Waudagama Wanduressegama road near Potuwewa Cemetery. | North Western Province | Kurunegala | North Western Province | Kurunegala | Maho | DL Stage 04 | Direct Labour | Rural Road |  |  | 45888080.58 | 45888080.58 | Awarded | 87%
RR/RDA/18/25/317 | Lakee Land Road in Wilattawa Division | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 04 | Direct Labour | Rural Road |  |  | 9799762.91 | 9799762.91 | Awarded | 100%
RR/RDA/18/25/319 | Kabaledevgama 3rd Lane and 4 Lane in Kaballewa Division of Kaballewa Division | North Western Province | Kurunegala | North Western Province | Kurunegala | Kurunegala | DL Stage 04 | Direct Labour | Rural Road |  |  | 21709247.87 | 21709247.87 | Awarded | 100%
RR/RDA/18/25/311 | Road from Kopihena Junction to Dangolla in Damunugala Division of Piduruwella Division | North Western Province | Kurunegala | North Western Province | Kurunegala |  | DL Stage 04 | Direct Labour | Rural Road |  |  | 55494114.67 | 55494114.67 | Awarded | 100%
RR/RDA/18/25/312 | Junction in front of Narampola Thoraya Muslim College to Budanapartiya Road via Narampola | North Western Province | Kurunegala | North Western Province | Kurunegala |  | DL Stage 04 | Direct Labour | Rural Road |  |  | 43368925.99 | 43368925.99 | Awarded | 100%
RR/RDA/19/25/36 | Renovation of Warusavithana Laboratory Road | North Western Province | Puttalam | North Western Province | Chilaw | Chilaw | DL Stage 04 | Direct Labour | Rural Road |  |  | 19592732.06 | 19592732.06 | Awarded | 65%
RR/RDA/19/25/35 | Carpeting & Development of Kolithatissa Mawatha | North Western Province | Puttalam | North Western Province | Chilaw | Puttalam | DL Stage 04 | Direct Labour | Rural Road |  |  | 10359335.01 | 10359335.01 | Awarded | 100%
RR/RDA/10/25/21 | 3rd Cross Street | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | DL Stage 01 | Direct Labour | Rural Road |  |  | 11072958.55 | 11072958.55 | Awarded | 100% |  | 2025-09-21
RR/RDA/10/25/17 | College Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | DL Stage 01 | Direct Labour | Rural Road |  |  | 35288918.91 | 35288918.91 | Awarded | 100% |  | 2025-09-21
RR/RDA/12/25/44 | Menicfarm school road (0.5km) (NVVPE97) | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | DL Stage 01 | Direct Labour | Rural Road |  |  | 11100861.98 | 11100861.98 | Awarded | 100% |  | 2025-09-21
RR/RDA/13/25/09 | Aninchiyankulam 2nd Lane MUTE095 | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | DL Stage 01 | Direct Labour | Rural Road |  |  | 46445947.77 | 46445947.77 | Awarded | 100% |  | 2025-09-21
RR/RDA/11/25/12 | Renovation of Chemmantheevu 4th Cross Street. | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | DL Stage 01 | Direct Labour | Rural Road |  |  | 25184287.62 | 25184287.62 | Awarded | 100% |  | 2025-09-21
RR/RDA/10/25/12 | Anaikoddai - Kakaithivu Road | Northern Province | Jaffna | Northern Province | Jaffna | Jaffna | DL Stage 02 | Direct Labour | Rural Road |  |  | 34361480.4 | 34361480.4 | Awarded | 100% |  | 2025-11-10
RR/RDA/10/25/26 | VC Road No 15 | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | DL Stage 02 | Direct Labour | Rural Road |  |  | 23825730.98 | 23825730.98 | Awarded | 100%
RR/RDA/12/25/06 | Paalavinayagar road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | DL Stage 02 | Direct Labour | Rural Road |  |  | 18688450.91 | 17373382.99 | Awarded | 100% |  | 2025-11-13
RR/RDA/13/25/04 | Suthanthirapuram Main Road Package 1 | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | DL Stage 02 | Direct Labour | Rural Road |  |  | 110821121.4 | 110821121.4 | Awarded | 100% |  | 2025-11-12
RR/RDA/11/25/17 | Alakkatu Internal Road 5 | Northern Province | Mannar | Northern Province | Vavuniya | Mannar | DL Stage 02 | Direct Labour | Rural Road |  |  | 25141870.23 | 25141870.23 | Awarded | 100% |  | 2025-12-13
RR/RDA/14/25/05 | Kanakapuram school behind road | Northern Province | Kilinochchi | Northern Province | Mullaitivu | Kilinochchi | DL Stage 02 | Direct Labour | Rural Road |  |  | 43582937.83 | 43582937.83 | Awarded | 100%
RR/RDA/13/25/05 | Suthanthirapuram Main Road Package 2 | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | DL Stage 03 | Direct Labour | Rural Road |  |  | 63852534.37 | 63852534.37 | Awarded | 100% |  | 2025-11-30
RR/RDA/12/25/11 | Madeenanagar road | Northern Province | Vavuniya | Northern Province | Vavuniya | Vavuniya | DL Stage 03 | Direct Labour | Rural Road |  |  | 21394474.49 | 21394474.49 | Awarded | 100% |  | 2025-11-01
RR/RDA/13/25/02 | Kokkilai Estuary fishing village Road | Northern Province | Mullaitivu | Northern Province | Mullaitivu | Mullaitivu | DL Stage 04 | Direct Labour | Rural Road |  |  | 26445698.08 | 26445698.08 | Awarded | 100%
RR/RDA/10/25/23 | Oorany Kudiyetta thidda Veethy | Northern Province | Jaffna | Northern Province | Jaffna | Point Pedro | DL Stage 04 | Direct Labour | Rural Road |  |  | 12148965.86 | 12148965.86 | Awarded | 100%
RR/RDA/25/24/07 | Godawela Wela Middle Road (Const. side walls) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | DL Stage 01 | Direct Labour | Rural Road |  |  | 21801991.89 | 21801991.89 | Awarded | 100% |  | 2025-09-21
RR/RDA/25/24/15 | D03 Road Near the Yaka Poll | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | DL Stage 01 | Direct Labour | Rural Road |  |  | 52683572.48 | 52683572.48 | Awarded | 100% |  | 2025-09-21
RR/RDA/25/24/08 | From Mr.Ranjth's House to Mr.Premasiri's House in Maduwanwela Janapadaya 2nd Lane Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | DL Stage 01 | Direct Labour | Rural Road |  |  | 39030233.29 | 39030233.29 | Awarded | 100% |  | 2025-09-21
RR/RDA/25/25/16 | Ma dola Jansalu Mawatha Rathnapuara Colombo Road to Welangalla Maha ela Bridge | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | DL Stage 01 | Direct Labour | Rural Road |  |  | 37225336.73 | 40604043.84 | Awarded | 100% |  | 2025-09-25
RR/RDA/25/25/17 | Na gahamula Junction to 28 Janapadaya Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | DL Stage 01 | Direct Labour | Rural Road |  |  | 30370502.56 | 30370502.56 | Awarded | 100% |  | 2025-09-21
RR/RDA/25/24/12 | Siyabalagahayata Junction to Blue Mountain Housing Complex Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | DL Stage 02 | Direct Labour | Rural Road |  |  | 23571917.19 | 23571917.19 | Awarded | 100% |  | 2025-10-10
RR/RDA/25/24/09 | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Pelmadulla | DL Stage 02 | Direct Labour | Rural Road |  |  | 33251409.79 | 33251409.79 | Awarded | 100% |  | 2025-11-15
RR/RDA/25/25/18 | Concreting Beragala Army Camp to Beragala 3way Junction VIA Niyadagala | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Kegalle | DL Stage 02 | Direct Labour | Rural Road |  |  | 34687905.11 | 34687905.11 | Awarded | 100% |  | 2025-10-31
RR/RDA/25/25/21 | Kalupahanawaththa Road | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | DL Stage 02 | Direct Labour | Rural Road |  |  | 28324647.09 | 28324647.09 | Awarded | 100% |  | 2025-11-30
RR/RDA/25/24/11 | Cinema Hall Road to Dooliyangodella Pitawaththa Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Ratnapura | DL Stage 03 | Direct Labour | Rural Road |  |  | 27759052.36 | 27759052.36 | Awarded | 100% |  | 2025-11-30
RR/RDA/25/25/30 | Developing the dilapidated section of the lower part of the Pallebage road to the Watte junction | Sabaragamuwa Province | Kegalle | Sabaragamuwa Province | Kegalle | Ruwanwella | DL Stage 03 | Direct Labour | Rural Road |  |  | 6992158.2 | 6992158.2 | Awarded | 100% |  | 2025-10-10
RR/RDA/25/24/35 | Ilumba Kanda Road from Milinduthalawa Temple | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | DL Stage 04 | Direct Labour | Rural Road |  |  | 24709638.71 | 24709638.71 | Awarded | 30% |  | 2026-03-31
RR/RDA/25/24/17 | Pahalawaththa to Batahenkanda Road | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | DL Stage 04 | Direct Labour | Rural Road |  |  | 112040241.38 | 112040241.38 | Awarded | 10% |  | 2026-03-31
RR/RDA/25/24/19 | Wijeriya Iththekanda Margaya Sanwardanaya Kirima | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | DL Stage 04 | Direct Labour | Rural Road |  |  | 72158727.69 | 72158727.69 | Awarded | 35% |  | 2026-03-31
RR/RDA/25/24/20 | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) | Sabaragamuwa Province | Ratnapura | Sabaragamuwa Province | Ratnapura | Embilipitiya | DL Stage 04 | Direct Labour | Rural Road |  |  | 126132479.8 | 126132479.8 | Awarded | 15% |  | 2026-03-31
RR/RDA/08/25/Si | Sithulpauwa Rajamaha Viharaye Katharagama Para | Southern Province | Hambantota | Southern Province | Hambantota | Hambantota | DL Stage 01 | Direct Labour | Rural Road |  |  | 3969390.34 | 3969390.34 | Awarded | 100% |  | 2025-08-15
RR/RDA/07/25/07 | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 01 | Direct Labour | Rural Road |  |  | 27520890.33 | 27520890.73 | Awarded | 100% |  | 2025-08-22
RR/RDA/07/25/16 | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima | Southern Province | Galle | Southern Province | Galle | Hiniduma | DL Stage 01 | Direct Labour | Rural Road |  |  | 30597079.78 | 30597079.78 | Awarded | 100% |  | 2025-08-31
RR/RDA/25/08/07 | Ovitigamuwa Alahenpita margaya Sanwardanaya Kirima (RDA yatathe Idikirima Arambha kara atharamaga nawatha etha) | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 01 | Direct Labour | Rural Road |  |  | 29034089.99 | 29034089.99 | Awarded | 100% |  | 2025-08-22
RR/RDA/25/08/01 | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara | Southern Province | Matara | Southern Province | Matara | Deniyaya | DL Stage 01 | Direct Labour | Rural Road |  |  | 78061393.44 | 78061393.44 | Awarded | 100% |  | 2025-10-15
RR/RDA/08/25/04 | Vigamuwa Pattiyapola Road from Vigamuwa School | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | DL Stage 01 | Direct Labour | Rural Road |  |  | 74802039.66 | 74802039.66 | Awarded | 100% |  | 2025-09-15
RR/RDA/09/25/01 | Karametiya Road | Southern Province | Hambantota | Southern Province | Hambantota | Hambantota | DL Stage 01 | Direct Labour | Rural Road |  |  | 74446690.12 | 74446690.12 | Awarded | 100% |  | 2025-09-15
RR/RDA/07/25/03 | Wackwella Palama asala sita aranbe handiya dakwa Margaya | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 02 | Direct Labour | Rural Road |  |  | 26781909.97 | 26781909.97 | Awarded | 100% |  | 2025-09-15
RR/RDA/07/25/04 | Galwehera C.P. the Silva Mawatha Carpet kirima | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 02 | Direct Labour | Rural Road |  |  | 30571235.09 | 30571235.08 | Awarded | 100% |  | 2025-10-30
RR/RDA/07/25/18 | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima | Southern Province | Galle | Southern Province | Galle | Hiniduma | DL Stage 02 | Direct Labour | Rural Road |  |  | 27525465.5 | 27525465.5 | Awarded | 100% |  | 2025-10-30
RR/RDA/25/08/06 | Samarasinghe Mawathw Ithiri Kotasa Sanwardanaya Kirima | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 02 | Direct Labour | Rural Road |  |  | 16851257.35 | 17005961.71 | Awarded | 100% |  | 2025-10-30
RR/RDA/25/08/11 | Thambagala Margaya Sanwardanaya Kirima (Highway pitawime sthanayen arambha vi Pradeepa Mahathmiyage Niwasa dakwa Kotasa) | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 02 | Direct Labour | Rural Road |  |  | 9425286.29 | 9396645.17 | Awarded | 100% |  | 2025-09-15
RR/RDA/09/25/02 | Wam Iwura Janawasa Margaya | Southern Province | Hambantota | Southern Province | Hambantota | Hambantota | DL Stage 02 | Direct Labour | Rural Road |  |  | 37666563.49 | 37666563.49 | Awarded | 100% |  | 2025-10-30
RR/RDA/08/25/23 | Epitakaduwa Krishantha Senarath Yapa Road (Eptakaduwa Budu medura to Mr. LG Jagath Yapa home) | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 03 | Direct Labour | Rural Road |  |  | 7231417.22 | 7231417.22 | Awarded | 100% |  | 2025-11-16
RR/RDA/07/25/14 | Moonugoda Road | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 03 | Direct Labour | Rural Road |  |  | 21211506.6 | 21211506.6 | Awarded | 100% |  | 2025-11-16
RR/RDA/08/25/05 | Koggalla bus stand to Sooriyawewa Road | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | DL Stage 03 | Direct Labour | Rural Road |  |  | 127573213.52 | 127573213.52 | Awarded | 95% |  | 2025-12-16
RR/RDA/07/25/22 | Asphalting Meepawala henegewaththa road | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 04 | Direct Labour | Rural Road |  |  | 21395564.1 | 21395564.1 | Awarded | 100% |  | 2026-02-27
RR/RDA/07/25/21 | Asphalting Newungala Na tree to Bedimeda road | Southern Province | Galle | Southern Province | Galle | Hiniduma | DL Stage 04 | Direct Labour | Rural Road |  |  | 35369824.16 | 35369824.16 | Awarded | 100% |  | 2026-03-20
RR/RDA/07/25/01 | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) | Southern Province | Galle | Southern Province | Galle | Galle | DL Stage 04 | Direct Labour | Rural Road |  |  | 76680545.16 | 76680545.16 | Awarded | 98%
RR/RDA/08/25/22 | Kirinda Roundabout Road with drainages | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 04 | Direct Labour | Rural Road |  |  | 23083588.28 | 23083588.28 | Awarded | 100%
RR/RDA/08/25/02 | Andaledduwa Road | Southern Province | Matara | Southern Province | Matara | Matara | DL Stage 04 | Direct Labour | Rural Road |  |  | 24533049.28 | 24533049.28 | Awarded | 100%
RR/RDA/09/25/12 | Development of the road from Lunugamwehera Jadura Lake to Udaeva | Southern Province | Hambantota | Southern Province | Hambantota | Hambantota | DL Stage 04 | Direct Labour | Rural Road |  |  | 66506406.57 | 66506406.57 | Awarded | 92%
RR/RDA/09/25/06 | Raluwa main road | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | DL Stage 04 | Direct Labour | Rural Road |  |  | 17377865.99 | 17377865.99 | Awarded | 70%
RR/RDA/09/25/07 | Carpeting Dabewelena Gravel Road | Southern Province | Hambantota | Southern Province | Hambantota | Hambantota | DL Stage 04 | Direct Labour | Rural Road |  |  | 54766473.95 | 54766473.95 | Awarded | 98% |  | 2025-12-31
RR/RDA/09/25/14 | Development of road near Olu ara School | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | DL Stage 04 | Direct Labour | Rural Road |  |  | 101801692.33 | 101801692.33 | Awarded | 90%
RR/RDA/09/25/10 | Development of Valasmulla Pallekanda road from 3 km post to 5 km post | Southern Province | Hambantota | Southern Province | Hambantota | Tangalle | DL Stage 04 | Direct Labour | Rural Road |  |  | 84525263.23 | 84525263.23 | Awarded | 95%
RR/RDA/22/25/32 | Asphalt laying and Development of Haddaththawa 80 Acre road | Uva Province | Badulla | Uva Province | Badulla | Mahiyanganaya | DL Stage 01 | Direct Labour | Rural Road |  |  | 93242250.14 | 93242250.14 | Awarded | 100% |  | 2025-09-15
RR/RDA/22/25/03 | Hubaslinda Meda Margaya | Uva Province | Badulla | Uva Province | Badulla | Mahiyanganaya | DL Stage 01 | Direct Labour | Rural Road |  |  | 19159838.84 | 19159838.84 | Awarded | 100% |  | 2025-09-25
RR/RDA/22/25/16 | Dameria Handiye sita wathu Karyalaya Dakwa Margaya | Uva Province | Badulla | Uva Province | Badulla | Badulla | DL Stage 01 | Direct Labour | Rural Road |  |  | 12215323.92 | 12215323.92 | Awarded | 100% |  | 2025-08-15
RR/RDA/22/26/01 | Rajamawatha Road | Uva Province | Badulla | Uva Province | Badulla | Bandarawela | DL Stage 01 | Direct Labour | Rural Road |  |  | 15077652.84 | 15077652.84 | Awarded | 100% |  | 2025-09-25
RR/RDA/23/25/01 | Puwakgoda Uramada Margaya K.M.Thilak Bandara Mahathage niwasa idiripita sita ema Margayema R.M.Punchi Nona Mahathmiyage Niwasa Dakwa Margaya | Uva Province | Monaragala | Uva Province | Monaragala | Bibile | DL Stage 01 | Direct Labour | Rural Road |  |  | 64599474.91 | 64599474.91 | Awarded | 100% |  | 2025-09-15
RR/RDA/23/25/04 | Walawegaga Asala (Nildiya Mankada) Sita Udawalawa Bant eka Dakwa | Uva Province | Monaragala | Uva Province | Monaragala | Monaragala | DL Stage 01 | Direct Labour | Rural Road |  |  | 74104374.63 | 74104374.63 | Awarded | 100% |  | 2025-09-15
RR/RDA/22/25/13 | Peessa Pradana Margaye Abalan wu Ellanda Marga Kotasa | Uva Province | Badulla | Uva Province | Badulla | Badulla | DL Stage 02 | Direct Labour | Rural Road |  |  | 13192586.35 | 13192586.35 | Awarded | 100% |  | 2025-10-30
RR/RDA/22/25/10 | Kosgolla Edaru Ulpatha Margaya | Uva Province | Badulla | Uva Province | Badulla | Bandarawela | DL Stage 02 | Direct Labour | Rural Road |  |  | 13085885.7 | 13085885.7 | Awarded | 100% |  | 2025-10-30
RR/RDA/23/25/03 | Liyangolla Lolla Margaya | Uva Province | Monaragala | Uva Province | Monaragala | Bibile | DL Stage 02 | Direct Labour | Rural Road |  |  | 38879897 | 38879897 | Awarded | 100% |  | 2025-10-30
RR/RDA/23/25/02 | Uduwara wewa Handiya sita Athula Margaya | Uva Province | Monaragala | Uva Province | Monaragala | Bibile | DL Stage 02 | Direct Labour | Rural Road |  |  | 34079767.34 | 34079767.34 | Awarded | 100% |  | 2025-10-30
RR/RDA/01/25/11 | Vijitha Salawa asala sita Kothalawala Vidyalaya Asalin Gothami Viharaya dakva Margaya | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 01 | Direct Labour | Rural Road |  |  | 17512654.33 | 17512654.33 | Awarded | 100% |  | 2025-08-15
RR/RDA/01/25/07 | 428/B Ihala Kosgama Grama Niladhari Wasame Praja Shalawa Pahala Margaya | Western Province | Colombo | Western Province | Colombo | Avissawella | DL Stage 01 | Direct Labour | Rural Road |  |  | 51557606.95 | 51557606.95 | Awarded | 100% |  | 2025-10-17
RR/RDA/02/25/02 | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). | Western Province | Gampaha | Western Province | Gampaha | Gampaha | DL Stage 01 | Direct Labour | Rural Road |  |  | 10523274.77 | 10523274.77 | Awarded | 100% |  | 2025-08-15
RR/RDA/02/25/01 | Heendeniya Dumriya Sthanaya Dakwa Margaya | Western Province | Gampaha | Western Province | Gampaha | Nittambuwa | DL Stage 01 | Direct Labour | Rural Road |  |  | 13144147.11 | 13144147.11 | Awarded | 100% |  | 2025-07-09
RR/RDA/02/25/04 | Delpe Kadawara sita Nelumwaththa margaya arambaye sita Dewadasa mahathage niwasa dakwa Margaya | Western Province | Gampaha | Western Province | Gampaha | Negombo | DL Stage 01 | Direct Labour | Rural Road |  |  | 26006255.54 | 26006255.54 | Awarded | 100% |  | 2025-09-10
RR/RDA/03/25/01 | Asphalting Samagipura Road (LECO office to Maha ela) | Western Province | Kalutara | Western Province | Kalutara | Kalutara | DL Stage 01 | Direct Labour | Rural Road |  |  | 25713214.4 | 25713214.4 | Awarded | 100% |  | 2025-09-21
RR/RDA/03/25/04 | Development of the Kotupathgoda road by asphalting | Western Province | Kalutara | Western Province | Kalutara | Horana | DL Stage 01 | Direct Labour | Rural Road |  |  | 32439574.76 | 32439574.76 | Awarded | 100% |  | 2025-09-21
RR/RDA/03/25/36 | 10 Mw T Jayarathne mahathge niwas asala concrete kara nawatha ati sthanaya sita nawa margaya desata | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | DL Stage 01 | Direct Labour | Rural Road |  |  | 34917696.41 | 34917696.41 | Awarded | 100% |  | 2025-09-21
RR/RDA/01/25/02 | Paving and developing the road from North Borella Ganga Lower Vivekaramaya Temple to Siwali Lane No. 241/35D. | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 02 | Direct Labour | Rural Road |  |  | 3636186.59 | 3636186.59 | Awarded | 100% |  | 2025-09-17
RR/RDA/01/25/06 | Development of Rambutan gahamula Suramya Mawatha using carpet in Magammana East Grama Niladhari Domain | Western Province | Colombo | Western Province | Colombo | Avissawella | DL Stage 02 | Direct Labour | Rural Road |  |  | 16341118.27 | 16341118.27 | Awarded | 100% |  | 2025-11-07
RR/RDA/03/25/07 | Carpeting of Shekmadara Road | Western Province | Kalutara | Western Province | Kalutara | Kalutara | DL Stage 02 | Direct Labour | Rural Road |  |  | 14674228.65 | 14674228.65 | Awarded | 100% |  | 2025-08-07
RR/RDA/01/25/17 | Access road to Polgasowita Dikhena Aranya | Western Province | Colombo | Western Province | Colombo | Avissawella | DL Stage 03 | Direct Labour | Rural Road |  |  | 7965231.1 | 7965231.1 | Awarded | 100% |  | 2025-11-15
RR/RDA/02/25/07 | Road near Ozon Educational Institiute | Western Province | Gampaha | Western Province | Gampaha | Gampaha | DL Stage 03 | Direct Labour | Rural Road |  |  | 12058540.61 | 12058540.61 | Awarded | 100%
RR/RDA/03/25/11 | Jilani road in Darga Town | Western Province | Kalutara | Western Province | Kalutara | Kalutara | DL Stage 03 | Direct Labour | Rural Road |  |  | 14759196.13 | 14759196.13 | Awarded | 100% |  | 2025-11-17
RR/RDA/03/25/13 | Morapitiya Aluth Mawatha to 1st mile post via Rankoth lane | Western Province | Kalutara | Western Province | Kalutara | Agalawatta | DL Stage 03 | Direct Labour | Rural Road |  |  | 38713954.65 | 38713954.65 | Awarded | 100%
RR/RDA/01/25/16 | Bangalawa Road from 01st Gate to 04th Gate | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 04 | Direct Labour | Rural Road |  |  | 18170451.82 | 18170451.82 | Awarded | 100%
RR/RDA/02/25/20 | St. Lazarus Road (Depot Road) | Western Province | Gampaha | Western Province | Gampaha | Negombo | DL Stage 04 | Direct Labour | Rural Road |  |  | 23521864.99 | 26943025.76 | Awarded | 100%
RR/RDA/03/25/20 | Development of Gemunu Mawatha by laying 500 meters of carpet | Western Province | Kalutara | Western Province | Kalutara | Kalutara | DL Stage 04 | Direct Labour | Rural Road |  |  | 12547527.78 | 12547527.78 | Awarded | 100% |  | 2026-03-12
RR/RDA/01/25/21 | Development of Yakala Cemetery Road up to Welihinda Bridge by carpeting | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 04 | Direct Labour | Rural Road |  |  | 9242749.23 | 9242749.23 | Awarded | 5%
RR/RDA/01/25/24 | Development of the road from the beginning of the Horahena road from Wanaguru Mawatha in the Hokandara East Division to the Hokandara Pasmanhandiya with a carpet | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 04 | Direct Labour | Rural Road |  |  | 3140831.06 | 3140831.06 | Awarded | 100%
RR/RDA/01/26/10KM/01 | Development of Honnatthara South Kudamadhuwa Road, Moonamalgahawatte Road up to House No. 138/3 by laying carpet and installing drains. | Western Province | Colombo | Western Province | Colombo | Avissawella | DL Stage 04 | Direct Labour | Rural Road |  |  | 20626056.18 | 20626056.18 | Awarded | 5%
RR/RDA/01/26/10KM/04 | Carpeting and development of Vijithapura Liyanage Mawatha and 3rd Lane | Western Province | Colombo | Western Province | Colombo | Colombo | DL Stage 04 | Direct Labour | Rural Road |  |  | 1560361.91 | 1560361.91 | Awarded | 100%
RR/RDA/01/26/01 | Major Alagiyawanna Road to Welivita Road | Western Province | Colombo | Western Province | Colombo |  | DL Stage 04 | Direct Labour | Rural Road |  |  |  | 39908152.7 | Awarded | 5%
RR/RDA/01/26/05 | Malabe Chandrika Kumarathunga Road | Western Province | Colombo | Western Province | Colombo |  | DL Stage 04 | Direct Labour | Rural Road |  |  |  | 539508513.37 | Awarded | 5%