## Weekly Progress
Weekly Physical Progress & Expenditure
Date: 2026-11-04
# | Contract No | Contract Name | Contractor | Days Left | Planned % | Prev Week Progress 2026-10-30 | Progress Up To This Week 2026-11-06 | Prev Week Expenditure (LKR Mn, incl. VAT) | Expenditure Up To This Week (LKR Mn, incl. VAT) | Expenditure Source | Weekly Spend (LKR Mn, incl. VAT)
1 | RR/RDA/04/25/13/CP/KY | Gonaala Pasala Asala Sita Kubukkadura Athuru Margayak Wana Gurumada Margaya | Dharshana Construction | 75 Days in Delay | 100% |  |  |  | 0 | IPC
2 | RR/RDA/04/25/15/CP/KY | Madolkale sita Huluganga dakwa yana athuru margaye Bandaranayakapura gam kotasata adala Margaya | UGD Constructions | Completed | 100% |  | 100% |  | 0 | IPC
3 |  | Palawa ihala meda Wijitha mawatha Waliyangadeniya margaya yakarana athuru Margaya | Galahitiyawa Builders | Completed | 100% |  | 100% |  | 0 | IPC
4 | RR/RDA/04/25/17/CP/KY | Nuganga Margaya | Weebedda Construction | Completed | 100% |  | 100% |  | 0 | IPC
5 | RR/RDA/04/25/19/CP/KY | Mulgama viduhala Asala sita lewalan dakwa | The Wise Lanka Construction Company (Pvt) Ltd | 294 Days in Delay | 100% |  |  |  | 0 | IPC
6 | RR/RDA/04/25/20/CP/KY | Carpeting road Ratemulla to Wendesiwaththa End | Wiscon (Pvt) Ltd | 272 Days in Delay | 100% |  |  |  | 0 | IPC
7 | RR/RDA/04/25/21/CP/KY | Galaha group sita finas kotasa Pahalagama-Ihalagama haraha nawa rohala dakwa Margaya | UGD Constructions | 308 Days in Delay | 100% |  |  |  | 0 | IPC
8 | RR/RDA/04/25/22/CP/KY | Rambukwella viharasthanaya asala sita Dodamgolla Rambukwella nagenhira haraha Udispaththuwa dakwa diwena Margaya | The Wise Lanka Construction Company (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
9 | RR/RDA/04/25/23/CP/KY | Minuwangamuwa gammada margaye Aberathne mahathage niwasa asala sita Abesinha Banda mahathage Niwasa dakwa | The Wise Lanka Construction Company (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
10 | RR/RDA/04/25/24/CP/KY | Galamuduna gamata pivisena Margaya | NAGMA ENGINEERING (PVT) LTD | — | 99% |  |  |  | 0 | IPC
11 | RR/RDA/04/25/25/CP/KY | Delgasthenna Road | NAGMA ENGINEERING (PVT) LTD | 182 Days in Delay | 100% |  |  |  | 0 | IPC
12 | RR/RDA/04/25/27/CP/KY | Dadahogama pitiye gedara pathibami sahitha Margaya | Nimsara Construction & Holdings (PVT) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
13 | RR/RDA/04/25/28/CP/KY | Dehideniya sita Hedeniya dakwa Margaya | Senerath Engineering (pvt) Ltd | 285 Days in Delay | 100% |  |  |  | 0 | IPC
14 | RR/RDA/04/25/31/CP/KY | Shantha Janapada Village middle road | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
15 | RR/RDA/04/25/31(1)/CP/KY | Paththunupitiya School road to Gampola Road through Pallegama Anguruwala | Central Engineering Services Pvt Ltd. (CESL) | 120 Days in Delay | 100% |  |  |  | 0 | IPC
16 | RR/RDA/04/25/32/CP/KY | Pilawala Navodya pasala asala sita Nelumpathhinna pansala dakwa margaya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
17 | RR/RDA/04/25/33/CP/KY | New forest kotase Jana Udana gammana margaya | The Wise Lanka Construction Company (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
18 | RR/RDA/04/25/34/CP/KY | Liyandeniya wewa margya | Nimsara Construction & Holdings (PVT) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
19 | RR/RDA/04/25/35/CP/KY | Gamunupura Gonawatta pradana margaye Gamunupura pera pasala asala sita idiriyata pradana margaya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
20 | RR/RDA/04/25/41/CP/KY | Karyala handiya pahala margya concrete kirima | UGD Constructions | 294 Days in Delay | 100% |  |  |  | 0 | IPC
21 | RR/RDA/04/25/43/CP/KY | Dodamgolla kowila asla sita hindu susana boomiya dakwa margaya | The Wise Lanka Construction Company (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
22 |  | Ambakote Road | Dharshana Construction | No schedule |  |  | 5% |  | 0 | IPC
23 | RR/RDA/04/25/52/CP/KY | Bokalawela Road from Hapugoda Junction to Ranawana (Drinage System Development and Road) | Senerath Engineering (pvt) Ltd | 74 Days in Delay | 100% |  |  |  | 0 | IPC
24 | RR/RDA/04/25/53/CP/KY | Road from Amuvandeniya to Magurudeniya (development of the drainage and carpeting of the road) | Tiasa Construction (Pvt) Ltd | 57 Days in Delay |  |  | 40% |  | 0 | IPC
25 |  | Development of the Dolapihilla road from Navinnapitiya via Deldeniya | Ajith Construction | 30 Days in Delay | 100% |  |  |  | 0 | IPC
26 |  | Development of entrance roads, pedestrian rest areas and parking areas of the Sri Dalada Maligawa premises | Southern Group Civil Construction (Pvt) Ltd. | 89 Days in Delay | 100% |  |  |  | 0 | IPC
27 |  | Renovation of road Haidri estate to Barcapal | Ajith Construction | 16 days left | 99.2% |  |  |  | 0 | IPC
28 | RR/RDA/05/25/01/CP/MTL | Moragahamada pasala asalin arambhawa Rajagammana gama madin Madawala adawala para dakwa pradana athuru Margaya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
29 | RR/RDA/05/25/02/CP/MTL | Lakshahena maragaya Mathalapitiya margaye sita Lakshahena Kosgolla dakwa Margaya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
30 | RR/RDA/05/25/04/CP/MTL | Aiththaliyadda sita Porcilain eka dakwa Margaya | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
31 | RR/RDA/05/25/07/CP/MTL | Uladawa Mansandiye sita Homapola Janapadaye Saukkaya Maddayasthanaya dakawa Diwena Udurmpelessa thek Diwena Margaya Kapat Kirima | Ajith Construction | No schedule |  |  | 0% |  | 0 | IPC
32 | RR/RDA/05/25/09/CP/MTL | Ilukkumbura Samurdhi karyalaya asala Patti ela pilama dakwa | Pragathi Civil Contractor | 285 Days in Delay | 100% |  |  |  | 0 | IPC
33 | RR/RDA/05/25/10/CP/MTL | Sonuththa pradana margaye Shailatharamaya idiriye sita 80 yaya dakwa | NAGMA ENGINEERING (PVT) LTD | 191 Days in Delay | 100% |  |  |  | 0 | IPC
34 | RR/RDA/05/25/11/CP/MTL | Hunukete sita Elagala dakwa Pradana Margaya | Senerath Engineering (pvt) Ltd | 223 Days in Delay |  |  | 50% |  | 0 | IPC
35 | RR/RDA/05/25/12/CP/MTL | A9 pare Kist biscuit factoryata meha sithuwam kanda board eka (savikara athi) Nalanda wattata yana para | Senevirathna Enterprise | Completed | 100% |  | 100% |  | 0 | IPC
36 | RR/RDA/05/25/13/CP/MTL | A9 pare Elik Aluvihare niwasa lagin arambha wee Hunugalwala dakwa margaya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
37 | RR/RDA/05/25/16/CP/MTL | Dangan pedesa Mithragama margya Kurunegala margaye sita Mithragama | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
38 | RR/RDA/05/25/17/CP/MTL | Ambagastenna to gurubebila temple via Polwaththa nikawella | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
39 | RR/RDA/05/25/18/CP/MTL | Bandarapola Ulpathapitiya haraha Kiula margaya | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
40 | RR/RDA/05/25/19/CP/MTL | Katudeniya bahukarya godanagilla asala Hettiyawatta dakwa margaya | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
41 | RR/RDA/05/25/20/CP/MTL | Harispattuwa margaya arambaka mansandiye sita Thusitha maranadara godanagilla dakwa | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
42 | RR/RDA/05/25/22/CP/MTL | Sigirimulla sita Mailetthewa Aluthyaya dakwa margaya | Asiri Contractor and Designers | Completed | 100% |  | 100% |  | 0 | IPC
43 | RR/RDA/05/25/24/CP/MTL | Pahala Hombawa palama dakwa Daduwagolla kanaththa langa sita | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
44 | RR/RDA/05/25/26/CP/MTL | Pallepola saukya karyalaye sita ekamuthugama dakwa margaya | Jayaru Engineering (Pvt) Ltd | 308 Days in Delay |  |  | 60% |  | 0 | IPC
45 | RR/RDA/05/25/27/CP/MTL | Welemulla sita Kandewaththa | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
46 | RR/RDA/05/25/29/CP/MTL | Pitawala handiye sita pitawala desata | Lahiru Construction & Consultants (PVT) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
47 | RR/RDA/05/25/30/CP/MTL | Ganadewi pilimaya asala Kulathunga mahathage welanda sala dakwa | Lahiru Construction & Consultants (PVT) Ltd | 86 Days in Delay | 100% |  |  |  | 0 | IPC
48 | RR/RDA/06/25/32/CP/NE | Nanuoya Glaso pahala kotasa Margaya | wiscon (pvt) ltd | 168 Days in Delay | 100% |  |  |  | 0 | IPC
49 | RR/RDA/06/25/34/CP/NE | Udupussellawa margaye Amasta handiye sita Ambagasdowa dakwa Margaya | NAGMA ENGINEERING (PVT) LTD | 182 Days in Delay | 100% |  |  |  | 0 | IPC
50 | RR/RDA/06/25/37/CP/NE | Gewal wissa handiye sita Bogalkanda dakwa Margaye asiru sthan | Ajith Construction | Completed | 100% |  | 100% |  | 0 | IPC
51 | RR/RDA/06/25/38/CP/NE | Ketahira Gallella margya palama haraha Udagama dakwa Margaya | NAGMA ENGINEERING (PVT) LTD | 182 Days in Delay | 100% |  |  |  | 0 | IPC
52 | RR/RDA/06/25/40/CP/NE | Walapane Samachaithya asalin Arambawana Kurundu oya diyaella dakwa Margaya | UGD Constructions | 299 Days in Delay | 100% |  |  |  | 0 | IPC
53 | RR/RDA/06/25/41/CP/NE | Nayapana Gammada tharapara sanwardhanaya | Central Engineering Services Pvt Ltd. (CESL) | 98 Days in Delay | 100% |  |  |  | 0 | IPC
54 | RR/RDA/06/25/42/CP/NE | AC Overlaying from Polpitiya Junction to 04th Mile Post (CH 3+700 – 8+700 km) | UKS Lanka Engineering Pvt Ltd. | 74 Days in Delay | 100% |  |  |  | 0 | IPC
55 |  | Carpeting of road from Bambaragama Moragollahinna to Karamidula | Ajith Construction | 152 Days in Delay |  |  | 10% |  | 0 | IPC
56 |  | Carpeting of Mahathenna to Hapugasdeniya Main Road | Ajith Construction | 152 Days in Delay |  |  | 73% |  | 0 | IPC
57 | RR/RDA/16/25/04/AKK/AMP | Pokunugama near Mr. Dinesh Tharaga House to Road (From Pokunugama Pre School to up to Mr. Dinesh Tharaga House) | Harischandra Idikirim | Completed | 100% |  | 100% |  | 0 | IPC
58 | RR/RDA/16/25/01/AKK/AMP | Samanalathenna- Road from House No.63 To the Monastery Muwagammana -From First Lane to Cemetry | Vithu Construction | Completed | 100% |  | 100% |  | 0 | IPC
59 | RR/RDA/16/25/03/AKK/AMP | Polbedda Junction to Galwalayaya Road | MOTEC Engineering & Construction | 239 Days in Delay | 100% |  |  |  | 0 | IPC
60 | RR/RDA/SP/16/25/01/AKK/AMP | Rectification and Asphalt Surfacing on Ambahagawela -Namaloya Main Road | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | 127 Days in Delay | 100% |  |  |  | 0 | IPC
61 | RR/RDA/STA II/16/25/02/AKK/AMP | Concreting entrance road with culvert at Dehiaththakandiya Kelegama | Vithu Construction | Completed | 100% |  | 100% |  | 0 | IPC
62 | RR/RDA/STA II/16/25/03/AKK/AMP | Padiyathalawa Navinna road from Navinna Junction A5 to Navinna Bridge | Vithu Construction | 162 Days in Delay | 100% |  |  |  | 0 | IPC
63 | RR/RDA/STA II/16/25/04/AKK/AKK | Lahugala Hulannuge Roundabout road | Zaka Engineering Consultancy | Completed | 100% |  | 100% |  | 0 | IPC
64 | RR/RDA/16/25/10KM/01/AKK/AMP | The road from the bridge near Ridee ela Temple to Island Plot No. 197 | Sawsiri Construction | 162 Days in Delay | 100% |  |  |  | 0 | IPC
65 | RR/RDA/16/25/10KM/02/AKK/AMP | Road from Nelum Cafe Junction to Neeththa | Gama Construction & Consultant pvt Ltd | 152 Days in Delay | 100% |  |  |  | 0 | IPC
66 | RR/RDA/16/25/10KM/03/AKK/AMP | On the road from Pulungasmulla to Padawala, the road from near Shanta Veladasala towards Padawala | Sawsiri Construction | 163 Days in Delay | 100% |  |  |  | 0 | IPC
67 | RR/RDA/16/25/10KM/04/AKK/AMP | Vevinna Boogas Junction Inner Road | Gama Construction & Consultant pvt Ltd | 180 Days in Delay | 100% |  |  |  | 0 | IPC
68 | RR/RDA/16/25/10KM/05/AKK/AMP | Road from Dorapaha Junction to Navagiriya Lake | Ema Constructions (Pvt) Ltd | 150 Days in Delay | 100% |  |  |  | 0 | IPC
69 | RR/RDA/16/25/10KM/06/AKK/AKK | Hulannuge School Road | Gama Construction & Consultant pvt Ltd | Completed | 100% |  | 100% |  | 0 | IPC
70 | RR/RDA/16/25/10KM/07/AKK/AMP | Bedirakka Malgastalawa Road | Pearl Construction | 173 Days in Delay | 100% |  |  |  | 0 | IPC
71 | RR/RDA/16/25/10KM/08/AKK/AKK | RDS Road Addalachena 6, 8 | MLH & sons Construction | 161 Days in Delay | 100% |  |  |  | 0 | IPC
72 | RR/RDA/16/25/10KM/09/AKK/AKK | Road behind Necode Institute (Navatkadu Akkarapattu) | SMA Careem Engineering Consultancy Services & Suppliers (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
73 | RR/RDA/16/25/10KM/11/AKK/AKK | Kalyana Road - Periyanilavanai Vishnu Kovil Road to Maradamuna Mashur Maulana Road | Zaka Engineering Consultancy | 151 Days in Delay | 100% |  |  |  | 0 | IPC
74 | RR/RDA/16/25/10KM/13/AKK/AKK | Jaica - Tsunami Village Road | Gama Construction & Consultant pvt Ltd | 144 Days in Delay | 100% |  |  |  | 0 | IPC
75 | RR/RDA/15/25/01/EP/BTC | Concreting to Vipulananthar road | SSK Construction | Completed | 100% |  | 100% |  | 0 | IPC
76 | RR/RDA/15/25/02/EP/BTC | Concreting to Samurthi 1st Cross road | Kumaran Construction and Civil Works | 636 Days in Delay | 100% |  |  |  | 0 | IPC
77 | RR/RDA/15/25/15/EP/BTC | Concrete to the Majma Nagar Mullivattuvan at paper town 210B | KMC Construction | 271 Days in Delay | 100% |  |  |  | 0 | IPC
78 | RR/RDA/15/25/05/EP/BTC | Concreting to Mailanthanai Sri Muththumariyamman Main Road | Kumaran Construction and Civil Works | 271 Days in Delay | 100% |  |  |  | 0 | IPC
79 | RR/RDA/15/25/07/EP/BTC | Concreting to Thakwa masjith Cross Road | Nazeeha Hardware and Construction | Completed | 100% |  | 100% |  | 0 | IPC
80 | RR/RDA/15/25/09/EP/BTC | Concreting to NHDA Housing Scheme Internal Road 1st 2nd Cross | DKJ Construction | 271 Days in Delay | 100% |  |  |  | 0 | IPC
81 | RR/RDA/15/25/11/EP/BTC | Concreting to Kali Kovil Road | Jeezan Trading and Transport | 271 Days in Delay | 100% |  |  |  | 0 | IPC
82 | RR/RDA/15/25/12/EP/BTC | Concreting to Muthalaikuda to Munnaikkadu Boundary Road | Kumaran Construction and Civil Works | 257 Days in Delay |  |  | 40% |  | 0 | IPC
83 | RR/RDA/15/25/13/EP/BTC | Concreting to Sangarpuram- Vilavadi | Kumaran Construction and Civil Works | 257 Days in Delay |  |  | 10% |  | 0 | IPC
84 | RR/RDA/15/25/14/EP/BTC | Concreting to Agriculture Road | Jeezan Trading and Transport | 271 Days in Delay | 100% |  |  |  | 0 | IPC
85 | RR/RDA/15/25/10KM/01/BTC | Sooriya farm Road sathurukondan | Ganan Construction | 12 Days in Delay |  |  | 50% |  | 0 | IPC
86 | RR/RDA/15/25/10KM/02/BTC | Iruthayapuram west 8th cross | Sanju Civil Construction | 12 Days in Delay |  |  | 30% |  | 0 | IPC
87 | RR/RDA/15/25/10KM/06/BTC | Al Ameen Vidyaya Road | Nathan's Construction | 4 days left |  |  | 20% |  | 0 | IPC
88 | RR/RDA/15/25/10KM/07/BTC | Kanady cross Road to Magalingeshwarar kovil Road | Motec Engineering & Construction | 1 Day in Delay |  |  | 5% |  | 0 | IPC
89 | RR/RDA/15/25/10KM/08/BTC | Poosakar Road, Kannakipuram, Mahiloor | Nathan's Construction | 12 Days in Delay |  |  | 95% |  | 0 | IPC
90 | RR/RDA/17/25/01/EP/TRN | Pillayar Road Renovation | Rina Construction | Completed | 100% |  | 100% |  | 0 | IPC
91 | RR/RDA/17/25/02/EP/TRN | Kathirkamathambi Road | Fareed | Completed | 100% |  | 100% |  | 0 | IPC
92 | RR/RDA/17/25/03/EP/TRN | Hospital Road | Pragash Construction | Completed | 100% |  | 100% |  | 0 | IPC
93 | RR/RDA/17/25/05/EP/TRN | Improvement to Jeyanthiwewa to Track 12 Main Road | Nirupama Construction | 127 days left | 92.6% |  |  |  | 0 | IPC
94 | RR/RDA/17/25/06/EP/TRN | Malporuwa to Thalgaswewa | Jeezan Trading and Transport | 127 days left | 92.6% |  |  |  | 0 | IPC
95 | RR/RDA/17/25/07/EP/TRN | Kanthamalawa Main Road | SSK Construction | Completed | 100% |  | 100% |  | 0 | IPC
96 | RR/RDA/17/25/09/EP/TRN | School-Galmetiyawa Main Internal Road | Zaka Engineering Consultancy | 75 Days in Delay | 100% |  |  |  | 0 | IPC
97 | RR/RDA/17/25/10/EP/TRN | From Medagama temple to Peramaduwa | Soyuru Sampath Construction & Suppliers | Completed | 100% |  | 100% |  | 0 | IPC
98 | RR/RDA/17/25/11/EP/TRN | Development of Road from near the Fair | MS Construction | 62 Days in Delay |  |  | 15% |  | 0 | IPC
99 | RR/RDA/17/25/12/EP/TRN | Improvement of RDS Road | MTA Construction | Completed | 100% |  | 100% |  | 0 | IPC
100 | RR/RDA/17/25/13/EP/TRN | Concreting from School junction to Boovidya Office | Hana Construction (Pvt) Ltd. | Completed | 100% |  | 100% |  | 0 | IPC
101 | RR/RDA/17/25/14/EP/TRN | Amaithusha Road (School road to Vaithiyar road) | Shaniff Construction | Completed | 100% |  | 100% |  | 0 | IPC
102 | RR/RDA/17/25/15/EP/TRN | Cemetery Road (Sajahan Mowlavi's house to Thajudeen shop) | Soyuru Sampath Construction & Suppliers | Completed | 100% |  | 100% |  | 0 | IPC
103 | RR/RDA/17/25/16/EP/TRN | Valuvar Road (Main road to Kovil road) | Shaniff Construction | Completed | 100% |  | 100% |  | 0 | IPC
104 | RR/RDA/17/25/18/EP/TRN | Sooranagar Main Road (Muththuchenai Junction to Thuvaraka Vithiyalayam)-Concrete | SSK Construction | Completed | 100% |  | 100% |  | 0 | IPC
105 | RR/RDA/17/25/19/EP/TRN | Periya Suwami Kovil Road-Concrete | Motec Engineering & Construction | 62 Days in Delay |  |  | 20% |  | 0 | IPC
106 | RR/RDA/SP/17/25/01/EP/TRN | Alankerny faisal Main Road (Koof Nagar) | NAS Construction | Completed | 100% |  | 100% |  | 0 | IPC
107 | RR/RDA/SP/17/25/03/EP/TRN | Hajra Road (Alhira Jalaira Road) | STAAR Construction | 75 Days in Delay | 100% |  |  |  | 0 | IPC
108 | RR/RDA/STAII/17/25/03/EP/TRN | From No.908 house to No.904 house road | Soyuru Sampath Construction & Suppliers | 1 day left |  |  | 15% |  | 0 | IPC
109 | RR/RDA/STAII/17/25/04/EP/TRN | From No.851 house to Rajaela road | ARN Engineering & Construction | 1 day left |  |  | 15% |  | 0 | IPC
110 | RR/RDA/17/25/10KM/01/EP/TRN | Road behind th hospital up to the morgue junction | Soyuru Sampath Construction & Suppliers | 4 days left |  |  | 10% |  | 0 | IPC
111 | RR/RDA/17/25/10KM/02/EP/TRN | LB cannel bridge to pachchimarama temple | Rina Construction | 4 days left |  |  | 5% |  | 0 | IPC
112 | RR/RDA/17/25/10KM/03/EP/TRN | Ethabendiwewa Second Lane | Nathan's Construction | 1 day left |  |  | 90% |  | 0 | IPC
113 | RR/RDA/17/25/10KM/04/EP/TRN | Kajuwaththa gama meda road | NMST Construction | 6 Days in Delay |  |  | 5% |  | 0 | IPC
114 | RR/RDA/17/25/10KM/06/EP/TRN | Budu pilima and 4th lane road | RS Construction | 6 Days in Delay |  |  | 15% |  | 0 | IPC
115 | RR/RDA/17/25/10KM/07/EP/TRN | Kawanthissa mawatha and in front of the cementerv road | Rina Construction | 4 days left |  |  | 20% |  | 0 | IPC
116 | RR/RDA/17/25/10KM/08/EP/TRN | Paththini Amman Kevil road | Alpha Engineering Services & Suppliers | 1 Day in Delay |  |  | 25% |  | 0 | IPC
117 | RR/RDA/17/25/10KM/09/EP/TRN | Bazar mosque road | MTA Construction | 1 Day in Delay |  |  | 40% |  | 0 | IPC
118 | RR/RDA/20/25/01/NCP/ANP | Road from Thambuttegama - Nochchiyagama road to the road near the DIG's office of Thambuthegama Rajanganaya | Creates Consultant and Construction | 62 Days in Delay |  |  | 30% |  | 0 | IPC
119 | RR/RDA/20/25/03/NCP/ANP | Thalawa - Eppawala margaye kele Amunukola handiyen aramba vee kele amunukola viddiyalayen divena margaya | Dissanayaka Builders | 281 Days in Delay |  |  | 40% |  | 0 | IPC
120 | RR/RDA/20/25/04/NCP/ANP | A - 9 maragayen aramba vee wale kade dakwa margaya | Dissanayaka Builders | 281 Days in Delay |  |  | 45% |  | 0 | IPC
121 | RR/RDA/20/25/05/NCP/ANP | Meda oyamaduwa handiye sita ehetuwawa dakwa margaya | D.M.C. CONSTRUCTION (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
122 | RR/RDA/20/25/06/NCP/ANP | Ududumbara boogas handiye sita sarakkugala pasal handiya dakwa margaya | Dissanayaka Builders | 281 Days in Delay |  |  | 0% |  | 0 | IPC
123 | RR/RDA/20/25/10/NCP/ANP | Manewe sita machchiyagama dakwa margaya | Sawsiri Construction | Completed | 100% |  | 100% |  | 0 | IPC
124 | RR/RDA/20/25/11/NCP/ANP | Palayakulama sita halmillakulama dakwa margaya | Dissanayaka Builders | 281 Days in Delay |  |  | 75% |  | 0 | IPC
125 | RR/RDA/20/25/12/NCP/ANP | Thalakolawewa carpert margaye awasanaye sita kudagama haraha dakunu ela iuwra margaya | CS Construction | Completed | 100% |  | 100% |  | 0 | IPC
126 | RR/RDA/20/25/13/NCP/ANP | Maradankadawala Habarana pare kaudawa handiyen patangena rambewa gammanaya dakwa margaya | Sawsiri Construction | Completed | 100% |  | 100% |  | 0 | IPC
127 | RR/RDA/20/25/14/NCP/ANP | Kukulewa pansala asalin arambavee samadhigama haraha seeppukulama rambewa maragaya dakwa divena pare pasala asala sita margaya | Kumari Konthrathkaruwo | Completed | 100% |  | 100% |  | 0 | IPC
128 | RR/RDA/20/25/16/NCP/ANP | Hiriwadunna handiye sita idigaswewa pansal handiya dakwa margaya | Sun Constructions (Pvt) Ltd. | 245 Days in Delay |  |  | 80% |  | 0 | IPC
129 | RR/RDA/20/25/18/NCP/ANP | Pahala Talawa road of Thalawa Andarawewa road | HPS Construction | 127 Days in Delay |  |  | 80% |  | 0 | IPC
130 | RR/RDA/20/25/20/NCP/ANP | Development of the road from near the Siri Sambodhi Viharaya, 4th Mile post, on the Airport Roundabout Road to the house of Mr. Peme | HPS Construction | 41 days left |  |  | 70% |  | 0 | IPC
131 | RR/RDA/20/25/22/NCP/ANP | Development of the road starting from Mahamankadawala School and extending to Yalegama | D.M.C. CONSTRUCTION (PVT) LTD | No schedule |  |  | 0% |  | 0 | IPC
132 | RR/RDA/20/25/26/NCP/ANP | Development of IV lane from Nuwara Road to Mihinthalaya Road | Priyantha Civil Engineering | 2 Days in Delay |  |  | 6% |  | 0 | IPC
133 | RR/RDA/20/25/28/NCP/ANP | Development of Rathnayake Mawatha | Priyantha Civil Engineering | 266 Days in Delay |  |  | 5% |  | 0 | IPC
134 | RR/RDA/20/25/29/NCP/ANP | Development of the road from Udugama Colony rural road near the A9 road to the front of Mr. Somaratne Senanayake's house | Priyantha Civil Engineering | 2 Days in Delay |  |  | 0% |  | 0 | IPC
135 |  | Development of the road starting from Padaviya Kabithigollewa Road to Buddhangala Temple | NMST Contractor | No schedule |  |  | 20% |  | 0 | IPC
136 |  | Development of road from Sripura main road to 38 Kolaniya Cemetery | NMST Contractor | 13 Days in Delay |  |  | 2% |  | 0 | IPC
137 |  | Development of road from Wahalkada D6 to Thalapakattialam on Punchimudagama road | Priyantha Civil Engineering | 2 Days in Delay |  |  | 5% |  | 0 | IPC
138 |  | Development of first phase of road from Punewa to Warakwewa | RSW Engineering | 14 Days in Delay |  |  | 25% |  | 0 | IPC
139 |  | Development of the road from Punewa Junction to Kudahalmillewa Lake | Priyantha Civil Engineering | 2 Days in Delay |  |  | 25% |  | 0 | IPC
140 |  | Development of the road from near Ikirigollawa Muslim Maha Vidyalaya to Ratmalgahawewa main road from near Ikirigollawa dam to Ratmalgahawa road | WGL Holdings | 2 Days in Delay |  |  | 30% |  | 0 | IPC
141 |  | From Makicchawa Junction to Temple (to Kulumiwakada Junction) | Priyantha Civil Engineering | 2 Days in Delay |  |  | 35% |  | 0 | IPC
142 |  | Paddy Depot Road near Padaviya Divisional Secretariat to the entrance road to the archaeological reserve. | Pathiraja Construction | No schedule |  |  | 0% |  | 0 | IPC
143 |  | road from near Mekichchawa Temple to Gammehegewewa. | Kumari Konthrathkaruwo | No schedule |  |  | 0% |  | 0 | IPC
144 |  | Maradankulam Weerakele Temple Road. | Lisal Construction | No schedule |  |  | 0% |  | 0 | IPC
145 | RR/RDA/21/25/03/NCP/POL | Mahasenpura pradeepika kadaya asala sita Katukeliyawa dakwa margaya Carpart kireema | Nadun Construction (Pvt) Ltd | 238 Days in Delay | 100% |  |  |  | 0 | IPC
146 | RR/RDA/21/25/04/NCP/POL | 10th Canal Lake Road | Nadun Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
147 | RR/RDA/21/25/17/NCP/POL | Development of the road from Kaduruwela Muslim Kolaniya road to Pachcha Palliya | Central Engineering Services Pvt Ltd. (CESL) | 72 Days in Delay | 100% |  |  |  | 0 | IPC
148 | RR/RDA/21/25/17/NCP/POL | Development of 1 canal Road from Kadurwela Muslim Kolaniya Road to Parakum Mawatha | Nadun Construction (Pvt) Ltd | 34 Days in Delay |  |  | 45% |  | 0 | IPC
149 |  | Development of the road from near the Pimburatthewa Mahaweli Resort to the Aralaganwila Maha Oya main road | Sawsiri Construction | 56 days left |  |  | 7% |  | 0 | IPC
150 |  | Development of the road from near the railway on the entrance road to the house of Mrs. 286 Latha in Boatta village | Nathan's Construction | 41 days left |  |  | 3% |  | 0 | IPC
151 |  | Development of the road from the main road to near the Kadawala Wewa School | Nadun Construction (Pvt) Ltd | 41 days left |  |  | 5% |  | 0 | IPC
152 |  | Development of the road from near the house at Pulastigama 156 to Sungawila 1 Canal Junction | Nadun Construction (Pvt) Ltd | 41 days left |  |  | 5% |  | 0 | IPC
153 |  | Road from near the Wota Gedi Bridge to Dambalu Stores | Nathan's Construction | 41 days left |  |  | 3% |  | 0 | IPC
154 | RR/RDA/18/25/01/NWP/KRG | Development of Egodagama Talakolawewa road | Sri Ram Constructions | 182 Days in Delay | 100% |  |  |  | 0 | IPC
155 | RR/RDA/18/25/02/NWP/KRG | Road from Parakumpura to Yaya 04 | Ingress Engineering | Completed | 100% |  | 100% |  | 0 | IPC
156 | RR/RDA/18/25/04/NWP/KRG | The road from Hunugallewa road junction to Madadenigama Hunugallewa Mahamaruwa Beligahaya to Mee Oya bridge | Shanho Enterprises Pvt Ltd. | 148 Days in Delay | 100% |  |  |  | 0 | IPC
157 | RR/RDA/18/25/07/NWP/KRG | Road from Moragolla Junction to Nabadewa Girilla Carpet Road via Kirinda | Jayasinghe Constructions (Pvt) Ltd. | 176 Days in Delay | 100% |  |  |  | 0 | IPC
158 | RR/RDA/18/25/08/NWP/KRG | Paving of road from Nammuawa to Nagansole temple | Omega Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
159 | RR/RDA/18/25/09/NWP/KRG | Paving the road from Pahala Galapitiyagama to Tharanagolla Sports Ground | Senerath Engineering (pvt) Ltd | 246 Days in Delay | 100% |  |  |  | 0 | IPC
160 | RR/RDA/18/25/11/NWP/KRG | Development of road from Dambulu Road to Havanathenna via Ehelagollaya | Shanho Enterprises Pvt Ltd. | 126 Days in Delay | 100% |  |  |  | 0 | IPC
161 | RR/RDA/18/25/16/NWP/KRG | Development of concrete road from near Wadawa temple to the lake | Jayawardana Constructions (Pvt) Ltd. | Completed | 100% |  | 100% |  | 0 | IPC
162 | RR/RDA/18/25/22/NWP/KRG | Paving of culverts and sidewalls at the necessary places on the road from near Moragane Samiti Hall to Siyambalaweva via Galkadulla. | Jayasinghe Constructions (Pvt) Ltd. | 153 Days in Delay | 100% |  |  |  | 0 | IPC
163 | RR/RDA/18/25/24/NWP/KRG | Paving and developing the road from Seelarathana Mawatha to Girana Junction | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
164 | RR/RDA/18/25/104/NWP/KRG | Pinnagolla Junction to Kokowaththa Junction VIA Alakolapelessa | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
165 | RR/RDA/18/25/106/NWP/KRG | Thagahinna Temple Road | Jayawansa Construction (PVT) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
166 | RR/RDA/18/25/NWP/KRG/10 | Uyandana Yaggapitiya | Senerath Engineering (pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
167 | RR/RDA/18/25/135/NWP/KRG | Kelegedara Gamameda Road (CTB Basaya Dawanaya wana) Kavudumunna, Kunumade, Hungan pitiya haraha diwena Margaya Kapat Kirima | Jayasinghe Contractors (Pvt) Ltd. | 168 Days in Delay |  |  | 20% |  | 0 | IPC
168 | RR/RDA/18/25/136/NWP/KRG | Ranasinghe Hotel Asalin Koralaya Waththe sita Panwala Kubura Dakwa Diwena Margaya Kapat Kirima | Jayasinghe Contractors (Pvt) Ltd. | Completed | 100% |  | 100% |  | 0 | IPC
169 | RR/RDA/18/25/137/NWP/KRG | Damunugolla Sita Kobbewehera Handiya Dakwa Margaya Kapat Kirima | W P J Engineering(Pvt)Ltd | 212 Days in Delay | 100% |  |  |  | 0 | IPC
170 | RR/RDA/18/25/138/NWP/KRG | Pudukkulama Bogas Handiye sita Keppitiya haraha Thihawa Dakwa Margaya Kapat Kirima | W P J Engineering(Pvt)Ltd | 211 Days in Delay | 100% |  |  |  | 0 | IPC
171 | RR/RDA/18/25/139/NWP/KRG | Akkara Panaha Mansandiye Sita Walahamulla Dakwa Margaya | Jayawansa Construction (PVT) Ltd | 170 Days in Delay | 100% |  |  |  | 0 | IPC
172 |  | Wijekoon Mawatha near Narammala Bus Stand and Hospital Mawatha from Peralaswella | Thushara roofing (pvt) ltd | 94 Days in Delay | 100% |  |  |  | 0 | IPC
173 | RR/RDA/19/25/01/NWP/PUT | Development of carpeting the Gammedda road up to Anathapara. | Chandana Construction | 319 Days in Delay | 100% |  |  |  | 0 | IPC
174 | RR/RDA/19/25/04/NWP/PUT | Carpeting of green light carpeted road from Bogus Junction (80 acres). | Sri Ram Constructions | 240 Days in Delay | 100% |  |  |  | 0 | IPC
175 | RR/RDA/19/25/05/NWP/PUT | Development of the road from near Mr. Chaminda's house to Boga Pathaha | Sampath Contractors | 245 Days in Delay | 100% |  |  |  | 0 | IPC
176 | RR/RDA/19/25/08/NWP/PUT | Carpeting of Velasia Main Road from Madurankuliya. | Sri Ram Constructions | 214 Days in Delay | 100% |  |  |  | 0 | IPC
177 | RR/RDA/19/25/26/NWP/PUT | Abayarama Mawatha Bomimakka Kovil Road to Sembandaluwa Temple Road | Sampath Construction | Completed | 100% |  | 100% |  | 0 | IPC
178 | RR/RDA/19/25/27/NWP/PUT | The entrance to the Medical Officer's Office in the Galahitiyawa Grama Niladhari Division | Omega Construction (Pvt) Ltd | 274 Days in Delay | 100% |  |  |  | 0 | IPC
179 | RR/RDA/19/25/28/NWP/PUT | Samagi Mawatha | Ranuja Construction | Completed | 100% |  | 100% |  | 0 | IPC
180 | RR/RDA/19/25/29/NWP/PUT | Development of the road from Galkuliya Welameda to Mrs. Deepani's house | Sampath Construction | Completed | 100% |  | 100% |  | 0 | IPC
181 | RR/RDA/19/25/30/NWP/PUT | Development of carpeting from Mihirajthotupola to Serakkuliya 1 on the Serakkuliya main road | Omega Construction (Pvt) Ltd | 206 Days in Delay | 100% |  |  |  | 0 | IPC
182 | RR/RDA/19/25/31/NWP/PUT | Development of carpeting from the point where carpeting has stopped on the Tammana main road | Sampath Construction | 175 Days in Delay | 100% |  |  |  | 0 | IPC
183 | RR/RDA/19/25/32/NWP/PUT | Development of the Bammeyaya Road | Jayawardana Constructions (Pvt) Ltd. | 176 Days in Delay | 100% |  |  |  | 0 | IPC
184 | RR/RDA/19/25/33/NWP/PUT | Development of the road from near the Sugatarama Temple, Periyakulam to Thalgaswewa | Jayawardana Constructions (Pvt) Ltd. | 206 Days in Delay | 100% |  |  |  | 0 | IPC
185 | RR/RDA/19/25/34/NWP/PUT | Carpeting & Development of Bodhirajapura 4th Lane | Sampath Construction | 176 Days in Delay | 100% |  |  |  | 0 | IPC
186 | RR/RDA/19/25/37/NWP/PUT | Lawyer Wijayananda's House Road | Ponnamperuma Suppliers | 204 Days in Delay | 100% |  |  |  | 0 | IPC
187 | RR/RDA/19/25/38/NWP/PUT | North Dummaladeniya Cross Road | Ponnamperuma Suppliers | 204 Days in Delay | 100% |  |  |  | 0 | IPC
188 | RR/RDA/19/25/39/NWP/PUT | Renovation of Khemananda Road | SriLak Import and Export Company | 199 Days in Delay | 100% |  |  |  | 0 | IPC
189 |  | Development of the road from Madurankuliya to Velasiya College | Sampath Construction | 167 Days in Delay |  |  | 30% |  | 0 | IPC
190 |  | Development of Fenando Road - Picchawala Road | Dilini Builders (PVT) LTD | 79 Days in Delay | 100% |  |  |  | 0 | IPC
191 | RR/RDA/10/25/01/NP/JFN | Maveli Periyathurai Road. 3.6509 | Sun Constructions (Pvt) Ltd. | No schedule |  |  | 20% |  | 0 | IPC
192 | RR/RDA/10/25/03/NP/JFN | Navalar Road | KBS Engineering Solution | Completed | 100% |  | 100% |  | 0 | IPC
193 | RR/RDA/10/25/04/NP/JFN | Aluminium Factory Road | Majurathas Building Contractors | Completed | 100% |  | 100% |  | 0 | IPC
194 | RR/RDA/10/25/05/NP/JFN | Renovation of Kokkuruniya Veethy | Majurathas Building Contractors | Completed | 100% |  | 100% |  | 0 | IPC
195 | RR/RDA/10/25/06/NP/JFN | Renovation of West beach Road | Sun Constructions (Pvt) Ltd. | 200 Days in Delay | 100% |  |  |  | 0 | IPC
196 | RR/RDA/10/25/08/NP/JFN | Renovation of Ilanthaikulam Road | KBS Engineering Solution | Completed | 100% |  | 100% |  | 0 | IPC
197 | RR/RDA/10/25/10/NP/JFN | Nayanmar Road | AVP Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
198 | RR/RDA/10/25/11/NP/JFN | Amman Road | Thaaru Construction | Completed | 100% |  | 100% |  | 0 | IPC
199 | RR/RDA/10/25/13/NP/JFN | lnbacholai Road (Iththiyadi Muthali Kovilady - Inbacholai Road) | AVP Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
200 | RR/RDA/10/25/14/NP/JFN | Pankuru Veethy | Thaaru Construction | 162 Days in Delay | 100% |  |  |  | 0 | IPC
201 | RR/RDA/10/25/15/NP/JFN | Kadavaippulam Road | KBS Engineering Solution | Completed | 100% |  | 100% |  | 0 | IPC
202 | RR/RDA/10/25/16/NP/JFN | Kalai Makal Road | Jana Civil Work Contractors and Material Suppliers | Completed | 100% |  | 100% |  | 0 | IPC
203 | RR/RDA/10/25/18/NP/JFN | Atchuvely Industrial Road | Sun Constructions (Pvt) Ltd. | 214 Days in Delay | 100% |  |  |  | 0 | IPC
204 | RR/RDA/10/25/20/NP/JFN | Thuvali Veethy | Majurathas Building Contractors | Completed | 100% |  | 100% |  | 0 | IPC
205 | RR/RDA/10/25/22/NP/JFN | Anaivilunthan Sudalai Road | Yaso Engineering | 215 Days in Delay | 100% |  |  |  | 0 | IPC
206 | RR/RDA/10/25/25/NP/JFN | Palaiya Vaikal Veeethy | Sun Constructions (Pvt) Ltd. | 216 Days in Delay | 100% |  |  |  | 0 | IPC
207 | RR/RDA/12/25/01/NP/VVN | Thiruchchenthooran mill road NVSTE541 | TMC Constructions | 36 Days in Delay | 100% |  |  |  | 0 | IPC
208 | RR/RDA/12/25/02/NP/VVN | Eswarypuram housing scheme internal road (NVSTE178) | Sintha Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
209 | RR/RDA/12/25/03/NP/VVN | Puthiya manipuram, main road (NVSTE481) | Yaso Engineering | 264 Days in Delay | 100% |  |  |  | 0 | IPC
210 | RR/RDA/12/25/04/NP/VVN | Suntharapuram main road | Sun Constructions (Pvt) Ltd. | 154 Days in Delay | 100% |  |  |  | 0 | IPC
211 | RR/RDA/12/25/17/NP/VVN | Lyca village enterance Road | Sun Constructions (Pvt) Ltd. | 154 Days in Delay |  |  | 35% |  | 0 | IPC
212 | RR/RDA/12/25/22/NP/VVN | Mannankerny road | Sun Constructions (Pvt) Ltd. | 154 Days in Delay |  |  | 50% |  | 0 | IPC
213 | RR/RDA/12/25/52/NP/VVN | Menanager Malakattu Kalkuwari Road | Sun Constructions (Pvt) Ltd. | 154 Days in Delay |  |  | 65% |  | 0 | IPC
214 | RR/RDA/12/25/05/NP/VVN | Sinnakulam road – laxapana road | Arul Selvi Construction and Hardware | Completed | 100% |  | 100% |  | 0 | IPC
215 | RR/RDA/12/25/07/NP/VVN | Tharanikulam main road | Sintha Construction (Pvt) Ltd | 255 Days in Delay | 100% |  |  |  | 0 | IPC
216 | RR/RDA/12/25/08/NP/VVN | Katkulam road | Yansika Success Group (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
217 | RR/RDA/12/25/10/NP/VVN | Achchipuram amman temble road | Ancheneya Constructions | 271 Days in Delay | 100% |  |  |  | 0 | IPC
218 | RR/RDA/12/25/12/NP/VVN | Nanthimiththiragama 1st | Ancheneya Constructions | 166 Days in Delay | 100% |  |  |  | 0 | IPC
219 | RR/RDA/12/25/13/NP/VVN | Nanthimiththiragama 2nd | Ancheneya Constructions | 196 Days in Delay | 100% |  |  |  | 0 | IPC
220 | RR/RDA/12/25/14/NP/VVN | Nanthimiththiragama 4th | Ancheneya Constructions | 196 Days in Delay | 100% |  |  |  | 0 | IPC
221 | RR/RDA/12/25/18/NP/VVN | Nedunkerny North sandankulam Road | Yaso Engineering | 265 Days in Delay |  |  | 35% |  | 0 | IPC
222 | RR/RDA/12/25/19/NP/VVN | Senaipilavu Road | Yaso Engineering | 265 Days in Delay |  |  | 70% |  | 0 | IPC
223 | RR/RDA/12/25/20/NP/VVN | Puthiyakudiyiruppu parasankulam road | Bapithan Construction | 271 Days in Delay |  |  | 70% |  | 0 | IPC
224 | RR/RDA/12/25/21/NP/VVN | Bagaswewa 01st 22nd lane | Bapithan Construction | 271 Days in Delay |  |  | 35% |  | 0 | IPC
225 | RR/RDA/12/25/24/NP/VVN | Kanagarayankulam puthuvilankulam road (NVVNE073) | Bapithan Construction | 264 Days in Delay |  |  | 70% |  | 0 | IPC
226 | RR/RDA/12/25/25/NP/VVN | 2nd cross Lane Ginigathhena | Nimna Holdings (Pvt) Ltd | 256 Days in Delay |  |  | 70% |  | 0 | IPC
227 | RR/RDA/12/25/26/NP/VVN | Cemetery Road | Ranasinghe Construction | Completed | 100% |  | 100% |  | 0 | IPC
228 | RR/RDA/12/25/27/NP/VVN | From Acre 400 7th Lane to cross end of the 2nd internal road close to Andarawewa | Ranasinghe Construction | 246 Days in Delay |  |  | 30% |  | 0 | IPC
229 | RR/RDA/12/25/28/NP/VVN | From Janaudanagama 2nd internal road to end of the free school | North Construction (Pvt) Ltd | 271 Days in Delay |  |  | 35% |  | 0 | IPC
230 | RR/RDA/12/25/29/NP/VVN | Kalasiyambalawa Road | North Construction (Pvt) Ltd | 264 Days in Delay |  |  | 50% |  | 0 | IPC
231 | RR/RDA/12/25/30/NP/VVN | Maradammaduwa Rural Road | Sevvel Construction & Suppliers | Completed | 100% |  | 100% |  | 0 | IPC
232 | RR/RDA/12/25/31/NP/VVN | Mahakachchakodiya to Ettambagaskada | Yansika Construction | 288 Days in Delay |  |  | 30% |  | 0 | IPC
233 | RR/RDA/12/25/32/NP/VVN | Kalukummankaduwa to Alagalla Rural Road | Yansika Construction | Completed | 100% |  | 100% |  | 0 | IPC
234 | RR/RDA/12/25/33/NP/VVN | Mamaduwa Thiyawaragama Road | 5N Group Construction | Completed | 100% |  | 100% |  | 0 | IPC
235 | RR/RDA/12/25/35/NP/VVN | Awusadapitiya Pubudugama Road | Nimna Holdings (Pvt) Ltd | 256 Days in Delay |  |  | 70% |  | 0 | IPC
236 | RR/RDA/12/25/36/NP/VVN | Mamaduwa to Dikwewa | Sintha Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
237 | RR/RDA/12/25/37/NP/VVN | Parakumawatha | Ranasinghe Construction | Completed | 100% |  | 100% |  | 0 | IPC
238 | RR/RDA/12/25/38/NP/VVN | Salalinigama 11 lane | Sintha Construction (Pvt) Ltd | 255 Days in Delay |  |  | 50% |  | 0 | IPC
239 | RR/RDA/12/25/39/NP/VVN | Madukanda lake side road | Sintha Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
240 | RR/RDA/12/25/40/NP/VVN | Halabagaswewa | North Construction (Pvt) Ltd | 255 Days in Delay |  |  | 5% |  | 0 | IPC
241 | RR/RDA/12/25/41/NP/VVN | Arasadikulam - veerapuram road (2km) veerapuram 1st lane (NVVPE227) | Omega Construction (Pvt) Ltd | No schedule |  |  | 0% |  | 0 | IPC
242 | RR/RDA/12/25/42/NP/VVN | Veerapuram main road (veerapuram 2nd 3rd lane) | Yaso Engineering | Completed | 100% |  | 100% |  | 0 | IPC
243 | RR/RDA/12/25/43/NP/VVN | Pavatkulam tack 5 vaarikuttiyoor | North Construction (Pvt) Ltd | 255 Days in Delay | 100% |  |  |  | 0 | IPC
244 | RR/RDA/12/25/46/NP/VVN | Sinnasippikulam to neriyakulam road | North Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
245 | RR/RDA/12/25/48/NP/VVN | Mukaththankulam 7th lane (NVVPE173) | Sintha Construction (Pvt) Ltd | 255 Days in Delay | 100% |  |  |  | 0 | IPC
246 | RR/RDA/12/25/51/NP/VVN | Adappankulam aladi road | North Construction (Pvt) Ltd | 255 Days in Delay | 100% |  |  |  | 0 | IPC
247 | RR/RDA/12/25/53/NP/VVN | Ethawetunuwewa Temple Road | Shiyamala Construction | Completed | 100% |  | 100% |  | 0 | IPC
248 | RR/RDA/12/25/54/NP/VVN | Nikawewa Right Village Road | Yansika Construction | 272 Days in Delay |  |  | 70% |  | 0 | IPC
249 | RR/RDA/12/25/55/NP/VVN | Mayawewa to Namalpura Road | Yansika Construction | Completed | 100% |  | 100% |  | 0 | IPC
250 | RR/RDA/12/25/56/NP/VVN | From Nikawewa Post Office to Nikawewa Right Village | Yansika Construction | Completed | 100% |  | 100% |  | 0 | IPC
251 | RR/RDA/12/25/57/NP/VVN | Nikawewa Right to Sapumalthanna | Yansika Construction | Completed | 100% |  | 100% |  | 0 | IPC
252 | RR/RDA/12/25/58/NP/VVN | Preschool Road | 5N Group Construction | Completed | 100% |  | 100% |  | 0 | IPC
253 | RR/RDA/12/25/59/NP/VVN | Kalyanipura 2nd lane | 5N Group Construction | Completed | 100% |  | 100% |  | 0 | IPC
254 | RR/RDA/12/25/60/NP/VVN | Salalinigama lane 12 | Sintha Construction (Pvt) Ltd | 124 Days in Delay | 100% |  |  |  | 0 | IPC
255 | RR/RDA/12/25/62/NP/VVN | Periyavilathikulam | Omega Construction (Pvt) Ltd | 124 Days in Delay | 100% |  |  |  | 0 | IPC
256 | RR/RDA/12/25/63/NP/VVN | 1st Cross Street Alakarai Road | North Construction | 167 Days in Delay | 100% |  |  |  | 0 | IPC
257 | RR/RDA/12/25/64/NP/VVN | Nedunkulama | Arul Selvi Construction and Hardware | 124 Days in Delay | 100% |  |  |  | 0 | IPC
258 | RR/RDA/13/25/01/NP/MUL | Akkaraiveli Paraiyanaru ( Vilaththiyad) Road Package 1 | Sun Constructions (Pvt) Ltd. | 247 Days in Delay | 100% |  |  |  | 0 | IPC
259 | RR/RDA/13/25/03/NP/MUL | Navatkadu Road | TMC Constructions | 217 Days in Delay | 100% |  |  |  | 0 | IPC
260 | RR/RDA/13/25/06/NP/MUL | Pandaravanniyan Silaiyadi Road | Sun Constructions (Pvt) Ltd. | 223 Days in Delay | 100% |  |  |  | 0 | IPC
261 | RR/RDA/13/25/07/NP/MUL | Kanagarayankulam District Boundary Road (Old Kandy road) | Sun Constructions (Pvt) Ltd. | 223 Days in Delay | 100% |  |  |  | 0 | IPC
262 | RR/RDA/13/25/08/NP/MUL | Kumulamunai Akkarayan road | Nimna Holdings (Pvt) Ltd | 217 Days in Delay | 100% |  |  |  | 0 | IPC
263 | RR/RDA/13/25/10/NP/MUL | Pandiyankulam Neddankandal Road | Nimna Holdings (Pvt) Ltd | 217 Days in Delay | 100% |  |  |  | 0 | IPC
264 | RR/RDA/13/25/11/NP/MUL | Ethawetuvuwewa to Sampathnuwara | Nimna Holdings (Pvt) Ltd | 135 Days in Delay |  |  | 30% |  | 0 | IPC
265 | RDA/GOSL/NP/RR/LCB/PACKAGE 2(MU) | Thapaalaga veethi Section I &II, 2nd Cross Road, Kallappadu kadtkarai Main Road, Koolamurippu kerudamadu enaippu veethi and Olumadu Pullmachchinathikulam Ampakamam Road | RR Construction (Pvt) Ltd. | No schedule |  |  | 0% |  | 0 | IPC
266 | RR/RDA/11/25/01/NP/MNR | Mahilankulam Pallamadhu road | George Steuart Engineering (Pvt)Ltd | 163 Days in Delay |  |  | 50% |  | 0 | IPC
267 | RR/RDA/11/25/02/NP/MNR | Piramanayankulam Parappukadanthan road | George Steuart Engineering (Pvt)Ltd | 163 Days in Delay |  |  | 55% |  | 0 | IPC
268 | RR/RDA/11/25/03/NP/MNR | Kaddadivayal Ramayankulam Naddankandal road | Nimna Holdings (Pvt) Ltd | No schedule |  |  | 0% |  | 0 | IPC
269 | RR/RDA/11/25/04/NP/MNR | Tharavankottai to Keeri Main Road | VN Construction JV | 153 Days in Delay |  |  | 60% |  | 0 | IPC
270 | RR/RDA/11/25/07/NP/MNR | Avithappar Panimayam Internal Road with Culvert - Pesalai | VN Construction JV | 153 Days in Delay |  |  | 70% |  | 0 | IPC
271 | RR/RDA/11/25/11/NP/MNR | Eruvittan - Vellalakaddu Road | VN Construction JV | 153 Days in Delay |  |  | 5% |  | 0 | IPC
272 | RR/RDA/11/25/05/NP/MNR | Konnayan Kudiyiruppu Internal Main Road | Sun Constructions (Pvt) Ltd. | 179 Days in Delay |  |  | 5% |  | 0 | IPC
273 | RR/RDA/11/25/06/NP/MNR | Martin Road | Pastini Construction Material Supply | No schedule |  |  | 60% |  | 0 | IPC
274 | RR/RDA/11/25/09/NP/MNR | Renovation of Mathirikiramam internal Road Naruvilikulam | Abdul Cader Constructions | 238 Days in Delay |  |  | 70% |  | 0 | IPC
275 | RR/RDA/11/25/10/NP/MNR | Malikaippiddy 1st 2nd 3rd 4th Road | Vision Lanka Engineering (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
276 | RR/RDA/11/25/13/NP/MNR | Variveli Pandaraveli Road | Sanjeeve Construction Work | Completed | 100% |  | 100% |  | 0 | IPC
277 | RR/RDA/11/25/14/NP/MNR | Pichaivanifa Nedunkulam Scheme Internal Road 2 | Fahim Builders | Completed | 100% |  | 100% |  | 0 | IPC
278 | RR/RDA/11/25/15/NP/MNR | Veppankulam Scheme Internal Road (Mosque) 3 | Sanjeeve Construction Work | Completed | 100% |  | 100% |  | 0 | IPC
279 | RR/RDA/11/25/16/NP/MNR | P.P.Potkerny Scheme Internal Road 1 | Abdul Cader Constructions | 216 Days in Delay |  |  | 70% |  | 0 | IPC
280 | RR/RDA/11/25/18/NP/MNR | Akaththimurippu Internal Road 3 | Abdul Cader Constructions | 216 Days in Delay |  |  | 70% |  | 0 | IPC
281 | RR/RDA/11/25/19/NP/MNR | Chilawathurai Maiyavadi Road | Abdul Cader Constructions | Completed | 100% |  | 100% |  | 0 | IPC
282 | RR/RDA/11/25/20/NP/MNR | Kondachchi to Pasithenral Road | Abdul Cader Constructions | No schedule |  |  | 70% |  | 0 | IPC
283 | RR/RDA/11/25/22/NP/MNR | School back side road | Sintha Construction (Pvt) Ltd | No schedule |  |  | 30% |  | 0 | IPC
284 | RR/RDA/11/25/23/NP/MNR | Palakaimunai Beach Road | Sun Constructions (Pvt) Ltd. | No schedule |  |  | 20% |  | 0 | IPC
285 | RR/RDA/11/25/24/NP/MNR | Murukan Kovil Main Road | Abdul Cader Constructions | Completed | 100% |  | 100% |  | 0 | IPC
286 |  | Pallavarayankaddu Junction - Kiranchi - Ponnaveli Road | Nimna Holdings (Pvt) Ltd | No schedule |  |  | 0% |  | 0 | IPC
287 | RR/RDA/14/25/06/NP/KLN | Skanthapuram Kannan Temple road | Sun Constructions (Pvt) Ltd. | 246 Days in Delay |  |  | 35% |  | 0 | IPC
288 | RR/RDA/14/25/07/NP/KLN | Mayilvakanapuram kolunthupulavu road | RR Construction (Pvt) Ltd. | No schedule |  |  | 30% |  | 0 | IPC
289 | RR/RDA/14/25/08/NP/KLN | Kalmadu 7th unit 3rd lane | Kanola Constructions & Engineering (Pvt) Ltd | 246 Days in Delay |  |  | 20% |  | 0 | IPC
290 | RR/RDA/14/25/09/NP/KLN | Neliyai Amman kovil road | Kanola Constructions & Engineering (Pvt) Ltd | 239 Days in Delay | 100% |  |  |  | 0 | IPC
291 | RR/RDA/10/25/24/NP/KLN | Kevil Nithtiyaveddai Road 2.150 | Kanola Constructions & Engineering (Pvt) Ltd | 239 Days in Delay | 100% |  |  |  | 0 | IPC
292 | RDA/GOSL/NP/RR/LCB/PACKAGE 1(KN) | Vannerikulam Jeyapuram Road, Anaikkaddy Road, Veddukkaddu Road Sec.i & iii and Sekkalai Mudkompan Road | RR Construction (Pvt) Ltd. | No schedule |  |  | 0% |  | 0 | IPC
293 | RR/RDA/25/24/01/SBP/RTP | From Delgas Junction To Vilehena Road | Siri Construction | 324 Days in Delay | 100% |  |  |  | 0 | IPC
294 | RR/RDA/25/24/02/SBP/RTP | Thundola Varathenna Road | Siri Construction | 186 Days in Delay | 100% |  |  |  | 0 | IPC
295 | RR/RDA/25/24/03/SBP/RTP | From Thunaghahena To Temple Road | Siri Construction | 324 Days in Delay | 100% |  |  |  | 0 | IPC
296 | RR/RDA/25/24/04/SBP/RTP | Keenagahawila Kanuggala Road | SSP Engineering | Completed | 100% |  | 100% |  | 0 | IPC
297 | RR/RDA/25/24/05/SBP/RTP | From Nadurana Kosgas Junction to Bathalakotuwa Via Kiriporuwa Road | SSP Engineering | Completed | 100% |  | 100% |  | 0 | IPC
298 | RR/RDA/25/24/06/SBP/RTP | Hewainna Koshenagama Road | Asela Construction | Completed | 100% |  | 100% |  | 0 | IPC
299 | RR/RDA/25/24/10/SBP/RTP | From Deniya kade Market to Henyaya Road Via Keenagahaella Road | Sam Dam | 191 Days in Delay | 100% |  |  |  | 0 | IPC
300 | RR/RDA/25/24/13/SBP/RTP | Henyaya - Mirishena South Road | SSP Engineering | Completed | 100% |  | 100% |  | 0 | IPC
301 | RR/RDA/25/24/14/SBP/RTP | Pimbura- Peelwatta Road | SSP Engineering | Completed | 100% |  | 100% |  | 0 | IPC
302 | RR/RDA/25/24/16/SBP/RTP | Kalawana Salgaha Yata Road | SSP Engineering | Completed | 100% |  | 100% |  | 0 | IPC
303 | RR/RDA/24/25/21/SBP/RTP | Sudagala Grama Seva Division, From Sudagala to Tunudola Road up the mountain to near the cooperative | DKS Construction | 22 Days in Delay | 100% |  |  |  | 0 | IPC
304 | RR/RDA/24/25/25/SBP/RTP | From the point where the Bulathgama-Pallevela road starts from Rasagala Road | Sathira Construction | 18 days left | 89.4% |  |  |  | 0 | IPC
305 | RR/RDA/24/25/28/SBP/RTP | From near Kalal Ella Rubber Store to Narangalla via Navinikanda Road | KEP Construction | 5 days left | 100% |  |  |  | 0 | IPC
306 | RR/RDA/24/25/31/SBP/RTP | Development of Koratuwegoda Road from Main Road | KEP Construction | 29 days left | 82.3% |  |  |  | 0 | IPC
307 | RR/RDA/24/25/32/SBP/RTP | Weligepola to Nitta Kumbura Road | Sasiri Construction | 18 days left | 89.4% |  |  |  | 0 | IPC
308 | RR/RDA/24/25/34/SBP/RTP | Matuwagala Mudun Kotu Road | DKS Construction | 22 Days in Delay | 100% |  |  |  | 0 | IPC
309 | RR/RDA/24/25/35/SBP/RTP | Induruwa Junction to Kadawatha junction road joining Kuruwita - Siripagama road | Creates Consultant and Construction | No schedule |  |  | 0% |  | 0 | IPC
310 | RR/RDA/25/25/02/SBP/KGL | Elagapitiya Colany Road From Debathgama Pallebage to Tea Shakthi Praja Shalawa | EHL Constructions | 184 Days in Delay | 100% |  |  |  | 0 | IPC
311 | RR/RDA/25/25/03/SBP/KGL | From Kehelpannala Junction to Pahala Kabawita Road | SF Constructions | 188 Days in Delay | 100% |  |  |  | 0 | IPC
312 | RR/RDA/25/25/05/SBP/KGL | Siyabalangamuwa Kudumbuwa Road | Shanho Engineering | Completed | 100% |  | 100% |  | 0 | IPC
313 | RR/RDA/25/25/06/SBP/KGL | From Dombemada Post Office to Sillugala Via Wedollamada well | Shanho Engineering | Completed | 100% |  | 100% |  | 0 | IPC
314 | RR/RDA/25/25/09/01/SBP/KGL | The first phase of the Matiyagane-Berawandare road from Mas Potha via Haliyagoda | Samindra construction | Completed | 100% |  | 100% |  | 0 | IPC
315 | RR/RDA/25/25/09/02/SBP/KGL | The first phase of the Gaitahpura road via Ambagala on the Warakapola Technical College Road |  | No schedule |  |  | 0% |  | 0 | IPC
316 | RR/RDA/25/25/10/SBP/KGL | Elipangamuwa School Road through Pananawaththa | DHP Construction | Completed | 100% |  | 100% |  | 0 | IPC
317 | RR/RDA/25/25/15/SBP/KGL | Moraliya Gagaboda Road | DHP Construction | 276 Days in Delay | 100% |  |  |  | 0 | IPC
318 | RR/RDA/25/25/20/SBP/KGL | Neluwakkana gama meda Road | Loshitha Construction | 259 Days in Delay |  |  | 95% |  | 0 | IPC
319 | RR/RDA/25/25/28/SBP/KGL | Naagas thenna Road | Jayasinghe Contractors (Pvt) Ltd. | 84 Days in Delay |  |  | 90% |  | 0 | IPC
320 | RR/RDA/25/25/31/SBP/KGL | Developing the section connecting the road from the old office in Yatawala to the road in Beraliyahinna | DHP Construction | Completed | 100% |  | 100% |  | 0 | IPC
321 | RR/RDA/25/25/32/SBP/KGL | Concreting the unconcreted areas of the Hingurana road | DHP Construction | Completed | 100% |  | 100% |  | 0 | IPC
322 | RR/RDA/25/25/33/SBP/KGL | Rehabilitation of Kahatapanawa Kajugahamula road | Jayabima Engineering | Completed | 100% |  | 100% |  | 0 | IPC
323 | RR/RDA/25/25/34/SBP/KGL | Road Connecting Ihala Palampitiya and Pahala Palampitiya | DKS Nishantha Construction | 13 Days in Delay | 100% |  |  |  | 0 | IPC
324 | RR/RDA/25/25/35/SBP/KGL | Kudadeniya Adurapola Watta Road | TMT Construction | 155 Days in Delay | 100% |  |  |  | 0 | IPC
325 | RR/RDA/25/25/38/SBP/KGL | Development of the road near the closed tea factory on Edurapola Watta main road | TMT Construction | 153 Days in Delay | 100% |  |  |  | 0 | IPC
326 | RR/RDA/25/25/39/SBP/KGL | Development of Gatayamulla Jagatpura Pannala Rasnadeniya road | Samindra Construction | 65 Days in Delay | 100% |  |  |  | 0 | IPC
327 | RR/RDA/25/25/40/SBP/KGL | Kabagamuwa 17 Acres Road Development | TMT Construction | 160 Days in Delay |  |  | 95% |  | 0 | IPC
328 | RR/RDA/07/25/02/SP/GAL | Delgahabedda-Kirimatiya Margaya | Dissanayaka Builders | 323 Days in Delay | 100% |  |  |  | 0 | IPC
329 | RR/RDA/07/25/05/SP/GAL | Atawalawatta Sri Rewatha Viduhala Idiripita Margaya | Dissanayaka Builders | 323 Days in Delay | 100% |  |  |  | 0 | IPC
330 | RR/RDA/07/25/06/SP/GAL | Mulana Nagenahira ha Panwila Grama Niladari Wasam Sambandha wana athuru Margaya | Star Light Construction | Completed | 100% |  | 100% |  | 0 | IPC
331 | RR/RDA/07/25/08/SP/GAL | Mahajana Mawatha Magurukaduwa Margaya Elpitiya Pitigala Pradhana Margaye sita Magurukaduwa Awasanaya dakwa Concrete athura Sanwardanaya Kirima | EHL Constructions | Completed | 100% |  | 100% |  | 0 | IPC
332 | RR/RDA/07/25/09/SP/GAL | Panwila Hena Pradhana Margaya Lalith Mahathage Niwasa Asala Sita Manjula Jayaweera Mahathage Niwasa Dakwa Margaya | DGSD Construction | 323 Days in Delay | 100% |  |  |  | 0 | IPC
333 | RR/RDA/07/25/11/SP/GAL | Elathota Pituwara Margaya Depasa Kanu ha Pathi Bami Yoda Carpet Kirima | Jayathissa Construction | Completed | 100% |  | 100% |  | 0 | IPC
334 | RR/RDA/07/25/12/SP/GAL | Galandeniya Margaya | Star Light Construction | Completed | 100% |  | 100% |  | 0 | IPC
335 | RR/RDA/07/25/13/SP/GAL | Aganaketiya Anuruddagama Mansandiye sita Samagipura dakwa Pradana Maragaya | EHL Constructions | No schedule |  |  | 0% |  | 0 | IPC
336 | RR/RDA/07/25/15/SP/GAL | Dikhena Margaya | Thilak Kumara Builders | Completed | 100% |  | 100% |  | 0 | IPC
337 | RR/RDA/07/25/17/SP/GAL | Dasa Kadaya Asala sita Jack Fruit Ceylon (Pvt) ayathanaya dakwa Margaya 1 Km carpert kirima | P.H. Engineering Construction (Pvt) Ltd | 323 Days in Delay | 100% |  |  |  | 0 | IPC
338 | RR/RDA/07/25/19/SP/GAL | SuriEla Margaya | A.D. Herath Engineering | 300 Days in Delay | 100% |  |  |  | 0 | IPC
339 | RR/RDA/07/25/20/SP/GAL | Road from Kammale Kadaya Junction to Udumalagala Juunction | Kumarage Enterprises(Pvt)Ltd | Completed | 100% |  | 100% |  | 0 | IPC
340 | RR/RDA/07/26/10KM/05 | Widening and Development of the road from Angaliya Junction to Akuratiya Hill with culverts | EHL Constructions | 44 days left | 64.4% |  |  |  | 0 | IPC
341 | RR/RDA/07/26/10KM/08 | Development of 700 meters from Baddegama Vanduramba Road near Kola Kids Preschool and 300 meters from Temple Junction towards Dolahena | Kumarage Enterprises(Pvt)Ltd | 42 days left | 64.4% |  |  |  | 0 | IPC
342 | RR/RDA/07/26/10KM/12 | 9 Pillar Junction to Mr. Asanka's Shop on Udubattawa Watta Road | Kumarage Enterprises(Pvt)Ltd | 42 days left | 64.4% |  |  |  | 0 | IPC
343 | RR/RDA/07/26/10KM/14 | Kodagoda Thudugala Road | Jayathissa Construction | 44 days left | 64.4% |  |  |  | 0 | IPC
344 | RR/RDA/07/26/10KM/18 | Expansion of Alikehena Road from Thalawa Junior College to Atakohota border | S.A.Construction | 50 days left | 54.8% |  |  |  | 0 | IPC
345 | RR/RDA/07/26/10KM/20 | Development of Paramount City Road. | EHL Constructions | 47 days left | 54.8% |  |  |  | 0 | IPC
346 | RR/RDA/07/26/10KM/21 | Concretisation of Dikhena Welamedda road up to Addunkelle with 2 culverts and side walls on both sides. | Isula Construction | 47 days left | 54.8% |  |  |  | 0 | IPC
347 | RR/RDA/07/26/10KM/22 | Kapalwila Olympus Waththa I.K. Road from Mr. Sunil's house to Rakshana Village Bodhi near Ketagoda Kada. | Woshitha Engineering(Pvt)Ltd | 44 days left | 64.4% |  |  |  | 0 | IPC
348 | RR/RDA/25/08/03/SP/MTR | Wattakgoda Ayurvedha Rohala Margaya Sanwardanay kirima | Visula Construction | Completed | 100% |  | 100% |  | 0 | IPC
349 | RR/RDA/25/08/08/SP/MTR | Asmagoda Galabadahena Margaya Sanwardanaya Palamu Adiyara | Induwara Construction | Completed | 100% |  | 100% |  | 0 | IPC
350 | RR/RDA/25/08/10/SP/MTR | Arapotha Belideniya Margaya Carpet athura Sanwardanaya Kirima | Rathna Construction | Completed | 100% |  | 100% |  | 0 | IPC
351 | RR/RDA/25/08/12/SP/MTR | Nawalahena Palamu Para Sanwardanaya Kirima (Jagath Mahathage Niwasa asala sita Kuruppu Mahathage Niwasa Dakwa) | Rathnayake Construction | Completed | 100% |  | 100% |  | 0 | IPC
352 | RR/RDA/08/25/13/SP/MTR | Heelakanda Kanishta Vidyalaya asala sita Budu Medura Dakwa margaya Sanwardanaya Kirima | Madurapperuma Construction & Supply | Completed | 100% |  | 100% |  | 0 | IPC
353 | RR/RDA/08/25/14/SP/MTR | Kanaththewatta kade asala sita Mulana Ela Margaya Dakwa Sanwardanaya Kirima (Pethibemi Sahithawa) | Madurapperuma Construction & Supply | Completed | 100% |  | 100% |  | 0 | IPC
354 | RR/RDA/08/25/15/SP/MTR | Pasal Mawathe Weerathunga Petti Bokkuwa Asala Sita Iriyagaha Mulana Bokkuwa Dakwa Pethi Bemi yoda Sanwardanaya Kirima | Madurapperuma Construction & Supply | Completed | 100% |  | 100% |  | 0 | IPC
355 | RR/RDA/08/25/16/SP/MTR | Walgama Saddathissa Mawathe Primesity Niwasa Sankeernaye Prawesha Margaya Kapat yoda Sanwardanaya kirima | Jagath construction | Completed | 100% |  | 100% |  | 0 | IPC
356 | RR/RDA/08/25/18/SP/MTR | Dekatukella Margaya Pethibemma sahithawa Sanwardanaya kirima | Dashodhaya (Pvt)Ltd | 300 Days in Delay | 100% |  |  |  | 0 | IPC
357 | RR/RDA/08/25/19/SP/MTR | Sahakara wathu Adikari nila niwasa asala sita koppara weediya pittaniya dakwa margaya Sanwardanaya kirima | Gamage Builders | Completed | 100% |  | 100% |  | 0 | IPC
358 | RR/RDA/08/25/20/SP/MTR | Naymbala kendawala haraha wellethota margaye wedugoda sthanaye pethi bemma sahithawa Sanwardanaya kirima | Rathnayake Construction | Completed | 100% |  | 100% |  | 0 | IPC
359 |  | Development of the road by laying Asphalt starting from near Saddhatissa Junior College on the Panattiyana-Weligama road up to Barawadeniya Junction | GEL Construction | No schedule |  |  | 0% |  | 0 | IPC
360 |  | Development of the Pathegama Temple Road (Massalatiya Road) by carpeting | GEL Construction | No schedule |  |  | 0% |  | 0 | IPC
361 | RR/RDA/09/25/08/SP/HMB | Carpeting Pissubedda Medagamgoda road | Samarasinghe Construction(Pvt)Ltd | 138 Days in Delay | 100% |  |  |  | 0 | IPC
362 | RR/RDA/09/25/09/SP/HMB | Development of the road in front of Godawela School to Ambussa Wela | A.T.L. Construction | 104 Days in Delay | 100% |  |  |  | 0 | IPC
363 | RR/RDA/09/25/11/SP/HMB | Development of Walasmulla Daluwakgoda School Road | Samarasinghe Construction(Pvt)Ltd | 62 Days in Delay | 100% |  |  |  | 0 | IPC
364 | RR/RDA/09/25/13/SP/HMB | Development of the road from Puak Dandawa near Aligerappa house through Weerasijahagoda to Satinamaluwa Kapuduarawatta field. | A.T.L. Construction | 105 Days in Delay | 100% |  |  |  | 0 | IPC
365 | RR/RDA/09/26/01 | From near the Bedigama North Health Center to Indimandiya | Isula Construction | 50 days left | 54.8% |  |  |  | 0 | IPC
366 | RR/RDA/22/25/01/UP/BDL | Kirikoonthenna Gamata piwisena Margaya | Ema Constructions (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
367 | RR/RDA/22/25/02/UP/BDL | 23 Ela Krushi Margaya | Priyankara Industries and Contractors | Completed | 100% |  | 100% |  | 0 | IPC
368 | RR/RDA/22/25/04/UP/BDL | Buluwa Margaya | Samadhi Construction | Completed | 100% |  | 100% |  | 0 | IPC
369 | RR/RDA/22/25/07/UP/BDL | Tharuna Govipola Margaye ithiri Kotasa Sanwardanaya Kirieema | Samadhi Construction | 264 Days in Delay |  |  | 0% |  | 0 | IPC
370 | RR/RDA/22/25/08/UP/BDL | Maragaha ella Margaya Concrete Kireema | Priyantha Rathnayaka | Completed | 100% |  | 100% |  | 0 | IPC
371 | RR/RDA/22/25/09/UP/BDL | Piyarapandowa Neluwa Margaya | Liyanage Contractors | No schedule |  |  | 10% |  | 0 | IPC
372 | RR/RDA/22/25/12/UP/BDL | Galwelagama Margaye Pansala Asala Kotasa | Priyankara Industries and Contractors | Completed | 100% |  | 100% |  | 0 | IPC
373 | RR/RDA/22/25/14/UP/BDL | Pulleyar Kadura sita Keselwaththa Dakwa Piwisena Athrur Margaya | Priyankara Industries and Contractors | Completed | 100% |  | 100% |  | 0 | IPC
374 | RR/RDA/22/25/15/UP/BDL | Gallulla sita Galwelagama Margaya | Ema Constructions (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
375 | RR/RDA/22/25/18/UP/BDL | Pelgahathenna Vidyalaya asalin Landewela dakwa athi Margaya | Prasad Builders | Completed | 100% |  | 100% |  | 0 | IPC
376 | RR/RDA/22/25/19/UP/BDL | Tholabowaththa sita Meedumpitiya Dakwa yana Athuru Margaya | Priyankara Industries and Contractors | Completed | 100% |  | 100% |  | 0 | IPC
377 | RR/RDA/22/25/22/UP/BDL | Achchupatti Margaya | Priyankara Industries and Contractors | 272 Days in Delay |  |  | 20% |  | 0 | IPC
378 |  | Kiriibban wewa Ayurweda road | U P Ranugge Construction (Pvt) Ltd | Completed | 100% |  | 100% |  | 0 | IPC
379 | RR/RDA/01/25/03/WP/COL | Appropriate development of road from Maligagodella lake crossing near Isuri Motors to junction with Chandrika Kumaratunga Mawatha | Jayasinghe Contractors (Pvt) Ltd. | Completed | 100% |  | 100% |  | 0 | IPC
380 | RR/RDA/01/25/14/WP/COL | Development of the section from Arangala Bridge to Mihindu Mawatha in Malabe West Division | W.A. Perera & Company (Pvt) Ltd. | 176 Days in Delay |  |  | 68% |  | 0 | IPC
381 | RR/RDA/01/25/09/WP/COL | Kottawa Malabe Road Sirimalwatta 1 Main road carpeted and developed | Accon Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
382 | RR/RDA/01/25/12/WP/COL | 550 A Lakshapathi North Sri Lanka Army Electrical and Mechanical Engineering Base Workshop (Katupedda) to be carpeted and developed from Galle Road. | Accon Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
383 | RR/RDA/01/25/19WP/COL | Puwakpitiya Dharmalapala Mawatha Main Road Development of the road from High Level Road to Elstonwatte Volleyball Court | Asela Construction | 173 Days in Delay |  |  | 90% |  | 0 | IPC
384 | RR/RDA/01/25/26/WP/COL | Boraluwathenna Pahala Uda Road | Next Engineering Services (PVT) LTD | 159 Days in Delay |  |  | 5% |  | 0 | IPC
385 | RR/RDA/01/25/30/WP/COL | Development of the road from near the transformer near Seebara Kade, Boralugoda to the Jayanthi Road | Asset Engineering (Pvt)LTD | 67 Days in Delay |  |  | 0% |  | 0 | IPC
386 | RR/RDA/02/25/05/WP/GMP | Improvements to 70/A Pahala Kandawala Grama Niladharee wasame suuriya mawathe athuru mawathak wana jayashantha mahathaage niwasa asalin athi para praja shaalawa dakwaa saha dakunu pasata thi wiharasthanaya dakwa kotasa | Jeyanthan Construction | Completed | 100% |  | 100% |  | 0 | IPC
387 | RR/RDA/02/25/03/WP/GMP | Development of De silva road beginning from Angurukaramulla temble road to Negombo Colombo road | Dilini Builders (PVT) LTD | 37 Days in Delay | 100% |  |  |  | 0 | IPC
388 | RR/RDA/02/25/08 | Carpeting of the road from near the Buddha Temple towards the Lindara Temple on the Neligama Guru Godella Road started from Halugama Dharmapala Colledge in the Lindara Grama Niladhari Division of the Mirigama Divisional Secretariat. | Wijerathna Construction | 152 Days in Delay |  |  | 20% |  | 0 | IPC
389 |  | The road from Thaladuwa Road near Negombo Bus Stand, passing Jude Church, to the cemetery | Dilini Builders (PVT) LTD | 84 Days in Delay |  |  | 0% |  | 0 | IPC
390 |  | Road from Pinnawatta Junction to Mr. Sandaruwan's shop on the Hapitiya entrance road | Jeyanthan Construction | 106 Days in Delay |  |  | 0% |  | 0 | IPC
391 |  | Udupila South Dolewatta | Creates Consultant and Construction | 113 Days in Delay | 100% |  |  |  | 0 | IPC
392 | RR/RDA/02/25/18/WP/GAM | Peliyagoda Naranminiya Road | Ceylux Civil engineering (Pvt) Ltd | 15 Days in Delay |  |  | 0% |  | 0 | IPC
393 |  | 3 A road carpeted development near the Japanese Montessori at the junction of the North Kadirana Division. | Jeyanthan Construction | 106 Days in Delay |  |  | 0% |  | 0 | IPC
394 |  | 241 B Near Weliweriya North Suruwama Junction to Weliweriya Town | Yagoda Construction | 6 Days in Delay |  |  | 0% |  | 0 | IPC
395 |  | Near Urapana Sisira Coir Mill to Hapugahagama Co-operative | Jeyanthan Construction | 117 Days in Delay |  |  | 0% |  | 0 | IPC
396 | RR/RDA/03/25/02/WP/KTR | Concreting of the first side road on the left side of Rasik Road | Develco Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
397 | RR/RDA/03/25/03/WP/KTR | Carpeting of Uswatta Lane | Ramano Engineers | Completed | 100% |  | 100% |  | 0 | IPC
398 | RR/RDA/03/25/05/WP/KTR | From near Mr. Abeywardena's house on the Yawita Kammalgoda road block stones and development (first phase) | Develco Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
399 | RR/RDA/03/25/08/WP/KTR | Asphalting from near Valkandala transformer to Panthiya Watta (Malamiriskanda road) | Accon Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
400 | RR/RDA/03/25/09/WP/KTR | Concreting of Weedahena road | Develco Engineering (PVT) LTD | Completed | 100% |  | 100% |  | 0 | IPC
401 | RR/RDA/03/25/12/WP/KTR | Concreting Batawala Road | Next Engineering Services (PVT) LTD | 197 Days in Delay |  |  | 39% |  | 0 | IPC
402 |  | Development of 2.64 km section of Neluwa-Karapagala road with carpet | EHL Constructions | No schedule |  |  | 0% |  | 0 | IPC
403 | RR/RDA/03/25/WP/KLT/15 | Development of 1.5 km carpeting of Suduvelipatha Athale road from near Suduvelipatha bodhia towards Athale school | EHL Constructions | No schedule |  |  | 0% |  | 0 | IPC
404 | RR/RDA/03/25/16/WP/KTR | Development of carpeting of 1 km from Gane Aramba Road, Bogalla Junction to Ambepitiya Pinhena | Asela Construction | 124 Days in Delay | 100% |  |  |  | 0 | IPC
405 |  | Development of 0.8 km carpeting of Newfa Mawatha | Develco Engineering (PVT) LTD | 105 Days in Delay |  |  | 0% |  | 0 | IPC
406 | RR/RDA/03/25/18/WP/KTR | Development of carpeting of the section (length 800 m) from near Minerithenna temple to Jananandanarama temple | Asela Construction | 124 Days in Delay | 100% |  |  |  | 0 | IPC
407 |  | Carpeting and development of 500 meters of Moragahakanda watta Bodumaga Senasuna Viharastha Road | Develco Engineering (PVT) LTD | 105 Days in Delay |  |  | 55% |  | 0 | IPC
408 |  | Development of from Lewis Stadium to Heladiva Malshalawa | Develco Engineering (PVT) LTD | 105 Days in Delay |  |  | 55% |  | 0 | IPC
409 | RDA/GOSL/WP/RR/LCB/Pacakge2(KL) | From Addaragoda Weepella Road via Wedigoda, Gulanwatta Nawala Mandagala Road and Boralugoda Thiniyawala Road | RR Construction (Pvt) Ltd. | No schedule |  |  | 0% |  | 0 | IPC
410 | RR/RDA/04/25/42 | Mahanuwara Digana pradana margaye gamudawa jala tankiya asala sita Malgahamula handiya dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
411 | RR/RDA/04/25/45 | Seewalee Kande sits Mahthanna Samadi Senasuna dakwa divena margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
412 | RR/RDA/04/25/18 | Dewaraja Mw (Balance Work) |  | Completed | 100% |  | 100% |  | 0 | IPC
413 | RR/RDA/04/25/30 | Uduwella Ganadevi strachue near the Sahira Estate to Alugolla Road |  | Completed | 100% |  | 100% |  | 0 | IPC
414 | RR/RDA/05/25/03 | Serugolla Middle Road Kanwawala Junction to NawarathnaGoda Main Road |  | Completed | 100% |  | 100% |  | 0 | IPC
415 | RR/RDA/05/25/05 | Near the Old Foodsity to Galwetiyawa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
416 | RR/RDA/06/25/33 | Mool oya Main Road Section 1 |  | Completed | 100% |  | 100% |  | 0 | IPC
417 | RR/RDA/06/25/35 | Gaminipura Road |  | Completed | 100% |  | 100% |  | 0 | IPC
418 | RR/RDA/06/25/36 | CWM Factory Road |  | Completed | 100% |  | 100% |  | 0 | IPC
419 | RR/RDA/04/25/12 | Wattaranthenna Sri Sumangala Mawatha |  | Completed | 100% |  | 100% |  | 0 | IPC
420 | RR/RDA/04/25/37 | Elkaduwa pare sita Japan para sanwardanaya kirima |  | Completed | 100% |  | 100% |  | 0 | IPC
421 | RR/RDA/04/25/40 | Lanka bankuwa asala sita Unambuwa dakwa diwena margaya thara damima |  | Completed | 100% |  | 100% |  | 0 | IPC
422 | RR/RDA/04/25/46 | Gelioya to Pahingamuwa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
423 | RR/RDA/05/25/15 | Salagama margaya Nikagolla margaye sita Boraluwa dakwa |  | Completed | 100% |  | 100% |  | 0 | IPC
424 | RR/RDA/06/25/39 | Madakumbura Dunukedeniya haraha Udagama dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
425 | RR/RDA/04/25/38 | Moladanda handiye sita Mangalagama maima dakwa diwena margaya thara dama sanwardanya |  | Completed | 100% |  | 100% |  | 0 | IPC
426 | RR/RDA/04/25/47 | Manikhinna Hurikaduwa Iththamaliyagoda New Temple Access Road |  | Completed | 100% |  | 100% |  | 0 | IPC
427 | RR/RDA/06/25/43 | Development of Ponnagar Road |  | Completed | 100% |  | 100% |  | 0 | IPC
428 | RR/RDA/06/25/44 | Carpeting of Muloya Main Road Section 2 |  | 308 Days in Delay | 100% |  |  |  | 0 | IPC
429 | RR/RDA/06/25/47 | Carpeting of the road from Gatakula to Madanwala via Diaudagama, Kottala |  | 308 Days in Delay | 100% |  |  |  | 0 | IPC
430 | RR/RDA/06/25/48 | Development of road in front of Divisional Secretariat East of Sangiripalayam Kothmale |  | Completed | 100% |  | 100% |  | 0 | IPC
431 | RR/RDA/06/25/52 | Development of Chandra Lal Karunarathne Mawatha |  | Completed | 100% |  | 100% |  | 0 | IPC
432 | RR/RDA/05/25/23 | Manchanayake shed eka asala sita sampath waththa haraha Galketiyawa margaya |  | 144 Days in Delay | 100% |  |  |  | 0 | IPC
433 | RR/RDA/05/25/28 | Adawala Udagama Road |  | 255 Days in Delay | 100% |  |  |  | 0 | IPC
434 | RR/RDA/16/25/05 | Jannah Road from Annor Road to Jannah Mosque Junction |  | Completed | 100% |  | 100% |  | 0 | IPC
435 | RR/RDA/16/25/06 | Improvement of Mosque Lane from beach Road to Jummah Mosque Lane (0+500)m |  | Completed | 100% |  | 100% |  | 0 | IPC
436 | RR/RDA/SP/16/25/02 | Karana junction south pahalawela palanoya road (From near Pahalalanda post office junction to Karanagama) |  | Completed | 100% |  | 100% |  | 0 | IPC
437 | RR/RDA/16/25/02 | Muwagammana First Lane to Cemetry |  | Completed | 100% |  | 100% |  | 0 | IPC
438 | RR/RDA/STA II/17/25/01 | Hira Village Road |  | Completed | 100% |  | 100% |  | 0 | IPC
439 | RR/RDA/16/25/10KM/10 | Imam Roomy School Road |  | Completed | 100% |  | 100% |  | 0 | IPC
440 | RR/RDA/16/25/10KM/12 | Kalyana Road |  | Completed | 100% |  | 100% |  | 0 | IPC
441 | RR/RDA/15/25/08 | Kumpila Madu Road |  | Completed | 100% |  | 100% |  | 0 | IPC
442 | RR/RDA/17/25/04 | Cemetry Road (Poompuhr) |  | Completed | 100% |  | 100% |  | 0 | IPC
443 | RR/RDA/15/25/10 | Concreting to Internal at MMV School |  | 354 Days in Delay | 100% |  |  |  | 0 | IPC
444 | RR/RDA/17/25/17 | Furkaniya Marcus connection road (S.M.Unithu house to Market main road) |  | Completed | 100% |  | 100% |  | 0 | IPC
445 | RR/RDA/17/25/08 | Concreting of Play Ground Road Mahadiulwewa Stage II |  | 218 Days in Delay | 100% |  |  |  | 0 | IPC
446 | RR/RDA/20/25/02 | Anuradhapura - Kurunegala pradana pare paththara kade handiyen aramba vee kodigala dakwa diwena margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
447 | RR/RDA/20/25/07 | Road from A9 main road to Karapikkada Carpet Road (0+290 - 0+960) |  | Completed | 100% |  | 100% |  | 0 | IPC
448 | RR/RDA/20/25/15 | Dikediyaya mahaweli pradhana ele sita galewela pradhana margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
449 | RR/RDA/21/25/02 | 273 Idama Sita Katuwavila Main Road |  | Completed | 100% |  | 100% |  | 0 | IPC
450 | RR/RDA/21/25/05 | Ketayam Kade asala sita Rampanam oya Dhakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
451 | RR/RDA/20/25/21 | Pawithrapura Road |  | Completed | 100% |  | 100% |  | 0 | IPC
452 | RR/RDA/20/25/08 | Jaya mawatha sita Kaththaragama pansala dakwa margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
453 | RR/RDA/20/25/09 | Padavi para Rambukepuwewa mansandiye sita Elapath wewa margaya dakwa margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
454 | RR/RDA/21/25/01 | Ganangolla pradhana para sihala moola asala sita sirisena mahathage niwasa dakwa margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
455 | RR/GA/21/25/CC/13 | Sathutugama Nidahas mawatha sanwardhanaya kireema |  | Completed | 100% |  | 100% |  | 0 | IPC
456 | RR/RDA/20/25/17 | Galwaduwawa Junction to Yaya 02 road of Thambuththegama Eppawala Road |  | Completed | 100% |  | 100% |  | 0 | IPC
457 | RR/RDA/20/25/24 | Konketiyawa School to Mayilankulama Vilage road |  | Completed | 100% |  | 100% |  | 0 | IPC
458 | RR/RDA/21/25/AC/15 | Aralaganwila Allewewa road Balance Section |  | Completed | 100% |  | 100% |  | 0 | IPC
459 | RR/GA/21/25/CC/12 | Girithale janapadaya pasal mawatha carpet kara ithiri kotasa wana D.G. Jayasiri mahathage niwasa asala sita Akkara 15 handiya Jhon Raja mahathage niwasa dakwa margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
460 | RR/RDA/21/25/16 | Diyabeduma to Jamburewela Road |  | Completed | 100% |  | 100% |  | 0 | IPC
461 | RR/RDA/21/25/28 | Development of the road Sathutugama nidahas Mawatha Balance Section from the house of Mr. Lahiru Madhusanka to the house of Mr. Navaratne in the area of ​​Giritale. |  | Completed | 100% |  | 100% |  | 0 | IPC
462 | RR/RDA/20/25/19 | Thalawa Tsunami junction to Indigaspathana road of Padeniya Anuradhapura Road |  | Completed | 100% |  | 100% |  | 0 | IPC
463 | RR/RDA/20/25/23 | Megichchawa Junction to Temple Road (Kulumeewakada Junction) |  | Completed | 100% |  | 100% |  | 0 | IPC
464 | RR/RDA/20/26/23 | First phase of Priman Mawatha via the by-road behind Kumbichchankulama tank |  | No schedule |  |  | 0% |  | 0 | IPC
465 | RR/RDA/21/25/25 | School Main Road (Old Jumma Mosque Road) |  | Completed | 100% |  | 100% |  | 0 | IPC
466 | RR/RDA/21/25/17 | Hingurakgoda Samupakara Road to Bubula |  | No schedule |  |  | 80% |  | 0 | IPC
467 | RR/RDA/21/25/46 | Girithale janapadaya pasal mawatha starting Section |  | Completed | 100% |  | 100% |  | 0 | IPC
468 | RR/RDA/18/25/12 | Anura Mahaththayalage niwase sita Nalalida dakwa kadurugaha ela dakwa margaya (Ganewatte) |  | Completed | 100% |  | 100% |  | 0 | IPC
469 | RR/RDA/18/25/05 | 158 Digana Grama niladari wasame 3 patumaga (vawa dakwa) (Yapahuwa) |  | Completed | 100% |  | 100% |  | 0 | IPC
470 | RR/RDA/18/25/23 | Horagasagara Nawarathna handiye sita Ihala kadigamuwa handiya dakwa margaya (Bingiriya) |  | Completed | 100% |  | 100% |  | 0 | IPC
471 | RR/RDA/18/25/99 | Rajanganaya reservoir to Parakumpura Junction (Left bank Road) |  | Completed | 100% |  | 100% |  | 0 | IPC
472 | RR/RDA/19/25/09 | Water front Mawatha (wennappuwa) |  | Completed | 100% |  | 100% |  | 0 | IPC
473 | RR/RDA/19/25/03 | Nawagattegama Rohala Pare sita Thapal Karyalaya Dakwa margaya (Nawagattegama) |  | Completed | 100% |  | 100% |  | 0 | IPC
474 | RR/RDA/18/25/06 | Walaliya Piduruwellewa road to the middle of the village |  | Completed | 100% |  | 100% |  | 0 | IPC
475 | RR/RDA/18/25/17 | No. 245 from near Jeevan Lasantha's house no. 37 Development of the main road up to Mr. Nihal's house with five (5) side roads. |  | Completed | 100% |  | 100% |  | 0 | IPC
476 | RR/RDA/18/25/21 | Wattakkawatta Road - Paving of Road (ABC Paving) from near Kelimune Pustalaya. |  | Completed | 100% |  | 100% |  | 0 | IPC
477 | RR/RDA/18/25/103 | Wellawa Thalatuwa Junction to Gepellawa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
478 | RR/RDA/18/25/105 | Thihawa Junction to Mailamada |  | Completed | 100% |  | 100% |  | 0 | IPC
479 | RR/RDA/19/25/02 | Concrete development of the road from Hopper Kada junction to Elu Farm. |  | Completed | 100% |  | 100% |  | 0 | IPC
480 | RR/RDA/19/25/07 | Development of the road from near Kalegama School to Erungwila. |  | Completed | 100% |  | 100% |  | 0 | IPC
481 | RR/RDA/19/25/25 | Development of Mada Koswadiya Bogaha Road |  | Completed | 100% |  | 100% |  | 0 | IPC
482 | RR/RDA/18/25/314 | Road from Nugawela Junction in Walagane to Maspotha Crematorium via Temple |  | Completed | 100% |  | 100% |  | 0 | IPC
483 | RR/RDA/18/25/309 | From near Kongaha in Waudagama on the Katupotha Waudagama Wanduressegama road near Potuwewa Cemetery. |  | No schedule |  |  | 87% |  | 0 | IPC
484 | RR/RDA/18/25/317 | Lakee Land Road in Wilattawa Division |  | Completed | 100% |  | 100% |  | 0 | IPC
485 | RR/RDA/18/25/319 | Kabaledevgama 3rd Lane and 4 Lane in Kaballewa Division of Kaballewa Division |  | Completed | 100% |  | 100% |  | 0 | IPC
486 | RR/RDA/18/25/311 | Road from Kopihena Junction to Dangolla in Damunugala Division of Piduruwella Division |  | Completed | 100% |  | 100% |  | 0 | IPC
487 | RR/RDA/18/25/312 | Junction in front of Narampola Thoraya Muslim College to Budanapartiya Road via Narampola |  | Completed | 100% |  | 100% |  | 0 | IPC
488 | RR/RDA/19/25/36 | Renovation of Warusavithana Laboratory Road |  | No schedule |  |  | 65% |  | 0 | IPC
489 | RR/RDA/19/25/35 | Carpeting & Development of Kolithatissa Mawatha |  | Completed | 100% |  | 100% |  | 0 | IPC
490 | RR/RDA/10/25/21 | 3rd Cross Street |  | Completed | 100% |  | 100% |  | 0 | IPC
491 | RR/RDA/10/25/17 | College Road |  | Completed | 100% |  | 100% |  | 0 | IPC
492 | RR/RDA/12/25/44 | Menicfarm school road (0.5km) (NVVPE97) |  | Completed | 100% |  | 100% |  | 0 | IPC
493 | RR/RDA/13/25/09 | Aninchiyankulam 2nd Lane MUTE095 |  | Completed | 100% |  | 100% |  | 0 | IPC
494 | RR/RDA/11/25/12 | Renovation of Chemmantheevu 4th Cross Street. |  | Completed | 100% |  | 100% |  | 0 | IPC
495 | RR/RDA/10/25/12 | Anaikoddai - Kakaithivu Road |  | Completed | 100% |  | 100% |  | 0 | IPC
496 | RR/RDA/10/25/26 | VC Road No 15 |  | Completed | 100% |  | 100% |  | 0 | IPC
497 | RR/RDA/12/25/06 | Paalavinayagar road |  | Completed | 100% |  | 100% |  | 0 | IPC
498 | RR/RDA/13/25/04 | Suthanthirapuram Main Road Package 1 |  | Completed | 100% |  | 100% |  | 0 | IPC
499 | RR/RDA/11/25/17 | Alakkatu Internal Road 5 |  | Completed | 100% |  | 100% |  | 0 | IPC
500 | RR/RDA/14/25/05 | Kanakapuram school behind road |  | Completed | 100% |  | 100% |  | 0 | IPC
501 | RR/RDA/13/25/05 | Suthanthirapuram Main Road Package 2 |  | Completed | 100% |  | 100% |  | 0 | IPC
502 | RR/RDA/12/25/11 | Madeenanagar road |  | Completed | 100% |  | 100% |  | 0 | IPC
503 | RR/RDA/13/25/02 | Kokkilai Estuary fishing village Road |  | Completed | 100% |  | 100% |  | 0 | IPC
504 | RR/RDA/10/25/23 | Oorany Kudiyetta thidda Veethy |  | Completed | 100% |  | 100% |  | 0 | IPC
505 | RR/RDA/25/24/07 | Godawela Wela Middle Road (Const. side walls) |  | Completed | 100% |  | 100% |  | 0 | IPC
506 | RR/RDA/25/24/15 | D03 Road Near the Yaka Poll |  | Completed | 100% |  | 100% |  | 0 | IPC
507 | RR/RDA/25/24/08 | From Mr.Ranjth's House to Mr.Premasiri's House in Maduwanwela Janapadaya 2nd Lane Road |  | Completed | 100% |  | 100% |  | 0 | IPC
508 | RR/RDA/25/25/16 | Ma dola Jansalu Mawatha Rathnapuara Colombo Road to Welangalla Maha ela Bridge |  | Completed | 100% |  | 100% |  | 0 | IPC
509 | RR/RDA/25/25/17 | Na gahamula Junction to 28 Janapadaya Road |  | Completed | 100% |  | 100% |  | 0 | IPC
510 | RR/RDA/25/24/12 | Siyabalagahayata Junction to Blue Mountain Housing Complex Road |  | Completed | 100% |  | 100% |  | 0 | IPC
511 | RR/RDA/25/24/09 | From Koralegama to Labuwalwaththa Road (From Mr.Pushpananda House) |  | Completed | 100% |  | 100% |  | 0 | IPC
512 | RR/RDA/25/25/18 | Concreting Beragala Army Camp to Beragala 3way Junction VIA Niyadagala |  | Completed | 100% |  | 100% |  | 0 | IPC
513 | RR/RDA/25/25/21 | Kalupahanawaththa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
514 | RR/RDA/25/24/11 | Cinema Hall Road to Dooliyangodella Pitawaththa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
515 | RR/RDA/25/25/30 | Developing the dilapidated section of the lower part of the Pallebage road to the Watte junction |  | Completed | 100% |  | 100% |  | 0 | IPC
516 | RR/RDA/25/24/35 | Ilumba Kanda Road from Milinduthalawa Temple |  | 218 Days in Delay | 100% |  |  |  | 0 | IPC
517 | RR/RDA/25/24/17 | Pahalawaththa to Batahenkanda Road |  | 218 Days in Delay | 100% |  |  |  | 0 | IPC
518 | RR/RDA/25/24/19 | Wijeriya Iththekanda Margaya Sanwardanaya Kirima |  | 218 Days in Delay | 100% |  |  |  | 0 | IPC
519 | RR/RDA/25/24/20 | Godawela Walakada margaya Sanwardanaya Kirima (Walakada Junction to Godawela Junction) |  | 218 Days in Delay | 100% |  |  |  | 0 | IPC
520 | RR/RDA/08/25/Si | Sithulpauwa Rajamaha Viharaye Katharagama Para |  | Completed | 100% |  | 100% |  | 0 | IPC
521 | RR/RDA/07/25/07 | Hapugala batuwanthuda Margaya Pivisume sita Roswudwatta Margaye Kelawara Dakwa Margaya (Jala Tankiya Margaya) |  | Completed | 100% |  | 100% |  | 0 | IPC
522 | RR/RDA/07/25/16 | Mahabodhiwatta sita Pongiliya haraha Vitahna Gedera Ela Dakwa Margaya Ketapathaliya Bokkuwa Athuluwa Bokku Sanwardanaya kara Concrete Kirima |  | Completed | 100% |  | 100% |  | 0 | IPC
523 | RR/RDA/25/08/07 | Ovitigamuwa Alahenpita margaya Sanwardanaya Kirima (RDA yatathe Idikirima Arambha kara atharamaga nawatha etha) |  | Completed | 100% |  | 100% |  | 0 | IPC
524 | RR/RDA/25/08/01 | Kajjuhena Margaya Sanwardanaya Kirima (Kajjuhena Handiya Sita Alikavila Budu Madura Dakwa ) I adiyara |  | Completed | 100% |  | 100% |  | 0 | IPC
525 | RR/RDA/08/25/04 | Vigamuwa Pattiyapola Road from Vigamuwa School |  | Completed | 100% |  | 100% |  | 0 | IPC
526 | RR/RDA/09/25/01 | Karametiya Road |  | Completed | 100% |  | 100% |  | 0 | IPC
527 | RR/RDA/07/25/03 | Wackwella Palama asala sita aranbe handiya dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
528 | RR/RDA/07/25/04 | Galwehera C.P. the Silva Mawatha Carpet kirima |  | Completed | 100% |  | 100% |  | 0 | IPC
529 | RR/RDA/07/25/18 | Agaliya Uthura Tranformaraya Sita Savanna Wella desata Margaya Interlock Kirima |  | Completed | 100% |  | 100% |  | 0 | IPC
530 | RR/RDA/25/08/06 | Samarasinghe Mawathw Ithiri Kotasa Sanwardanaya Kirima |  | Completed | 100% |  | 100% |  | 0 | IPC
531 | RR/RDA/25/08/11 | Thambagala Margaya Sanwardanaya Kirima (Highway pitawime sthanayen arambha vi Pradeepa Mahathmiyage Niwasa dakwa Kotasa) |  | Completed | 100% |  | 100% |  | 0 | IPC
532 | RR/RDA/09/25/02 | Wam Iwura Janawasa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
533 | RR/RDA/08/25/23 | Epitakaduwa Krishantha Senarath Yapa Road (Eptakaduwa Budu medura to Mr. LG Jagath Yapa home) |  | Completed | 100% |  | 100% |  | 0 | IPC
534 | RR/RDA/07/25/14 | Moonugoda Road |  | Completed | 100% |  | 100% |  | 0 | IPC
535 | RR/RDA/08/25/05 | Koggalla bus stand to Sooriyawewa Road |  | 323 Days in Delay | 100% |  |  |  | 0 | IPC
536 | RR/RDA/07/25/22 | Asphalting Meepawala henegewaththa road |  | Completed | 100% |  | 100% |  | 0 | IPC
537 | RR/RDA/07/25/21 | Asphalting Newungala Na tree to Bedimeda road |  | Completed | 100% |  | 100% |  | 0 | IPC
538 | RR/RDA/07/25/01 | Keselgahahena Pradana Margaya (Kanu Paddathiya Bokku Samaga) |  | No schedule |  |  | 98% |  | 0 | IPC
539 | RR/RDA/08/25/22 | Kirinda Roundabout Road with drainages |  | Completed | 100% |  | 100% |  | 0 | IPC
540 | RR/RDA/08/25/02 | Andaledduwa Road |  | Completed | 100% |  | 100% |  | 0 | IPC
541 | RR/RDA/09/25/12 | Development of the road from Lunugamwehera Jadura Lake to Udaeva |  | No schedule |  |  | 92% |  | 0 | IPC
542 | RR/RDA/09/25/06 | Raluwa main road |  | No schedule |  |  | 70% |  | 0 | IPC
543 | RR/RDA/09/25/07 | Carpeting Dabewelena Gravel Road |  | 308 Days in Delay | 100% |  |  |  | 0 | IPC
544 | RR/RDA/09/25/14 | Development of road near Olu ara School |  | No schedule |  |  | 90% |  | 0 | IPC
545 | RR/RDA/09/25/10 | Development of Valasmulla Pallekanda road from 3 km post to 5 km post |  | No schedule |  |  | 95% |  | 0 | IPC
546 | RR/RDA/22/25/32 | Asphalt laying and Development of Haddaththawa 80 Acre road |  | Completed | 100% |  | 100% |  | 0 | IPC
547 | RR/RDA/22/25/03 | Hubaslinda Meda Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
548 | RR/RDA/22/25/16 | Dameria Handiye sita wathu Karyalaya Dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
549 | RR/RDA/22/26/01 | Rajamawatha Road |  | Completed | 100% |  | 100% |  | 0 | IPC
550 | RR/RDA/23/25/01 | Puwakgoda Uramada Margaya K.M.Thilak Bandara Mahathage niwasa idiripita sita ema Margayema R.M.Punchi Nona Mahathmiyage Niwasa Dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
551 | RR/RDA/23/25/04 | Walawegaga Asala (Nildiya Mankada) Sita Udawalawa Bant eka Dakwa |  | Completed | 100% |  | 100% |  | 0 | IPC
552 | RR/RDA/22/25/13 | Peessa Pradana Margaye Abalan wu Ellanda Marga Kotasa |  | Completed | 100% |  | 100% |  | 0 | IPC
553 | RR/RDA/22/25/10 | Kosgolla Edaru Ulpatha Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
554 | RR/RDA/23/25/03 | Liyangolla Lolla Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
555 | RR/RDA/23/25/02 | Uduwara wewa Handiya sita Athula Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
556 | RR/RDA/01/25/11 | Vijitha Salawa asala sita Kothalawala Vidyalaya Asalin Gothami Viharaya dakva Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
557 | RR/RDA/01/25/07 | 428/B Ihala Kosgama Grama Niladhari Wasame Praja Shalawa Pahala Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
558 | RR/RDA/02/25/02 | Development from the road in front of Kanti Teacher's house onwards to Vivekarama Temple (up to Uruwal Mawatha). |  | Completed | 100% |  | 100% |  | 0 | IPC
559 | RR/RDA/02/25/01 | Heendeniya Dumriya Sthanaya Dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
560 | RR/RDA/02/25/04 | Delpe Kadawara sita Nelumwaththa margaya arambaye sita Dewadasa mahathage niwasa dakwa Margaya |  | Completed | 100% |  | 100% |  | 0 | IPC
561 | RR/RDA/03/25/01 | Asphalting Samagipura Road (LECO office to Maha ela) |  | Completed | 100% |  | 100% |  | 0 | IPC
562 | RR/RDA/03/25/04 | Development of the Kotupathgoda road by asphalting |  | Completed | 100% |  | 100% |  | 0 | IPC
563 | RR/RDA/03/25/36 | 10 Mw T Jayarathne mahathge niwas asala concrete kara nawatha ati sthanaya sita nawa margaya desata |  | Completed | 100% |  | 100% |  | 0 | IPC
564 | RR/RDA/01/25/02 | Paving and developing the road from North Borella Ganga Lower Vivekaramaya Temple to Siwali Lane No. 241/35D. |  | Completed | 100% |  | 100% |  | 0 | IPC
565 | RR/RDA/01/25/06 | Development of Rambutan gahamula Suramya Mawatha using carpet in Magammana East Grama Niladhari Domain |  | Completed | 100% |  | 100% |  | 0 | IPC
566 | RR/RDA/03/25/07 | Carpeting of Shekmadara Road |  | Completed | 100% |  | 100% |  | 0 | IPC
567 | RR/RDA/01/25/17 | Access road to Polgasowita Dikhena Aranya |  | Completed | 100% |  | 100% |  | 0 | IPC
568 | RR/RDA/02/25/07 | Road near Ozon Educational Institiute |  | Completed | 100% |  | 100% |  | 0 | IPC
569 | RR/RDA/03/25/11 | Jilani road in Darga Town |  | Completed | 100% |  | 100% |  | 0 | IPC
570 | RR/RDA/03/25/13 | Morapitiya Aluth Mawatha to 1st mile post via Rankoth lane |  | Completed | 100% |  | 100% |  | 0 | IPC
571 | RR/RDA/01/25/16 | Bangalawa Road from 01st Gate to 04th Gate |  | Completed | 100% |  | 100% |  | 0 | IPC
572 | RR/RDA/02/25/20 | St. Lazarus Road (Depot Road) |  | Completed | 100% |  | 100% |  | 0 | IPC
573 | RR/RDA/03/25/20 | Development of Gemunu Mawatha by laying 500 meters of carpet |  | Completed | 100% |  | 100% |  | 0 | IPC
574 | RR/RDA/01/25/21 | Development of Yakala Cemetery Road up to Welihinda Bridge by carpeting |  | No schedule |  |  | 5% |  | 0 | IPC
575 | RR/RDA/01/25/24 | Development of the road from the beginning of the Horahena road from Wanaguru Mawatha in the Hokandara East Division to the Hokandara Pasmanhandiya with a carpet |  | Completed | 100% |  | 100% |  | 0 | IPC
576 | RR/RDA/01/26/10KM/01 | Development of Honnatthara South Kudamadhuwa Road, Moonamalgahawatte Road up to House No. 138/3 by laying carpet and installing drains. |  | No schedule |  |  | 5% |  | 0 | IPC
577 | RR/RDA/01/26/10KM/04 | Carpeting and development of Vijithapura Liyanage Mawatha and 3rd Lane |  | Completed | 100% |  | 100% |  | 0 | IPC
578 | RR/RDA/01/26/01 | Major Alagiyawanna Road to Welivita Road |  | No schedule |  |  | 5% |  | 0 | IPC
579 | RR/RDA/01/26/05 | Malabe Chandrika Kumarathunga Road |  | No schedule |  |  | 5% |  | 0 | IPC