## Report Builder
Report Builder - Ditwah
Date | 2026-09-07
Contract No. | Contract Name | Province | District | EE Division | Package No. | Scope | LOA Date | Contract Amount | Project Duration (Days) | Planned Work Start | Planned Work Finish | LOA Issued | Agreement | Account Open | Advance Paid | Kick Off | Mobilized to Site | In Progress | Physical Progress % | Planned Progress % | Financial Progress % | Financial Progress (Mn) | Planned Financial (Mn) | IPC/Advance Pending (Mn)
RDA/DRP/CEN/KDY/KAD/11 | Rehabilitation / Improvement of Nawalapitiya - Dolosbage Road ( B -318) ( 10+500 - 19+350 ), Dedugala Dolosbage Road ( B -588) ( 10+100 - 12+410 ) | Central Province | Kandy | Kadugannawa | 4 | Construction of culverts, drain, Retaining structure,Base correction, Asphalt, safety Hand rails. | 2026-03-17 | 193404194.96 | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 0 | 93.8 | 22 | 42.62 | 169.62 | 0
RDA/DRP/CEN/KDY/KAN/14 | Rehabilitation /Improvement of Katugasthota Medawala road ( B 0206)( 0 + 000 - 9+370) | Central Province | Kandy | Kandy | 2 | Construction of Retaining structures, Construction of culverts, | 2026-08-14 | 0 | 182 | 2026-09-01 | 2027-03-01 | Yes | [6 empty] | 0 | 2.9 | 0 | 0 | 0 | 0
RDA/DRP/CEN/KDY/KUN/20 | Rehabilitation / Improvement to Structures on Madolkelle - Kabaragala - Kandenuwara Road (B 257) (4+000 - 8+000) | Central Province | Kandy | Kundasale | 1 | Construction of Retaining wall and Gabion wall | 2026-07-06 | 31558227.98 | 119 | 2026-07-20 | 2026-11-15 | Yes | Yes |  | No | Yes | Yes | Yes | 17 | 38.1 | 0 | 0 | 6.44 | 0
RDA/DRP/CEN/KDY/KUN/21 | Improvement of Pitiyegedara-Waththegama-Iriyagasthenna Road (0+000-5+400) | Central Province | Kandy | Kundasale | 2 | Surface Overlaying and Culvert Construction | 2026-03-12 | 257721453.96 | 182 | 2026-04-30 | 2026-10-28 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 9 | 79 | 21.2 | 54.55 | 149.22 | 0
RDA/DRP/CEN/KDY/KUN/22 | Improvement to Damaged Road Section on Weeragantota - Randenigala Road. (From CH 19+000 To CH 27+200) | Central Province | Kandy | Kundasale | 3 | Gabion Wall Construction and Asphlt Overlaying | 2026-03-12 | 224968435.78 | 182 | 2026-03-25 | 2026-09-23 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 35 | 93.8 | 21.1 | 47.43 | 197.3 | 0
RDA/DRP/CEN/KDY/KUN/25 | Construction of Gabion Retaining Wall on Katugastota Madawala Bamberella Road(LHS 9+600 - 9+655), (15+450 - 15+500), (10+235 - 10+300) and Wattegama Matale road (0+400 - 0+435) | Central Province | Kandy | Kundasale | 6 | Construction of Gabion Retaining Wall | 2026-06-16 | 157909825.01 | 119 | 2026-07-06 | 2026-11-01 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 26 | 55.7 | 21.2 | 33.45 | 54.48 | 0
RDA/DRP/CEN/KDY/KUN/27 | Improvement to Structures on Kandy - Jaffna Road 6+500 - 9+910 | Central Province | Kandy | Kundasale | 8 | Construction of Gabion Wall | 2026-06-16 | 113434139.4 | 119 | 2026-06-30 | 2026-10-27 | Yes | Yes | Yes |  | Yes | Yes | Yes | 30 | 63.2 | 0 | 0 | 46.05 | 23.75
RDA/DRP/CEN/KDY/KUN/29 | Improvement to Structures on Kandy - Mahiyanganaya - Padiyaththalawa Road (24+000-71+500) and Moragahamula victoria damtop | Central Province | Kandy | Kundasale | 10 | Construction of Retaining Walls, "U" Drain and Shoulder Construction | 2026-06-16 | 91559621.04 | 182 | 2026-07-06 | 2027-01-03 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 21 | 27.7 | 20.8 | 19.07 | 11.17 | 7.01
RDA/DRP/CEN/MTL/MTL/32 | Rehabilitation / Improvement of Kandy Jaffna (A-009)(17+710 - 46+450), Thalgodapitiya - Yatawatta - Dombawela (B-409) (15+030 - 26+800), Palapathwela - Galewela Road B-346)(0+000 - 8+100) Roads | Central Province | Matale | Matale | 2 | Shoulder and embankment constructions, surface applications, construction of drainage structures and construction of retaining structures | 2026-03-12 | 292279354.08 | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 61 | 78.1 | 21.2 | 61.9 | 164.55 | 5.27
RDA/DRP/CEN/MTL/MTL/33 | Rehabilitation / Improvement of Wattegama Matale Road (5+280 - 13+160) and Ukuwela Railway station (0+000 - 0+190) | Central Province | Matale | Matale | 3 | Shoulder and embankment construction, surface application, construction of drainage structures and construction of retaining walls | 2026-03-16 | 165006430.79 | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | No | Yes | Yes | Yes | Yes | 23 | 100 | 20.8 | 34.3 | 165.01 | 0
RDA/DRP/CEN/MTL/MTL/35 | Rehabilitation / Improvement of Rattota Gammaduwa Road (7+100 - 11+260) | Central Province | Matale | Matale | 5 | Earth works, base and shoulder work surface application, construction of drainage structures, construction of retaining structures and culvert construction | 2026-03-16 | 266607902.15 | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes |  | Yes | Yes | Yes | Yes | 56 | 78.1 | 20.5 | 54.69 | 150.1 | 0
RDA/DRP/CEN/MTL/MTL/38 | Rehabilitation / Improvement of Kalalpitiya Ukuwela Elkaduwa Road (B 180) (0+000 - 13+470) | Central Province | Matale | Matale | 8 | Earth works, base and shoulder work surface application, construction of drainage structures, construction of retaining structures | 2026-07-06 | 0 | 182 | 2026-07-30 | 2027-01-27 | Yes |  |  |  | Yes | Yes | Yes | 5 | 16.5 | 0 | 0 | 0 | 0
RDA/DRP/CEN/MTL/NAL/49 | Rehabilitation /Improvement of Drains,Hard shoulder & Cash barrier at Naula- Elahera- Pallegama- Hettipola Road (B-312) (8+200-61+240) | Central Province | Matale | Nalanda | 7 | Shoulder work .Drains & Cash barrier | 2026-05-29 | 44706119.13 | 154 | 2026-06-18 | 2026-11-18 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 65 | 54.9 | 19.2 | 8.58 | 15.16 | 5.79
RDA/DRP/CEN/MTL/NAL/51 | Rehabilitation /Improvement of Retaining wall , drains and shoulder construction Bowathenna Access Road (B-064) (0+000-2+410) | Central Province | Matale | Nalanda | 9 | Retaning wall ,Drain and shoulder Constructions | 2026-05-29 | 17458592.78 | 119 | 2026-06-18 | 2026-10-14 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 65 | 76.2 | 18.3 | 3.19 | 9.34 | 2.46
RDA/DRP/CEN/NUE/HAN/57 | Rehabilitation / Improvement of Keerthibandarapura Naranthalawa Road ( B -511 ) ( 0+000 - 4+100 ) | Central Province | NuwaraEliya | Hanguranketha | 7 | Surfacing(Asphalt), Drain,Shoulder,Hard shoulder,Retaning wall Construction | 2026-07-09 | 47755538.96 | 91 | 2026-07-30 | 2026-10-28 | Yes |  |  |  | Yes | Yes | Yes | 2 | 40.9 | 0 | 0 | 10.89 | 0
RDA/DRP/CEN/NUE/NUE/66 | Rehabilitation / Improvement of Nuwara Eliya Town Road (0+000 - 1+695 ) (0+000 - 0+240 ) | Central Province | NuwaraEliya | NuwaraEliya | 7 | Road Marking, U Drain Construction & Culvert Construction | 2026-03-12 | 161841095.7 | 91 | 2026-05-02 | 2026-07-31 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 58 | 100 | 31.8 | 51.43 | 161.84 | 0
RDA/DRP/CEN/NUE/NUE/67 | Rehabilitation / Improvement of Harangala - Kalapitiya - Kumbaloluwa Road (10+480 km - 17+140 km) | Central Province | NuwaraEliya | NuwaraEliya | 8 | Road Marking, U Drain Construction ,Shoulder Construction & Culvert Construction | 2026-03-17 | 239417811.34 | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 62 | 78.1 | 32.6 | 78.16 | 134.79 | 0
RDA/DRP/CEN/NUE/NUE/68 | Rehabilitation / Improvement of Thawalanthenna Thalawakelle Road (0+000 - 8+000) & (10+000 - 33+200) | Central Province | NuwaraEliya | NuwaraEliya | 9 | Asphalt overlay, Retaining wall Construction, U Drain Construction & Culvert Construction | 2026-03-24 | 213999600.01 | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 27 | 78.1 | 21.2 | 45.28 | 120.48 | 0
RDA/DRP/CEN/NUE/NUE/69 | Rehabilitation / Improvement of Ulapane Pussallawa Road (6+440 - 15+950) | Central Province | NuwaraEliya | NuwaraEliya | 10 | Road Marking Retaining wall Construction, Edge Wedining, Drain Construction & Culvert Construction | 2026-03-16 | 266045892.19 | 182 | 2026-05-02 | 2026-10-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | 45 | 78.1 | 29.3 | 77.84 | 149.78 | 12.96
RDA/DRP/CEN/NUE/NUE/86 | Rehabilitation / Improvement of Approch road to R'way station (Watagoda/ Thalawakele) Road | Central Province | NuwaraEliya | NuwaraEliya | 27 | Asphalt overlay, Road Marking Drain Construction | 2026-05-19 | 33765626.86 | 91 | 2026-06-12 | 2026-09-10 | Yes |  |  |  | Yes | Yes | Yes | 8 | 97.5 | 0 | 0 | 32.11 | 0
RDA/DRP/CEN/NUE/NUR/97 | Rehabilitation/Improvement of Nawalapitiya Ginigathena Road (B-319)(7+200-12+200) | Central Province | NuwaraEliya | Norwood | 11 | Asphalt overlay, Road Marking ,Retaining wall Construction,Drain Construction & Culvert Construction. | 2026-05-19 | 93758217.76 | 91 | 2026-06-17 | 2026-09-15 | Yes | Yes | Yes |  | Yes | Yes | Yes | 26 | 93.4 | 0 | 0 | 81.38 | 16.7
RDA/DRP/CEN/NUE/NUR/98 | Rehabilitation/Improvement Harangala Kalapitiya Road (B-148) (0+000-10+700), Approach Road to Hrangala Dam Crest Road (B-491) (0+000-3+820), Nawalapitiya Harangala Road (B-306) (0+000-10+700) | Central Province | NuwaraEliya | Norwood | 12 | Road Marking ,Retaining wall Construction,Drain Construction & Culvert Construction. | 2026-05-19 | 188617394.68 | 182 | 2026-06-18 | 2026-12-16 | Yes |  |  |  | Yes | Yes | Yes | 12 | 42.6 | 0 | 0 | 45.46 | 0
RDA/DRP/CEN/NUE/NUR/101 | Rehabilitation/Improvement of Hatton Maskeliya Delhouse Road (B-149) (0+000-31+970) | Central Province | NuwaraEliya | Norwood | 15 | Asphalt overlay, Road Marking ,Retaining wall Construction,Drain Construction & Culvert Construction. | 2026-05-19 | 86746198.17 | 147 | 2026-06-18 | 2026-11-11 | Yes |  |  |  | Yes | Yes | Yes | 3 | 58.7 | 0 | 0 | 32.1 | 0
RDA/DC/DRP/CP/NE/NRW/02 |  | Central Province | NuwaraEliya | Norwood |  |  | 2026-07-16 | 374859845.1 | 365 | 2026-07-30 | 2027-07-29 | Yes |  |  |  | Yes | Yes | Yes | 2 | 8.2 | 0 | 0 | 12.37 | 0